## work zone analysis
APPENDIX A - Example Problems | [8 empty] | June 2001
Worksheet 3.1: Analysis of the Work Zone
| Work Zone: |  | Off-Peak Hour Lane Reduction |  |  |  |  | Normal Capacity: |  |  | 6300
| Percent Trucks: |  | 10% |  | Percent Cars: | 90% |  | Work Zone/Detour Capacity: |  |  | 3000
| Directional ADT: |  | 50000 |  | Year: | 1999 |  | Lanes Under Normal Operation: |  |  | 3
3.1(A) |  | 3.1(B) | 3.1(C) | 3.1(D) | 3.1(E) | 3.1(F) | 3.1(G) | 3.1(H) | 3.1(I) | 3.1(J) | 3.1(K)
Time Period (hour) |  | Hourly Traffic (%) | Vehicle Demand (vph) | Lanes Open (#) | Roadway Capacity (vph) | Queue Rate (vph) | Queued Vehicles (vph) | Average Queued Vehicles (vph) | Vehicles that Travel Work Zone (vph) | Vehicles that Travel Detour (vph) | Vehicles that Travel Queue (vph) | Absolute Value of Queue Rate
12-1 AM |  | 0.7 | 350 | 2 | 3000 | -2650 | 0 | 0 | 350 | 0 | 0 | 2650
1-2 |  | 0.5 | 250 | 2 | 3000 | -2750 | 0 | 0 | 250 | 0 | 0 | 2750
2-3 |  | 0.4 | 200 | 2 | 3000 | -2800 | 0 | 0 | 200 | 0 | 0 | 2800
3-4 |  | 0.6 | 300 | 2 | 3000 | -2700 | 0 | 0 | 300 | 0 | 0 | 2700
4-5 |  | 1.8 | 900 | 2 | 3000 | -2100 | 0 | 0 | 900 | 0 | 0 | 2100
5-6 |  | 4.4 | 2200 | 2 | 3000 | -800 | 0 | 0 | 2200 | 0 | 0 | 800
6-7 |  | 6.2 | 3100 | 3 | 6300 | -3200 | 0 | 0 | 3100 | 0 | 0 | 3200
7-8 |  | 7.2 | 3600 | 3 | 6300 | -2700 | 0 | 0 | 3600 | 0 | 0 | 2700
8-9 |  | 5.6 | 2800 | 3 | 6300 | -3500 | 0 | 0 | 2800 | 0 | 0 | 3500
9-10 |  | 5 | 2500 | 2 | 3000 | -500 | 0 | 0 | 2500 | 0 | 0 | 500
10-11 |  | 4.8 | 2400 | 2 | 3000 | -600 | 0 | 0 | 2400 | 0 | 0 | 600
11-12 PM |  | 5.1 | 2550 | 2 | 3000 | -450 | 0 | 0 | 2550 | 0 | 0 | 450
12-1 |  | 5.3 | 2650 | 2 | 3000 | -350 | 0 | 0 | 2650 | 0 | 0 | 350
1-2 |  | 5.5 | 2750 | 2 | 3000 | -250 | 0 | 0 | 2750 | 0 | 0 | 250
2-3 |  | 5.6 | 2800 | 2 | 3000 | -200 | 0 | 0 | 2800 | 0 | 0 | 200
3-4 |  | 6.4 | 3200 | 3 | 6300 | -3100 | 0 | 0 | 3200 | 0 | 0 | 3100
4-5 |  | 7 | 3500 | 3 | 6300 | -2800 | 0 | 0 | 3500 | 0 | 0 | 2800
5-6 |  | 6.4 | 3200 | 3 | 6300 | -3100 | 0 | 0 | 3200 | 0 | 0 | 3100
6-7 |  | 5.9 | 2950 | 3 | 6300 | -3350 | 0 | 0 | 2950 | 0 | 0 | 3350
7-8 |  | 4.9 | 2450 | 3 | 6300 | -3850 | 0 | 0 | 2450 | 0 | 0 | 3850
8-9 |  | 4 | 2000 | 2 | 3000 | -1000 | 0 | 0 | 2000 | 0 | 0 | 1000
9-10 |  | 3 | 1500 | 2 | 3000 | -1500 | 0 | 0 | 1500 | 0 | 0 | 1500
10-11 |  | 2.1 | 1050 | 2 | 3000 | -1950 | 0 | 0 | 1050 | 0 | 0 | 1950
11-12 |  | 1.6 | 800 | 2 | 3000 | -2200 | 0 | 0 | 800 | 0 | 0 | 2200
TOTALS |  | 100 | 50000 | [5 empty] | 50000 | 0 | 0
Project: |  |  | EXAMPLE #2 | [5 empty] | Date: | July 1999
Description: |  |  | Off-Peak Hour Lane Reduction, Part A
NJDOT Road User Cost Manual | [10 empty] | A2-2

## work zone am
APPENDIX A - Example Problems | [8 empty] | June 2001
Worksheet 3.1: Analysis of the Work Zone
| Work Zone: |  | One Hour Overrun in AM Lane Reduction |  |  |  |  | Normal Capacity: |  |  | 6300
| Percent Trucks: |  | 10% |  | Percent Cars: | 90% |  | Work Zone/Detour Capacity: |  |  | 3000
| Directional ADT: |  | 50000 |  | Year: | 1999 |  | Lanes Under Normal Operation: |  |  | 3
3.1(A) |  | 3.1(B) | 3.1(C) | 3.1(D) | 3.1(E) | 3.1(F) | 3.1(G) | 3.1(H) | 3.1(I) | 3.1(J) | 3.1(K)
Time Period (hour) |  | Hourly Traffic (%) | Vehicle Demand (vph) | Lanes Open (#) | Roadway Capacity (vph) | Queue Rate (vph) | Queued Vehicles (vph) | Average Queued Vehicles (vph) | Vehicles that Travel Work Zone (vph) | Vehicles that Travel Detour (vph) | Vehicles that Travel Queue (vph) | Absolute Value of Queue Rate
12-1 AM | [11 empty] | 0
1-2 | [11 empty] | 0
2-3 | [11 empty] | 0
3-4 | [11 empty] | 0
4-5 | [11 empty] | 0
5-6 | [11 empty] | 0
6-7 |  | 6.2 | 3100 | 2 | 3000 | 100 | 100 | 50 | 3000 | 0 | 3000 | 100
7-8 | [11 empty] | 0
8-9 | [11 empty] | 0
9-10 | [11 empty] | 0
10-11 | [11 empty] | 0
11-12 PM | [11 empty] | 0
12-1 | [11 empty] | 0
1-2 | [11 empty] | 0
2-3 | [11 empty] | 0
3-4 | [11 empty] | 0
4-5 | [11 empty] | 0
5-6 | [11 empty] | 0
6-7 | [11 empty] | 0
7-8 | [11 empty] | 0
8-9 | [11 empty] | 0
9-10 | [11 empty] | 0
10-11 | [11 empty] | 0
11-12 | [11 empty] | 0
TOTALS |  | 6.2 | 3100 | [5 empty] | 3000 | 0 | 3000
Project: |  |  | EXAMPLE #2 | [5 empty] | Date: | July 1999
Description: |  |  | Off-Peak Hour Lane Reduction, Part B (AM)
NJDOT Road User Cost Manual | [10 empty] | A2-3

## work zone pm
APPENDIX A - Example Problems | [8 empty] | June 2001
Worksheet 3.1: Analysis of the Work Zone
| Work Zone: |  | One Hour Overrun in PM Lane Reduction |  |  |  |  | Normal Capacity: |  |  | 6300
| Percent Trucks: |  | 10% |  | Percent Cars: | 90% |  | Work Zone/Detour Capacity: |  |  | 3000
| Directional ADT: |  | 50000 |  | Year: | 1999 |  | Lanes Under Normal Operation: |  |  | 3
3.1(A) |  | 3.1(B) | 3.1(C) | 3.1(D) | 3.1(E) | 3.1(F) | 3.1(G) | 3.1(H) | 3.1(I) | 3.1(J) | 3.1(K)
Time Period (hour) |  | Hourly Traffic (%) | Vehicle Demand (vph) | Lanes Open (#) | Roadway Capacity (vph) | Queue Rate (vph) | Queued Vehicles (vph) | Average Queued Vehicles (vph) | Vehicles that Travel Work Zone (vph) | Vehicles that Travel Detour (vph) | Vehicles that Travel Queue (vph) | Absolute Value of Queue Rate
12-1 AM | [11 empty] | 0
1-2 | [11 empty] | 0
2-3 | [11 empty] | 0
3-4 | [11 empty] | 0
4-5 | [11 empty] | 0
5-6 | [11 empty] | 0
6-7 | [11 empty] | 0
7-8 | [11 empty] | 0
8-9 | [11 empty] | 0
9-10 | [11 empty] | 0
10-11 | [11 empty] | 0
11-12 PM | [11 empty] | 0
12-1 | [11 empty] | 0
1-2 | [11 empty] | 0
2-3 | [11 empty] | 0
3-4 |  | 6.4 | 3200 | 2 | 3000 | 200 | 200 | 100 | 3000 | 0 | 3000 | 200
4-5 | [11 empty] | 0
5-6 | [11 empty] | 0
6-7 | [11 empty] | 0
7-8 | [11 empty] | 0
8-9 | [11 empty] | 0
9-10 | [11 empty] | 0
10-11 | [11 empty] | 0
11-12 | [11 empty] | 0
TOTALS |  | 6.4 | 3200 | [5 empty] | 3000 | 0 | 3000
Project: |  |  | EXAMPLE #2 | [5 empty] | Date: | July 1999
Description: |  |  | Off-Peak Lane Reduction, Part B (PM)
NJDOT Road User Cost Manual | [10 empty] | A2-4

## queue delay off-peak
APPENDIX A - Example Problems | [12 empty] | June 2001
Worksheet 3.2: Queue Delay
| 3.2(A) | 3.2(B) |  | 3.2(C) |  | 3.2(D) |  | 3.2(E) |  | 3.2(F) |  | 3.2(G) |  |  | 3.2(H)
| Queue Period (hour) | Queue Volume (veh/hr) |  | Normal Capacity (veh/hr) |  | V/C Ratio |  | Average Queue Speed (mph) |  | Unrestricted Speed (mph) |  | Average Queued Vehicles per Queue Period (#) |  |  | Queue Lanes (#)
1 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  | 0
2
3
4
5
| 3.2(I) | 3.2(J) |  | 3.2(K) |  |  | 3.2(L) |  | 3.2(M) |  | 3.2(N) |  |  | 3.2(O)
| Average Vehicle Length (feet/veh) | Average Queue Length (mile) |  | Queue Travel Time at Unrestricted Speed (hr/veh) |  |  | Queue Travel Time at Queue Speed (hr/veh) |  | Added Time to Travel Queue (hr/veh) |  | Affected Vehicles per Queue Period (#) |  |  | Added Time per Queue Period (hour)
1 | 0 | 0 |  | 0 |  |  | 0 |  | 0 |  | 0 |  |  | 0
2
3
4
5
[5 empty] | Totals | [5 empty] | 0 |  |  | 0
[5 empty] | Added Time Weighted Average | [5 empty] | 0 |  |  | hr/veh
| Project: |  | EXAMPLE #2 | [8 empty] | Date: | July 1999
| Description: |  | Off-Peak Hour Lane Reduction, Part A
NJDOT Road User Cost Manual | [15 empty] | A2-5

## queue delay am
APPENDIX A - Example Problems | [12 empty] | June 2001
Worksheet 3.2: Queue Delay
| 3.2(A) | 3.2(B) |  | 3.2(C) |  | 3.2(D) |  | 3.2(E) |  | 3.2(F) |  | 3.2(G) |  |  | 3.2(H)
| Queue Period (hour) | Queue Volume (veh/hr) |  | Normal Capacity (veh/hr) |  | V/C Ratio |  | Average Queue Speed (mph) |  | Unrestricted Speed (mph) |  | Average Queued Vehicles per Queue Period (#) |  |  | Queue Lanes (#)
1 | 6AM - 7AM | 3000 |  | 6300 |  | 0.48 |  | 10 |  | 55 |  | 50 |  |  | 3
2
3
4
5
| 3.2(I) | 3.2(J) |  | 3.2(K) |  |  | 3.2(L) |  | 3.2(M) |  | 3.2(N) |  |  | 3.2(O)
| Average Vehicle Length (feet/veh) | Average Queue Length (mile) |  | Queue Travel Time at Unrestricted Speed (hr/veh) |  |  | Queue Travel Time at Queue Speed (hr/veh) |  | Added Time to Travel Queue (hr/veh) |  | Affected Vehicles per Queue Period (#) |  |  | Added Time per Queue Period (hour)
1 | 50 | 0.16 |  | 0.003 |  |  | 0.016 |  | 0.013 |  | 3000 |  |  | 39
2
3
4
5
[5 empty] | Totals | [5 empty] | 3000 |  |  | 39
[5 empty] | Added Time Weighted Average | [5 empty] | 0.013 |  |  | hr/veh
| Project: |  | EXAMPLE #2 | [8 empty] | Date: | July 1999
| Description: |  | Off-Peak Hour Lane Reduction, Part B (AM)
NJDOT Road User Cost Manual | [15 empty] | A2-6

## queue delay pm
APPENDIX A - Example Problems | [11 empty] | June 2001
Worksheet 3.2: Queue Delay
| 3.2(A) | 3.2(B) |  | 3.2(C) |  | 3.2(D) |  | 3.2(E) |  | 3.2(F) |  | 3.2(G) |  |  | 3.2(H)
| Queue Period (hour) | Queue Volume (veh/hr) |  | Normal Capacity (veh/hr) |  | V/C Ratio |  | Average Queue Speed (mph) |  | Unrestricted Speed (mph) |  | Average Queued Vehicles per Queue Period (#) |  |  | Queue Lanes (#)
1 | 3PM - 4PM | 3000 |  | 6300 |  | 0.48 |  | 10 |  | 55 |  | 100 |  |  | 3
2
3
4
5
| 3.2(I) | 3.2(J) |  | 3.2(K) |  |  | 3.2(L) |  | 3.2(M) |  | 3.2(N) |  |  | 3.2(O)
| Average Vehicle Length (feet/veh) | Average Queue Length (mile) |  | Queue Travel Time at Unrestricted Speed (hr/veh) |  |  | Queue Travel Time at Queue Speed (hr/veh) |  | Added Time to Travel Queue (hr/veh) |  | Affected Vehicles per Queue Period (#) |  |  | Added Time per Queue Period (hour)
1 | 50 | 0.32 |  | 0.006 |  |  | 0.032 |  | 0.026 |  | 3000 |  |  | 78
2
3
4
5
[5 empty] | Totals | [5 empty] | 3000 |  |  | 78
[5 empty] | Added Time Weighted Average | [5 empty] | 0.026 |  |  | hr/veh
| Project: |  | EXAMPLE #2 | [8 empty] | Date: | July 1999
| Description: |  | Off-Peak Lane Reduction, Part B (PM)
NJDOT Road User Cost Manual | [15 empty] | A2-7

## wz and circuity delay
APPENDIX A - Example Problems | [8 empty] | June 2001
Worksheet 3.3: Work Zone and Circuity (Detour) Delays
Work Zone Delay
3.3(A) |  | 3.3(B) |  | 3.3(C) |  | 3.3(D) |  | 3.3(E) |  |  |  | 3.3(F)
Work Zone Length (mile) |  | Work Zone Speed (mph) |  | Unrestricted Speed (mph) |  | Work Zone Travel Time at Unrestricted Speed (hr/veh) |  | Work Zone Travel Time at Work Zone Speed (hr/veh) |  |  |  | Added Time to Travel Work Zone (hr/veh)
3 |  | 45 |  | 55 |  | 0.055 |  | 0.067 |  |  |  | 0.012
Circuity (Detour) Delay
3.3(G) |  | 3.3(H) |  | 3.3(I) |  | 3.3(J) |  | 3.3(K) |  |  |  | 3.3(L)
Travel Length without Detour (mile) |  | Travel Length with Detour (mile) |  | Added Travel Length (mile) |  | Travel Time without Detour (hr/veh) |  | Travel Time with Detour (hr/veh) |  |  |  | Added Time to Travel Detour (hr/veh)
0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 0
Alternating Traffic (Flagging) Delay
Flagging Zone Length (mile) | Flagging Zone Speed (mph) |  | Unrestricted Speed (mph) |  | Flagging Zone Travel Time at Unrestricted Speed (hr/veh) |  | Flagging Zone Travel Time at Flagging Zone Speed (hr/veh) |  |  | Added Time to Travel Flagging Zone (hr/veh) |  |  | Approach Vehicle Wait Time (hr/veh)
0 | 0 |  | 0 |  | 0 |  | 0 |  |  | 0 |  |  | 0
Project: | EXAMPLE #2 | [9 empty] | Date: | July 1999
Description: | Off-Peak Hour Lane Reduction, Part A and Part B
NJDOT Road User Cost Manual | [13 empty] | A2-8

## escalation and cost rates
APPENDIX A - Example Problems | [9 empty] | June 2001
Worksheet 3.4: Escalation Factors and Cost Rates
Escalation Factors
3.4(A) |  |  |  |  | 3.4(B) |  | 3.4(C) |  |  |  | 3.4(D)
Cost Factors |  |  |  |  | 1970 (CPI-U) |  | Current (CPI-U)* |  |  |  | Escalation Factor
IDLING and VOC
(transportation component) |  |  |  |  | 37.5 |  | 140.6 |  |  |  | 3.75
TIME VALUE
(all components) |  |  |  |  | 38.8 |  | 165 |  |  |  | 4.25
* CPI-U = Unadjusted Consumer Price Index for all Urban Consumers, US City Average, March 1999
Cost Rates
3.4(E) | 3.4(F) |  | 3.4(G) | 3.4(H) |  | 3.4(I) |  | 3.4(J) |  |  |  | 3.4(K)
Vehicle Class | 1970 Time Value Cost Rate ($/veh-hr) |  | 1970 Idling Cost Rate ($/veh-hr) | 1970 VOC Cost Rate ($/mile) |  | Current Time Value Cost Rate ($/veh-hr) |  | Current Idling Cost Rate ($/veh-hr) |  |  |  | Current VOC Cost Rate ($/mile)
CAR | 3 |  | 0.1819 | 0.06 |  | 12.75 |  | 0.6821 |  |  |  | 0.225
TRUCK | 5 |  | 0.2092 | 0.12 |  | 21.25 |  | 0.7845 |  |  |  | 0.45
Project: |  | EXAMPLE #2 | [6 empty] | Date: | July 1999
Description: |  | Off-Peak Hour Lane Reduction, Part A and Part B
NJDOT Road User Cost Manual | [12 empty] | A2-9

## user costs A
NJDOT Road User Cost Manual | Worksheet 3.5: Road User Costs | [8 empty] | APPENDIX A - Example Problems
| 3.5(A) |  | 3.5(B) | 3.5(C) | 3.5(D) | 3.5(E) | 3.5(F) | 3.5(G) | 3.5(H)
| Road User Cost Component |  | Vehicle Class | Percent Class (%) | Total Vehicles (#) | Added Travel Length (mile/veh) | Added Time (hr/veh) | Cost Rate ($/veh-hr, $/mile) | Road User Cost ($)
| Queue Delay |  | CAR
| (Added Time) |  | TRUCK
| Queue Idling VOC |  | CAR
| (Added Cost) |  | TRUCK
| Work Zone Delay |  | CAR | 90 | 50000 |  | 0.012 | 12.75 | 6885
| (Added Time) |  | TRUCK | 10 | 50000 |  | 0.012 | 21.25 | 1275
| Circuity Delay |  | CAR
| (Added Time) |  | TRUCK
| Circuity VOC |  | CAR
| (Added Cost) |  | TRUCK
| Total Vehicles that Travel Queue: |  |  |  | 0 |  | Daily Road User Cost |  | 8160
| Total Vehicles that Travel Work Zone: |  |  |  | 50000 |  | Calculated Road User Cost (CRUC) |  | 4080
| Total Vehicles that Travel Detour: |  |  |  | 0 |  | Number of Work Zone Days |  | 75 | June 2001
| Percent Passenger Cars: |  |  |  | 90% |  | Total Road User Cost |  | 306000
| Percent Trucks: |  |  |  | 10%
A2-10
| Project: | EXAMPLE #2 | [5 empty] | Date: | July 1999
| Description: | Off-Peak Hour Lane Reduction, Part A

## user costs B(am)
NJDOT Road User Cost Manual | Worksheet 3.5: Road User Costs | [8 empty] | APPENDIX A - Example Problems
| 3.5(A) |  | 3.5(B) | 3.5(C) | 3.5(D) | 3.5(E) | 3.5(F) | 3.5(G) | 3.5(H)
| Road User Cost Component |  | Vehicle Class | Percent Class (%) | Total Vehicles (#) | Added Travel Length (mile/veh) | Added Time (hr/veh) | Cost Rate ($/veh-hr, $/mile) | Road User Cost ($)
| Queue Delay |  | CAR | 90 | 3000 |  | 0.013 | 12.75 | 448
| (Added Time) |  | TRUCK | 10 | 3000 |  | 0.013 | 21.25 | 83
| Queue Idling VOC |  | CAR | 90 | 3000 |  | 0.013 | 0.6821 | 24
| (Added Cost) |  | TRUCK | 10 | 3000 |  | 0.013 | 0.7845 | 3
| Work Zone Delay |  | CAR | 90 | 3000 |  | 0.012 | 12.75 | 413
| (Added Time) |  | TRUCK | 10 | 3000 |  | 0.012 | 21.25 | 77
| Circuity Delay |  | CAR
| (Added Time) |  | TRUCK
| Circuity VOC |  | CAR
| (Added Cost) |  | TRUCK
| Total Vehicles that Travel Queue: |  |  |  | 3000 |  | Daily Road User Cost |  | 1048 | June 2001
| Total Vehicles that Travel Work Zone: |  |  |  | 3000 |  | Calculated Road User Cost (CRUC) |  | 524
| Total Vehicles that Travel Detour: |  |  |  | 0 |  | Number of Work Zone Days |  | 1
| Percent Passenger Cars: |  |  |  | 90% |  | Total Road User Cost |  | 524
| Percent Trucks: |  |  |  | 10%
A2-11
| Project: | EXAMPLE #2 | [5 empty] | Date: | July 1999
| Description: | Off-Peak Hour Lane Reduction, Part B (AM)

## user costs B(pm)
NJDOT Road User Cost Manual | Worksheet 3.5: Road User Costs | [8 empty] | APPENDIX A - Example Problems
| 3.5(A) |  | 3.5(B) | 3.5(C) | 3.5(D) | 3.5(E) | 3.5(F) | 3.5(G) | 3.5(H)
| Road User Cost Component |  | Vehicle Class | Percent Class (%) | Total Vehicles (#) | Added Travel Length (mile/veh) | Added Time (hr/veh) | Cost Rate ($/veh-hr, $/mile) | Road User Cost ($)
| Queue Delay |  | CAR | 90 | 3000 |  | 0.026 | 12.75 | 895
| (Added Time) |  | TRUCK | 10 | 3000 |  | 0.026 | 21.25 | 166
| Queue Idling VOC |  | CAR | 90 | 3000 |  | 0.026 | 0.6821 | 48
| (Added Cost) |  | TRUCK | 10 | 3000 |  | 0.026 | 0.7845 | 6
| Work Zone Delay |  | CAR | 90 | 3000 |  | 0.012 | 12.75 | 413
| (Added Time) |  | TRUCK | 10 | 3000 |  | 0.012 | 21.25 | 77
| Circuity Delay |  | CAR
| (Added Time) |  | TRUCK
| Circuity VOC |  | CAR
| (Added Cost) |  | TRUCK
| Total Vehicles that Travel Queue: |  |  |  | 3000 |  | Daily Road User Cost |  | 1605
| Total Vehicles that Travel Work Zone: |  |  |  | 3000 |  | Calculated Road User Cost (CRUC) |  | 802.5 | June 2001
| Total Vehicles that Travel Detour: |  |  |  | 0 |  | Number of Work Zone Days |  | 1
| Percent Passenger Cars: |  |  |  | 90% |  | Total Road User Cost |  | 802.5
| Percent Trucks: |  |  |  | 10%
A2-12
| Project: | EXAMPLE #2 | [5 empty] | Date: | July 1999
| Description: | Off-Peak Lane Reduction, Part B (PM)