## Guide
New Jersey Broadband Equity Access and Deployment (BEAD)
As of date: July 2, 2026
CONFIDENTIAL: PROPRIETARY, PRELIMINARY, PRE-DECISIONAL, AND DELIBERATIVE ¦ DRAFT, NOT FOR DISTRIBUTION
DOCUMENT INTENDED TO PROVIDE INSIGHT BASED ON CURRENTLY AVAILABLE INFORMATION FOR CONSIDERATION AND NOT SPECIFIC ADVICE. INPUTS BASED ON DISCUSSIONS WITH OBC.
Instructions: NEPA Project Milestone Schedule
This template is to be used to document and track the environmental review milestones required for each project in accordance with NEPA requirements and applicable NTIA guidance. A separate NEPA Project Milestone Schedule must be completed for each individual project area awarded under the Subgrant Agreements. Maintain and update the schedule throughout the project as milestones are completed, permits and consultations progress, and new information becomes available. Submit the most current version with each quarterly report to OBC, and add rows as needed to track any project-specific environmental reviews, consultations, permits, authorizations, or approvals not included in the template.
Find an explanation of each column below:
Tracking Element | This includes the major environmental review milestones, consultations, permits, authorizations, and approvals required to complete each project's environmental review in compliance with NTIA guidance. Not every project will require every item. Grantees should complete the applicable milestones and add rows as needed for project-specific requirements.
Expected Date to Begin Process for Report / Consultation / Permit / Authorization | The anticipated date the subgrantee expects to initiate the process, such as beginning a consultation, preparing a report, or submitting a permit or authorization application. Enter the date in MM/DD/YYYY format.
Expected Date to Complete and Submit Report to Reviewing Agency or Expected Date for Specified Event | The anticipated date the subgrantee expects to complete and submit the required report, permit application, consultation package, or other documentation to the reviewing agency, or when the specified event is expected to occur. Enter the date in MM/DD/YYYY format.
Expected Date of Approval or Issue by Relevant Agency | The anticipated date the reviewing agency is expected to approve, issue, or otherwise complete the milestone, allowing the project to proceed. Enter the date in MM/DD/YYYY format.
Notes: | Use this column to provide additional information, such as identifying documents accompanying the upload (e.g., "SHPO concurrence letter dated 1/16/2026 attached"), explaining why a milestone is not applicable, or documenting issues, delays, or other information relevant to OBC's review.
Resources:
Link |  | Overview
NEPA for BEAD Frequently Asked Questions |  | Answers key environmental questions, including subgrantee and ESAPTT requirements
NTIA Permitting Resources |  | NTIA-provided resources and mapping tool that provides guidance on permits typically required for infrastructure deployment and related requirements of the BEAD program
USFWS IPaC Tool - Endangered Species Screening |  | Determines what impacts to sensitive natural resources are likely to occur from the project and provides suggestions for addressing them
FEMA Flood Map Service Center |  | Identifies floodplains
USFWS Wetlands Mapper |  | National Wetlands Inventory map that is used to screen for Clean Water Act/Section 404 triggers

## NEPA Milestone Schedule
New Jersey Broadband Equity Access and Deployment (BEAD) and Broadband Infrastructure Deployment Equity Program (NJIBDE).
As of date: July 1, 2026
CONFIDENTIAL: PROPRIETARY, PRELIMINARY, PRE-DECISIONAL, AND DELIBERATIVE ¦ DRAFT, NOT FOR DISTRIBUTION
DOCUMENT INTENDED TO PROVIDE INSIGHT BASED ON CURRENTLY AVAILABLE INFORMATION FOR CONSIDERATION AND NOT SPECIFIC ADVICE. INPUTS BASED ON DISCUSSIONS WITH OBC.
Tracking Element | Expected Date to Begin Process for Report / Consultation / Permit / Authorization | Expected Date to Complete and Submit Report to Reviewing Agency or Expected Date for Specified Event | Expected Date of Approval or Issue by Relevant Agency | Notes
1 NEPA Compliance Note: This row represents the overall timeline for tasks 1.a through 1.d. |  |  |  |  | <- rollup of 1.a-1.d
1.a Section 106 NHPA Compliance (as applicable) |  |  |  |  | <- rollup
1.a.1 Historic Resources Report and Survey
1.a.2 Archeological Background Study and Survey
1.a.3 Historic Commission (SHPO) Consultation
1.a.4 Tribal Consultation
1.b Clean Water Act Compliance Section (Water Resources) (as applicable for Section 401, 404 and/or 408) - add lines as needed |  |  |  |  | <- rollup
1.b.1 Wetland Delineation
1.b.2 Water Resources Report
1.b.3 Consultation with US Army Corp of Engineers
1.c Endangered Species Act Compliance (as applicable) |  |  |  |  | <- rollup
1.c.1 Conduct Species Analysis using the U.S. Fish & Wildlife Service (USFWS) iPaC tool
1.c.2 Habitat Assessment Report
1.c.3 Biological Assessment Report
1.c.4 Informal and/or Formal Coordination with USFWS
1.d. Other NEPA and Environmental Review (as applicable) - add lines as needed |  |  |  |  | <- rollup
1.d.1 Conduct [Analysis/Survey/Report] for [Agency]
1.d.2 Consultation with [Agency}
2. State and Local Environmental Compliance (as applicable) - add lines as needed |  |  |  |  | <- rollup
2.a.1. Conduct [Analysis/Survey/Report] for [Agency]
2.a.2 Consultation with [Agency}
3. Federal Agency Permits/Authorizations/Consents (as applicable) |  |  |  |  | <- rollup
Bureau of Land Management (BLM) ROW Authorization
Forest Service (FS) Special-use Permit
National Park Service (NPS) ROW Permit
U.S. Fish & Wildlife Service (USFWS) Special Uses Permit/ROW
Bureau of Indian Affairs (BIA) ROW Consent/Service Line Agreement
Bureau of Reclamation (BOR) ROW Authorization
Other Federal Permits/Authorizations/Consents, add lines and specify the permit and agency
Additional Notes
*Please also consult, NTIA Memo, "Authorization of NTIA Grant Recipients to Initiate Section 106 Consultation for NTIA Funded Projects" October 2025, https://broadbandusa.ntia.gov/sites/default/files/2025-10/NTIA_Section_106_NHPA_Grant_Recipient_Delegation_Notice.pdf and Related ACHP Program Comment Guidance, https://www.ntia.gov/blog/2024/expanding-internet-access-and-protecting-historic-properties
** Please also consult NTIA/USFWS Memo, "Authorization of NTIA Grant Recipients to Serve as N on-Federal Representatives for Section 7 Consultation," August 5, 2025 https://broadbandusa.ntia.gov/sites/default/files/2025-08/NTIA_FWS_Non-Federal_Designation_Memo_2025.pdf and related NTIA July 2025 Guidance, https://broadbandusa.ntia.gov/technical-assistance/Guide_to_Streamlined_ESA_Compliance_for_Broadband_Deployments