New Jersey Green Program of Study Year 5

- 15-BE39-G06

- NOTICE OF GRANT OPPORTUNITY

- Fiscal Year 2015

- David C. Hespe

- Acting Commissioner of Education

- Susan Martz

- Assistant Commissioner

Division of Student Services and Career Readiness

- Marie Barry

- Director

- Office of Career and Technical Education

Division of Student and Field Services

- JULY 2014

- Application Due Date:  August 21, 2014

- ORG/APU 5062-032

- NEW JERSEY DEPARTMENT OF EDUCATION

- P.O. Box 500

- Trenton, N.J.  08625-0500

- http://www.state.nj.us/education

STATE BOARD OF EDUCATION

ARCELIO APONTE ……….………………………………………	Middlesex

President

JOSEPH FISICARO………………………………………………….   Burlington

Vice President

MARK W. BIEDRON .........................................................................	Hunterdon

RONALD K. BUTCHER …………………………………………..	Gloucester

CLAIRE CHAMBERLAIN ………… ……………………………..	Somerset

JOSEPH FISICARO ………………………………………………..	Burlington

JACK FORNARO….………………………...…………………….	Warren

EDITHE FULTON ………………………………………………….	Ocean

ROBERT P. HANEY ………………………………………………	Monmouth

ERNEST P. LEPORE ……..………………………….…………….	Hudson

ANDREW J. MULVIHILL …………………………………………	Sussex

J. PETER SIMON ………………………………………………….	Morris

DOROTHY S. STRICKLAND …………………………….……….	Essex

Dave C. Hespe, Acting Commissioner

Secretary, State Board of Education

It is a policy of the New Jersey State Board of Education and the State Department of Education that no person, on the basis of race, color, creed, national origin, age, sex, handicap or marital status, shall be subjected to discrimination in employment or be excluded from or denied benefits of any activity, program or service for which the department has responsibility.  The department will comply with all state and federal laws and regulations concerning nondiscrimination.

- TABLE OF CONTENTS

When responding to this Notice of Grant Opportunity (NGO), applicants must also access the "Discretionary Grant Application (DGA)" for additional information governing the grant program.  See www.nj.gov/njded/grants/discretionary/apps/ or call the Application Control Center (ACC) at 609-633-6974.

- PAGE

- SECTION 1:		GRANT PROGRAM INFORMATION

- 1.1	Description of the Grant Program	1

- 1.2 	Eligibility to Apply	3

- 1.3 	Statutory/Regulatory Source and Funding	 3

- 1.4	Documentation of Federal Compliance	4

- 1.5 	Dissemination of This Notice	4

- 1.6 	Technical Assistance	4

- 1.7 	Application Submission	4

- 1.8 	Reporting Requirements	5

- 1.9 	Assessment of Statewide Program Results	7

- 1.10	Reimbursement Requests	8

- SECTION 2:		PROJECT GUIDELINES

  - Project Design Considerations	9

  - Project Requirements	13

  - Budget Design Requirements	13

  - Budget Requirements	14

- SECTION 3:		COMPLETING THE APPLICATION

- 3.1	General Instructions for Applying	16

- 3.2	Review of Continuation Applications	16				3.3	Application Component Checklist	16

- SECTION 1:  GRANT PROGRAM INFORMATION

  - DESCRIPTION OF THE GRANT PROGRAM

- The statewide goal of the New Jersey Green Program of Study Notice of Grant Opportunity (NJ Green POS) is to create model, green-focused four-year green programs of study in sustainable design, sustainable energy, and green construction that may be adopted by interested school districts and their postsecondary partners.  The Carl D. Perkins Career and Technical Education Act of 2006 (Perkins IV) calls for states to offer “career and technical programs of study,” which may be adopted by local educational agencies and postsecondary institutions, as an option to students (and their parents as appropriate) when planning for and completing future coursework.

- These programs, at a minimum, must:

- Incorporate and align secondary and postsecondary education elements;

- Include academic and CTE content in a coordinated, non-duplicative progression of courses;

- Offer the opportunity, where appropriate, for secondary students to acquire postsecondary credits; and

- Lead to an industry-recognized credential or certificate at the postsecondary level, or an associate or baccalaureate degree.

- By developing model green programs of study, the New Jersey Department of Education (NJDOE) has created a streamlined process for school districts and their postsecondary partners to obtain NJDOE program of study approvals in these high wage, high skill, and high demand green careers, enabling more school districts to offer high quality CTE programs with college credit options to their high school student.  The model green programs of study created through this grant program are currently available to any school district offering or interested in offering career and technical education programs in the design, energy, and/or construction fields.  Each of the three models includes curricula as follows:

- Sustainable Design Pathway:

| Year 1 | Year 2 | Year 3 | Year 4 |
| --- | --- | --- | --- |
| - Science and Sustainability - Green Careers Exploratory | - Introduction to Sustainable Design | - Sustainable Design 101 - Sustainable Design 102 | - Senior Internship & Mentoring - Sustainable Design 103 Sustainable Design 104 |

- Sustainable Energy Pathway:

| Year 1 | Year 2 | Year 3 | Year 4 |
| --- | --- | --- | --- |
| - Science and Sustainability - Green Careers Exploratory | - Intro to Energy for Sustainable Future | - Energy 101 - Energy 102 | - Energy 103 - Energy 104 - Sustainable Design |

- Green Construction Pathway:

| Year 1 | Year 2 | Year 3 | Year 4 |
| --- | --- | --- | --- |
| - Science and Sustainability - Green Careers Exploratory | - Building Science | - Green Construction Curriculum Modules to be integrated into trade-specific curriculum | - Green Construction Curriculum Modules to be integrated into trade-specific curriculum - Sustainable Design |

In Year 5, this continuation Notice of Grant Opportunity (NGO) will provide continuation funding to Essex County Vocational-Technical School District in order to accomplish the grant objectives listed in Section 2 of this NGO.  Grant objectives for Year 5 include providing support to the six pilot school districts to continue implementing model Green Programs of Study with their postsecondary partners, continue offering professional development to participating teachers, expanding the Green Program of Study to include new interested school districts and postsecondary partners, and transitioning the pilot program into the official New Jersey Green Program of Study.

One grant for a total $114,000 will be awarded for Year 5 of this grant program, which will commence on November 1, 2014, and conclude on October 31, 2015.  The final award for Year 5 is subject to the availability of State Vocational Education Aid funds.

1.1.1	 BACKGROUND

In June 2009, New Jersey was selected as one of five states to participate in a National Academy sponsored by the National Research Center for Career and Technical Education and the Office of Vocational and Adult Education at the US Department of Education.  This Academy was designed to support states’ efforts in developing “green-focused” career and technical education (CTE) programs of study in order to prepare secondary and postsecondary students for emerging green-focused careers.  Michael Pennella, then superintendent of Essex County Vocational-Technical School District, served as the leader of New Jersey’s team in the National Academy described above and is hosting the state green curriculum project in his district.

On July 1, 2009, the New Jersey Department of Education, Office of Career and Technical Education (OCTE), entered into a cooperative agreement with Essex County Vocational-Technical School District to develop the State’s first statewide green program of study.  Teams of teachers, college faculty and industry representatives were convened to initiate development of the curricula for the four-year programs of study in green-focused career areas. Through a subsequent multi-year targeted continuation NGO with Essex County Vocational-Technical School District, the four-year curricula have been developed for each of the three career areas.

On September 1, 2011, the OCTE awarded multi-year grants to six school districts for the purpose of piloting the green program of study curricula and develop NJ Green POS agreements with postsecondary partners in the three career areas.  The pilot school districts are implementing the grade 11 curricula during the 2013-2014 School Year, and will begin implementing the grade 12 curricula in the fall of the 2014-2015 School Year.  Work has begun on developing the program of study agreements with postsecondary partners.  Significant professional development and support was provided to the pilot school districts through this continuation NGO, including mentoring by sustainability experts in support of the curricula.

1.2 	ELIGIBILITY TO APPLY

This is a continuation NGO available only to Essex County Vocational-Technical School District, the recipient of original multi-year grant.

1.3	FEDERAL COMPLIANCE REQUIREMENTS (DUNS, SAM)

In accordance with the Federal Fiscal Accountability Transparency Act (FFATA), all grant recipients must have a valid Data Universal Numbering System (DUNS) number and must also be registered with the federal System for Award Management (SAM), the successor to the federal Central Contractor Registration (CCR) database.  DUNS numbers are issued by Dun and Bradstreet and are available for free to all entities required to register under FFATA.

•	To obtain a DUNS number, go to http://fedgov.dnb.com/webform/

•	To register with the SAM database, go to www.sam.gov

Applicants are required to submit their DUNS number and expiration date of their SAM registration as part of the EWEG application using the appropriate EWEG tab (contacts) and must certify that they will ensure that their registration will remain active for the entire grant period.

Applicants must also print the “Entity Overview” page from their www.sam.gov profile (which displays their DUNS number and street address with ZIP+4 code), and include this in their application..

No award will be made to an applicant not in compliance with FFATA.

1.4	STATUTORY/REGULATORY SOURCE AND FUNDING

The applicant’s project must be designed and implemented in conformance with all applicable State and Federal regulations. The New Jersey Green Program of Study is 100% percent funded from State Vocational Aid.  (ORG/APU 5062-032)

The final award is subject to the availability of State Vocational Aid funds. Total funds for the New Jersey Green Program of Study are $114,000.

The grantee is expected to complete the goal and objectives laid out in the approved grant application, complete implementation activities established in its grant agreement, and make satisfactory progress toward the completion of the approved action plan.  Failure to do so may result in the withdrawal by the NJDOE of the grantee’s eligibility for the continuation of grant funding.  The NJDOE will remove ineligible, inappropriate, or undocumented costs from funding consideration.

Final awards are subject to the availability of State Vocational Aid funds.

1.5	DISSEMINATION OF THIS NOTICE

The OCTE will make this notice available to the eligible applicant listed in Section 1.2, based upon the eligibility statement, and to the county superintendent of the county in which the eligible agency is located.

Additional copies of the NGO are also available on the NJDOE web site (http://www.nj.gov/njded/grants/discretionary/) or by contacting the OCTE at the New Jersey Department of Education, River View Executive Plaza, Building 100, Route 29, P.O. Box 500, Trenton, NJ  08625-0500; telephone (609) 633-0665; fax (609) 984-5347.

1.6	TECHNICAL ASSISTANCE

The OCTE will provide technical assistance on an as-needed basis, including EWEG.  Please contact Anne Freeman, Green Program of Study grant program officer, at 609-984-5906 or e-mail her at anne.freeman@doe.state.nj.us for additional information or to schedule technical assistance.

1.7 	APPLICATION SUBMISSION

The responsibility for a timely submission resides with the applicant. The Application Control Center (ACC) must receive an original and four (4) copies of the complete application NO LATER THAN 4:00 P.M. ON August 21, 2014.  Without exception, the ACC will not accept, and the Office of Grants Management cannot evaluate for funding consideration, an application received after this deadline. An applicant agency will lose the opportunity to be considered eligible for an award if the application is received after the due date.

The original and four (4) copies of the application must be mailed or delivered to:

## Application Control Center

New Jersey Department of Education

River View Executive Plaza, Building 100

P.O. Box 500

Trenton, NJ 08625-0500

The applicant is encouraged either to:

- hand deliver the application to the address above which is located next to Mercer County Waterfront Park on Route 29 in Trenton, between the hours of 8:30 a.m. and 4:00 p.m., Monday through Friday (excluding state holidays) and obtain a dated receipt; or

- send the application by Certified Mail, Return Receipt Requested; or

- arrange for delivery by an overnight delivery service to ensure timely delivery and receipt of the application.

Postmarks are not acceptable evidence of timely submission.  Receipt by the due date and time is required. Applicants are encouraged to obtain a receipt or to sign in upon delivery to verify DOE receipt. Complete applications are those that include all elements listed in Section 3.3, Application Component Checklist of this notice. Applications received by the due date and time will be screened to determine whether they are, in fact, eligible for evaluation. The Department of Education reserves the right to reject any application not in conformance with the requirements of this NGO. Applications submitted by fax cannot be accepted in any circumstances.

- 1.8	REPORTING REQUIREMENTS

Grant recipients are required to submit periodic project and fiscal progress reports. All reports will be submitted through the EWEG system. Reports for this program will be due as follows:

| Report | Reporting Period | Due Date |
| --- | --- | --- |
| Interim | 11/01/14 – 04/30/15 | 05/29/15 |
| Final | 11/01/14 – 10/31/15 | 11/30/15 |

1.8.1 	Interim Report: The Interim Report includes both program and fiscal reports.  The Interim Report will include the following:

a.	Interim Report Narrative. The grantee will submit an interim progress report narrative as follows:

- Progress made toward achieving the project outcomes, including successes as well as any barriers to success;

- If and why project activity timelines are moved;

- If and why budget items were not expended as anticipated;

- Documents and resources due; and

- Requests for technical assistance from the OCTE, if any.

b.	Interim Report Project Activity Plan. The grantee will submit the interim project activity plan as follows:

    - Triangles for completed activities will be filled in;

- Triangles for activities underway will be partially filled in;  and

- Triangles for activities for which the timeline has moved will be circled and redrawn in the new timeframe.

c.	Interim Fiscal Report: The grantee will submit an interim fiscal report as follows:

- Total expenditures to date by line item; and

- Summary of total expenditures to date.

1.8.2	Final Report:  The Final Report includes both program and fiscal reports.  The Final Report will include the following:

a. 	Final Report Narrative. The grantee will submit final progress report narrative as follows:

- Achievement of the project outcomes;

- If any project outcomes were not met, include an explanation of barriers to success;

- If any project activity timelines were not met, include an explanation of barriers to success;

- Hard-copy and electronic copies of all documents and resources to be created as part of the grant program, i.e. curriculum documents and resources;

- Copies of the program of study agreements established between pilot school districts and postsecondary partners;

- Lists of resources and support materials used to augment the curriculum, including contact information of resource providers, i.e. Green Education Foundation, industry credentials, etc;

- List and contact information for any non-pilot school districts participating in the Green POS;

- Possible strategies to continue to expand and refresh the NJ Green POS website and professional learning community dedicated social media tools;

- If budget items were not expended as anticipated, include an explanation of why;

- List of grant partners, consultants, and other contacts who have or can provide services and support to the NJ Green POS; and,

- A Strategic Action Plan to transition the NJ Green POS pilot program into the official New Jersey Green Program of Study Model.

b.	Final Report Project Activity Plan.  The grantee will submit the final project activity plan as follows:

- Triangles for completed activities will be filled in.

- Triangles for activities initiated but not completed will be partially filled in.

- Triangles for activities not initiated will be left blank.

c.	Final Report Budget Summary.  The grantee will submit the final Budget Summary as follows:

- Expenditures to date by line item; and

- Total expenditures to date.

1.8.3	Report Submission

All fiscal and program reports will be submitted through EWEG as part of the periodic expenditure report system (PERS).  All required supporting documentation such as curriculum documents and electronic documents will be submitted directly to the OCTE grant program officer in a format agreed on by the OCTE.

1.9	ASSESSMENT OF STATEWIDE PROGRAM RESULTS

The OCTE will periodically assess the grantee’s progress toward achieving the outcomes listed under Section 2.1: Project Design Considerations.  The primary tools for conducting these assessments are the Interim and Final Reports.  The OCTE will conduct the evaluation of the Interim and Final Reports by asking the following questions:

- Is the grantee making timely progress toward accomplishing the objectives and outcomes of this grant program as evidenced by the grantee meeting the approved activity timelines in the Project Activity Plan?

- Is progress being made between the pilot school districts and their postsecondary partners towards establishing the NJ Green Program of Study Articulation Agreements?

- Are interested non-pilot school districts being identified and supported?

- Is progress being made in developing a Strategic Action Plan to transition the pilot program to the official New Jersey Green Program of Study Model?

- Are curriculum documents and other resources being prepared for the transition?

- Is the grantee spending grant funds in support of the Project Activity Plan activities and timelines?

- Is there collaboration between the grantee, grant partners, and the OCTE in executing this grant program?

In addition, the OCTE may choose to conduct either or both of the following assessments:

- A survey of pilot districts, postsecondary partners, and/or industry partners during the grant year in order to assess their perception of the grant program activities and resources.

- A monitoring visit of the grantee to review the approved documentation identified in the Program Activity plan in order to demonstrate accomplishment of grant activities.

1.10 	REIMBURSEMENT REQUESTS

Payment of grant funds is made through a reimbursement system. Reimbursement requests for any grant funds the local project has expended are made through the Electronic Web-Enabled Grant (EWEG) system. Reimbursement requests may begin once the Grant Agreement has been fully executed and the award has been set up in the EWEG payment system. The Program Office will notify the grantee when the award has been established in EWEG.

Only one (1) request may be submitted per month. Grantees must submit their request no later than the 15th of the month. The requests may include funds that will be expended through the last calendar day of the month in which reimbursement is requested. If the grantees’ request is approved by the NJDOE program officer, the grantee should receive payment around the 8th-10th of the following month.

- Note: Payments cannot be processed until the award is set up in EWEG.

SECTION 2:  PROJECT GUIDELINES

- The intent of this section is to provide the applicant with the framework within which it will plan, design, and develop its proposed project to meet the purpose of this grant program. Before preparing an application, the potential applicant is advised to review Section 1.1, Description of the Grant Program, of this NGO to ensure a full understanding of the state’s vision and purpose for offering the program. Additionally, the information contained in Section 2 will complete the applicant’s understanding of the specific considerations and requirements that are to be considered and/or addressed in their project.

- Please note that the passage of the School District Accountability Act (A5 or Chapter Law 53) places additional administrative requirements on the travel of school district personnel.  The applicant is urged to be mindful of these requirements as they may impact the ability of school district personnel to participate in activities sponsored by the grant program.

## 2.1	PROJECT DESIGN CONSIDERATIONS

## The New Jersey Green Program of Study Pilot Program (pilot program) will encompass all of the tasks associated in support of the Statewide Goal of this grant program, which is to establish the model four-year green program of study described in this NGO and provide support to school districts implementing the model four-year programs of study.  This grant will provide support to six pilot school districts implementing the model program of study in the form of curricula and curriculum resources, model articulation agreements, professional development, technical assistance, industry credentials, electronic support, and other resources. It will also support interested school district in implementing the Year 1 curriculum.

## In Year 5, the applicant will address the following required grant objectives and indicators in support of the Statewide Goal as articulated in the applicant’s project narrative, project activity plan, and project budget, which are as follows:

STATEWIDE GOAL: To collaborate with the New Jersey Department of Education, Office of Career and Technical Education, to establish model four-year statewide green programs of study in “green-focused” career and technical education (CTE) programs for sustainable design, sustainable energy, and green construction (building science) in order to prepare secondary and postsecondary students for emerging green-focused careers.

Required Objectives and Indicators are established through this NGO to support the Statewide Goal.  Each objective is accompanied by an indicator of successful completion, as follows:

OBJECTIVE 1: Support implementation of the Model Green Curricula.

Coordinate implementation of the model Green Program of Study curricula for sustainable design, sustainable energy, and green construction with the pilot school districts, as follows:

1.A:	Commencing in the second quarter (, convening pilot school district teachers and curriculum consultants to update grade 11 curricula based upon pilot school experience implementing the curricula during the 2013-2014 school year.

Indicator 1.A: By the conclusion of the grant program, the grade 11 curriculum in each of the three career areas was updated as needed.

1.B: 	Commencing in February 2015, facilitating technical assistance, as requested, to pilot school districts implementing the grade 12 curricula during the 2014-2015 school year;

Indicator 1.B: Technical assistance was provided to the pilot school districts implementing the grade 12 curriculum as needed and requested.

OBJECTIVE 2:  Support the establishment of the Model Green Programs of Study.

Commencing in November 2014, provide support as needed to the pilot school districts and their postsecondary partners to ensure that each pilot school district establishes an articulation agreement using the NJ Green Program of Study Model in at least one of the three career areas prior to the end of the grant period.

Indicator 2:  By the end of the grant period, an articulation agreement in at least one of the three career areas using the New Jersey Green Program of Study Model was established by each of the pilot schools and their postsecondary partners.

OBJECTIVE 3:  Support the Electronic Green Professional Learning Community.

3.A:	Commencing in November 2014, provide support and leadership to the NJ Green POS electronic professional learning community (PLC), which operates on a dedicated social media platform.

Indicator 3.A: Commencing with the November 2014, support and leadership were provided to the NJ Green POS PLC electronic PLC.

3.B:	Commencing in November 2014, encourage non-pilot school district teachers to participate in the PLC.

Indicator 3.B: Non-pilot school district teachers joined and participated in the PLC.

OBJECTIVE 4: Expand the NJ Green POS to interested school districts.

Encourage non-pilot school districts to adopt the NJ Green POS and provide support to those schools implementing the program.

4.A:	Commencing in the November 2014, plan and implement technical assistance, professional development, and resources for non-pilot school districts.

Indicator 4.A: Technical assistance, professional development and resources were planned and implemented prior to the end of the grant period.

4.B:	Commencing in the November 2014, identify, develop and post resources on the NJ Green Program of Study website.

Indicator 4.B: Web-based resources were identified, developed, and posted on the NJ Green Program of Study website on a regular basis.

4.C:	Commencing in January 2015, plan a summer institute for interested school districts and implement the institute during June or July 2015.

Indicator 4.C: A summer institute targeting non-pilot school districts was implemented in the third quarter.

OBJECTIVE 5: 	Research industry credentials and deliver training to teachers and/or students.

5.A:	Commencing in January 2015, conduct research to identify relevant industry credentials pertaining to sustainable design, sustainable energy, and green construction appropriate for teachers and/or students.

Indicator 5.A: Research on industry credentials was conducted, relevant credentials were identified.

5.B:	Commencing no later than July 2015, deliver credential training to pilot and non-pilot school district teachers as appropriate and practical.

Indicator 5.B: Credential training was delivered as appropriate and practical to pilot and non-pilot teachers.

OBJECTIVE 6: Develop and implement a strategic action plan to transition the pilot program to the official NJ Green Program of Study Model.

Support the continuance of the NJ Green Program of Study Pilot Program for sustainable design, sustainable energy, and green construction, as follows:

6.A:	Submit a draft Strategic Action Plan to the OCTE by the end of the first quarter that to transition the pilot program to the official NJ Green Program of Study Model and revise plan as requested.

Indicator 6A: A draft Strategic Action Plan was submitted to the OCTE by the end of the first quarter and the plan was revised as requested.

6.B: Commencing in the second quarter, implement the Strategic Action Plan.

Indicator 6.B: The Strategic Action Plan was implemented as approved by the OCTE.

OBJECTIVE 7: Provide grant support to ensure the goal and objectives of the grant program are being met as planned.

Provide information, recommendations, and reports to the OCTE on a timely basis to ensure effective implementation of the State Goal and Objectives, and hire an external evaluator to assess achievement of grant outcomes.

7.A:	Commencing in the first quarter, participating in monthly online meetings with the OCTE to review grant progress and other meetings as requested.

Indicator 7.A: The grantee participated in monthly meetings called by the OCTE and other meetings as requested by the OCTE.

7.B:	Participate in the annual CTE Institute and other events as approved by the OCTE.

Indicator 7.B:  The grantee participated in the annual CTE Institute and other events as approved by the OCTE.

7.C:	Commencing in the first quarter, hire an external evaluator to evaluate the grant program to determine if the grant outcomes have been met and to make recommendations to the OCTE to improve performance of the NJ Green POS.  The external evaluator will have expertise in CTE programs and programs of study and grant evaluations.

Indicator 7.C:  An outside evaluator was hired and conducted the evaluation, with results and recommendations submitted to the OCTE no later than the third quarter.

- 2.2	PROJECT REQUIREMENTS

- In preparing a response to this NGO, the applicant is responsible for reviewing and complying with all grant program requirements set forth in this NGO. Below is a list of project requirements to be included in the applicant’s program design:

2.2.1	Project Description:

The Project Narrative will describe the applicant’s vision for implementing each of the Year 5 NGO objectives and indicators within the timelines established in this NGO.  Provide assurance that the strategies or activities are of sufficient quality and scope to ensure equitable access and participation among all eligible program participants.

- Include specific examples of systems, curriculum or design approaches that will be incorporated.

- Include justification for identifying this as an area to improve and the plan to make this transition.

- Include benchmarks for the early, middle and final stages of the process and how progress will be measured towards these benchmarks.

- Identify who will be responsible for what stages and what level of support they will be given.

- Write clearly and succinctly, focusing on quality and not quantity.

- Ensure that the steps of the Project Activity Plan are well-articulated and logically sequenced in the narrative.

- Include a staffing plan for the grant program, including consultants and vendors needed to accomplish NGO objectives.

2.2.2	Goals, Objectives and Indicators

The State Goal and Objectives are provided in this NGO.  The application must include a plan (develop indicators) to evaluate the project’s success in achieving its goal and objectives.

2.2.3	Project Activity Plan

The Project Activity Plan follows the goal(s) and objectives that were listed in the previous section. The Activity Plan is for the current grant period.  Activities represent the steps that it will take to achieve each identified objective.  Also, the activities that are identified in this section serve as the basis for the individual expenditures that are being proposed in the budget.  Review the Goal(s) and the Objectives when constructing the Project Activity Plan to ensure that appropriate links have been established between the goal(s) and objectives and the activities.

- State the relevant objective in full in the space provided.  Number the Goal 1 and each objective 1.1, 1.2, 1.3, etc.

- Describe all of the tasks and activities planned for the accomplishment of each goal and objective.

- List all the activities in chronological order.

- Space the activities appropriately across all report periods of the grant project.

- Identify the staff directly responsible for the implementation of the activity.  If the individual conducting the activity is not referenced appropriately on the Project Activity Plan, it may not be possible to determine an allocation of the requested cost, and costs may be disallowed.

- List the documentation that tracks the progress and confirms the completion of each activity, such as agenda, minutes, curriculum, etc.

- In the Report Period Column on the Project Activity Form, indicate with a checkmark the period in which the activity will be implemented.  If the activity is ongoing or recurring, place a checkmark in the boxes under each period in which the activity will talk place.

- Do not list the project director or other person with general oversight authority for the project as the “person responsible” for carrying out all activities.

2.3	BUDGET DESIGN CONSIDERATIONS

- Once the objectives that will guide the work in the implementation phase of the grant have been prioritized, begin to develop the details of the budget that will be necessary to carry out each activity.

- The applicant’s budget must be well-considered, necessary for the implementation of the project, remain within the funding parameters contained in this handout, and demonstrate prudent use of resources.  The budget will be reviewed to ensure that costs are customary and reasonable for implementation of each project activity.

- The applicant must provide a direct link for each cost to the goal, objectives and activities in the Project Activity Plan that provides programmatic support for the proposed cost.  In addition, the applicant must provide documentation and details sufficient to support each proposed cost.

- Guidance on constructing a grant budget may be found in the Discretionary Grant Application (DGA) document, which can be accessed at www.state.nj.us/education/grants/discretionary .

- The budget submitted as part of the application is for the current grant period only.

- The Department of Education will remove from consideration all ineligible costs, as well as costs not supported by the Project Activity Plan.  The actual amount awarded will be contingent upon the applicant’s ability to provide support for its proposed budget upon application and ultimately will be determined by the Department of Education through the pre-award revision process.  The applicant’s opportunity to make pre-award revisions will be limited by the Department of Education which is not responsible either to provide repeated opportunities for revisions or to permit reallocation of the funds previously requested for costs that have not been approved or have been disallowed.

- 2.4	BUDGET REQUIREMENTS

- Budget requests should be linked to specific project activities and objectives of the NJ Green POS.

- The provisions of A-5/Chapter Law 53 contain additional requirements concerning prior approvals, as well as expenditures related to travel.  It is strongly recommended that the applicant work with their business administrator when constructing the budget. The NJDOE applies the A-5 restrictions uniformly to all funded agencies. Unless otherwise specified, the following restrictions apply to all grant programs:

- No reimbursement for in-state overnight travel (meals and/or lodging)

- No reimbursement for meals on in-state travel

- Mileage reimbursement is capped at $.31/mile

#### 2.4.1	Mandatory Costs: The following costs must be included in the applicant’s proposed budget:

2.4.1.1	Salary, Fringe Benefits, and grant-related in-state travel of Project Director:  The funded agency must assign an employee or consultant of the funded agency to serve as a project coordinator to coordinate all aspects of implementing the grant program.  The percentage of time spent coordinating grant activities is to be established by the applicant. These costs will be considered either administrative or programmatic, depending upon the nature of the activity being carried out.

2.4.1.2	Salary, Fringe Benefits, and grant-related in-state travel of Project Coordinator:  The funded agency must hire a project coordinator to coordinate all aspects of implementing the grant program. These costs will be considered programmatic.

#### 2.4.1.3	External Evaluator: An external evaluator must be hired by the funded agency to conduct the evaluations and develop reports as per Objective 7.C.  This cost will be considered programmatic.

#### 2.4.1.4 	Eligible Costs: The following programmatic costs, unless otherwise indicated, may be included in the applicant’s proposed budget:

#### Administrative Costs: A maximum of 10% of the total grant award may be used for administrative costs to support the grant program, including the project director and support staff and the funded agency’s fiscal support of operating the grant program.

- Related Textbooks and Classroom Materials: Review copies of the required textbooks and classroom materials may be purchased.

- Consultant Costs: Consultants may be hired to support aspects of the Project Activity Plan. Consult the Discretionary Grant Application (DGA) document for cost limitations.

- Supplies: Supplies may be purchased to support the ongoing implementation of the grant program.

- Professional Development:  Includes costs associated with professional development for both the pilot and non-pilot school districts.

- Vendors: Costs associated with planning and implementing grant-related meetings, workshops and summer institutes.

- Stipends: Stipends for teachers, faculty and industry professionals engaged in curriculum writing and other grant-related activities.

- Substitute Teachers: Substitute teacher costs for pilot school districts when participating teachers attend curriculum writing meetings and other grant-related activities as approved by the OCTE.

- Website: Website host registration fees to maintain the NJ Green Program of Study website.

- Other: Any costs not identified above must be supported by the goals and objectives of this NGO and approved by the OCTE.

#### 2.4.1.8  	Ineligible Costs

- Ineligible costs include, but are not limited to:

- In-state meals and overnight lodging.

- Out-of-state travel and conferences unless approved by the OCTE.

- Indirect Costs

- Entertainment

- In reviewing this grant program application, the NJDOE may determine that certain proposed costs, though not specifically identified as ineligible, are not reasonable or appropriate under this grant program and, therefore, are not allowable.  In such a case, applicants may be requested to transfer grant funds between and among existing line items during the pre-contract revision process.

- SECTION 3:  COMPLETING THE APPLICATION

3.1	GENERAL INSTRUCTIONS FOR APPLYING

To apply for a grant under this NGO, applicants must prepare and submit a complete application. The application must be a response to the State’s vision as articulated in Section 1: Grant Program Information of this NGO. It must be planned, designed and developed in accordance with the program framework articulated in Section 2: Project Guidelines of this NGO. The applicant may wish to consult additional guidance found in the Discretionary Grant Application (DGA) document, found at www.state.nj.us/education/grants/discretionary.

3.2	REVIEW OF CONTINUATION APPLICATIONS

Department staff will review the application for completeness, accuracy, and how well the content addresses Sections 1 and 2 in this NGO.

Please be advised that in accordance with the Open Public Records Act P.L. 2001, c. 404, all applications for discretionary grant funds received September 1, 2003 or later, as well as the evaluation results associated with these applications, and other information regarding the competitive grants process, will become matters of public record upon the completion of the evaluation process, and will be available to members of the public upon request.

3.3	APPLICATION COMPONENT CHECKLIST

The following forms are required (see Required Column) to be included as part of the district’s application. Failure to include a required form may result in the application being removed from consideration for funding. Use the checklist (see Included Column) to ensure that all required forms are included in the district’s application.  Use the forms found in the DISCRETIONARY GRANT APPLICATION (DGA).  Electronic versions of the forms may be downloaded from the Department’s website at:  http://www.nj.gov/njded/grants/discretionary/apps/.

| Required  | Location | Form | Included  |
| --- | --- | --- | --- |
|  | NGO | Application Title Page |  |
|  | DGA | Board Resolution to Apply |  |
|  | DGA | Statement of Assurances |  |
|  | DGA | Documentation of Federal Compliance (DUNS/CCR) |  |
|  |  | Printout of “Entity Overview” page from www.sam.gov |  |
|  | DGA | Project Update |  |
|  | DGA | Project Description |  |
|  | DGA | Goals, Objectives, and Indicators |  |
|  | DGA | Project Activity Plan |  |
| * | DGA | Budget Form A: Full-Time and Part-Time Salaries |  |
| * | DGA | Budget Form B: Personal Services – Employee Benefits |  |
| * | DGA | Budget Form C: Purchased Professional and Technical Services |  |
| * | DGA | Budget Form D: Supplies and Materials |  |
|  | DGA | Budget Form F: Other Costs |  |
|  | DGA | Application for Funds – Budget Summary |  |

* Budget forms are required when applicable costs are requested.

NEW JERSEY DEPARTMENT OF EDUCATION

NOTICE OF GRANT OPPORTUNITY - TITLE PAGE

SECTION I:											15     BE39      G06

FY    NGO#     WKL

TITLE OF NGO:		New Jersey Green Program of Study Year 5

DIVISION:	     	Student and Career Readiness

OFFICE:		Career and Technical Education

SECTION II:										COUNTY:

LEA/OTHER:

SCHOOL:

COUNTY NAME:_____________________________

APPLICANT AGENCY

AGENCY ADDRESS

CITY							STATE						ZIP

(       )                                                                                                       (        )

AGENCY TELEPHONE NUMBER				AGENCY FAX #

SCHOOL NAME

PREVIOUS FUNDING:  Agency received funding from the NJ Department of Education within the last two years of submission of this application.

YES       NO

PROJECT DIRECTOR (Please print or type name):  _________________________________________________________________

TELEPHONE NUMBER:  (____)____________________  FAX#: (____)__________________  E-MAIL_______________________________

BUSINESS MANAGER:  ________________________________  PHONE#: (____)___________  E-MAIL_____________________________

DURATION OF PROJECT:	FROM: 	                   11/1/14        TO:     10/31/15

TOTAL AMOUNT OF FUNDS REQUESTED: $__________________________________________

APPLICATION CERTIFICATION:	To the best of my knowledge and belief, the information contained in the application is true and correct.  The document has been duly authorized by the governing body of this agency and we will comply with the attached assurances if funding is awarded.  I further certify the following is enclosed:

AGENCY TITLE PAGE

SIGNED STATEMENT OF ASSURANCES

BOARD RESOLUTION TO APPLY

APPLICATION NARRATIVE*

BUDGET SUMMARY AND BUDGET DETAIL FORMS*

ORIGINAL AND FOUR COPIES OF THE COMPLETE APPLICATION PACKAGE

___________________________________________________         _________________________________________	  ________________

SIGNATURE OF CHIEF SCHOOL ADMINISTRATOR                     TITLE					   DATE

OR EQUIVALENT OFFICER

___________________________________________________

(Please print or type name)

*FAILURE TO INCLUDE A REQUIRED APPLICATION COMPONENT CONSTITUTES A VIOLATION OF THE NGO AND WILL RESULT IN THE APPLICATION  BEING ELIMINATED FROM CONSIDERATION (See NGO  Section 3.3 for  itemized list).

SECTION III:

SEND OR DELIVER APPLICATIONS TO:					APPLICATIONS MUST BE RECEIVED BY:

NEW JERSEY DEPARTMENT OF EDUCATION

APPLICATION CONTROL CENTER				4:00 P.M., ON        08/21/14

RIVER VIEW EXECUTIVE PLAZA

BLDG. 100, ROUTE 29 – PO Box 500

TRENTON, NJ 08625-0500

NO FACSIMILE SUBMISSION WILL BE ACCEPTED.

NO LATE APPLICATIONS WILL BE ACCEPTED REGARDLESS OF THE DATE POSTMARKED.

NO ADDITIONAL MATERIALS CAN BE SUBMITTED AFTER RECEIPT OF THIS APPLICATION.