## project
Career Pathways Planner
[7 empty] | Period Highlight: |  |  |  |  | 1
|  | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT |  | Actual (beyond plan) |  |  | % Complete (beyond plan)
| ACTIVITY | START | DURATION | START | DURATION | COMPLETE | Year 1, Interim 1 | Year 1, Final | Year 2 | Year 3 | Year 4 | Year 5 | Beyond Grant
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
High Quality Partnerships
| Talent Network is involved with planning | 1 | 6 | 0 | 0 | 0%
| Advisory Board is established and requried members retained | 1 | 6 | 0 | 0 | 0%
| Signed Partnership Agreements | 1 | 6 | 0 | 0 | 0%
| Partnerships for each CTE Program are established and maintained | 1 | 6 | 0 | 0 | 0%
| High Quality Partnership Rubric | 2 | 5 | 0 | 0 | 0%
| Career pathway instructional supports are provided by partners | 1 | 6 | 0 | 0 | 0%
| Career pathway student supports are provided by partners | 2 | 5 | 0 | 0 | 0%
District Vision and Commitments
| Career Pathway Framework Self-Evaluation Rubric | 1 | 6 | 0 | 0 | 0%
| NJDOE PD is attended as required | 1 | 6 | 0 | 0 | 0%
| District/Advisory Board sponsored PD is provided | 1 | 6 | 0 | 0 | 0%
Career Pathway Vision Statement and Action Plan
| Plan and submit | 1 | 2 | 0 | 0 | 0%
| Implement and evaluate | 3 | 5 | 0 | 0 | 0%
Building level procedures and scheduling practices to support career pathways
| Recruitment plan for diversity of students (Plan, Implement, Evaluate) | 1 | 6 | 0 | 0 | 0%
| Support for interdisciplinary instruction (Plan, Implment, Evaluate) | 1 | 6 | 0 | 0 | 0%
| NJDOE virtual community participation | 1 | 6 | 0 | 0 | 0%
| Web-ready curriclum documents and resources | 3 | 4 | 0 | 0 | 0%
| Advisory Board/instructional staff present at DOE sponsored events | 4 | 3 | 0 | 0 | 0%
| Strategies for sustainability | 6 | 1 | 0 | 0 | 0%
| Materials to DOE to support career pathways | 6 | 1 | 0 | 0 | 0%
High-Quality CTE Programs of Study
| First career pathway identified | 1 | 1 | 0 | 0 | 0%
| First career pathway included in scheduling materials | 1 | 2 | 0 | 0 | 0%
| First CTE Program application submitted | 2 | 1 | 0 | 0 | 0%
| First career pathway curriculum developed/adopted | 1 | 3 | 0 | 0 | 0%
| First career pathway-Course 1 implemented with students enrolled | 3 | 4 | 0 | 0 | 0%
| Dual Enrollment/Articulation Agreement initiated for first CTE program | 2 | 2 | 0 | 0 | 0%
| Dual Enrollment/Articulation Agreement implemented for CTE program | 4 | 3 | 0 | 0 | 0%
| Second career pathway identified | 4 | 1 | 0 | 0 | 0%
| Second career pathway included in scheduling materials | 5 | 1 | 0 | 0 | 0%
| Second CTE Program Application submitted | 4 | 1 | 0 | 0 | 0%
| Second career pathway curriculum developed/adopted | 4 | 2 | 0 | 0 | 0%
| Second career pathway-Course 1 implemented with students enrolled | 5 | 1 | 0 | 0 | 0%
| Dual Enrollment/Articulation Agreement initiated for second career pathway | 4 | 1 | 0 | 0 | 0%
| Dual Enrollment/Articulation Agreement Implemented for second career pathway | 6 | 1 | 0 | 0 | 0%
Pedagogical Approach and Interdisciplinary Instruction
Structured Learning Experiences
| Planning/training | 1 | 2 | 0 | 0 | 0%
| Implement and evaluate | 3 | 4 | 0 | 0 | 0%
Interdisciplinary instruction/co-curricular project-based learning
| Planning/training | 1 | 2 | 0 | 0 | 0%
| Implement and evaluate | 3 | 4
Individualized Planning and Supportvie Services for Learners
Individulized student supportive services
| Planning/training | 1 | 2 | 0 | 0 | 0%
| Implement and evaluate | 3 | 4 | 0 | 0 | 0%
Indivdual career exploration and planning
| Planning/training | 1 | 2 | 0 | 0 | 0%
| Implement and evaluate | 3 | 4 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
Data Informed Improvement Cycle
| Advisory Board uses data to evaluate career pathway program | 3 | 4 | 0 | 0 | 0%
| Instructional staff uses data to evaluate student acheviement | 4 | 3 | 0 | 0 | 0%
| Decision-making process and analysis is formalized | 6 | 1 | 0 | 0 | 0%