## Slide 1: State Plan Update
Implementation Plan

## Slide 2: Process Overview
Four concurrent paths/end products
  Plan Document
  Infrastructure Needs Assessment
  Impact Assessment
  State Plan Policy Map and Mapping Protocol
Constant feedback loops among all four paths as each path further inform the development of the others.
Nevertheless, all four paths can be completed concurrently
Stakeholder engagement is critical
  An early Stakeholder outreach plan
  Required 27 public hearings, per Rules,

## Slide 3: Plan Document
Preliminary Plan – Per NJSA 52:18A-199(a), the Commission “…shall provide a coordinated integrated and comprehensive plan for growth, development, renewal, and conservation of the State and its regions and which shall identify areas for growth, agriculture, open space conservation, and other appropriate designations”.
  The basis for Cross Acceptance
  Early Stakeholder Process
    Not required in the Rules, but critical
Cross Acceptance
  a negotiating process, designed to encourage consistency between municipal, county, regional, and state plans to create a meaningful, up-to-date, and viable State Plan and State Plan Policy Map that is representative of their input and that of the public.
Draft Final Plan
  incorporates the negotiated agreements from the cross-acceptance process. Once the State Planning Commission approves the Draft Final Plan, that document, together with the State Plan Policy Map, becomes the new State Development and Redevelopment Plan

## Slide 4: Infrastructure Needs Assessment
Per NJSA 52:18A-199(b), the Commission “shall prepare and adopt as part of the Plan a long-term infrastructure Needs Assessment, which shall provide information on present and prospective conditions, needs and costs with regard to State, county and municipal capital facilities, including water, sewerage, transportation, solid waste, drainage, flood protection, shore protection, and related capital facilities”.
Broken into two phases
  Phase I – Environment, Energy, and Transportation
  Phase II – Affordable Housing, Farmland retention, public recreation, open space land, public recreation facilities, public education, higher education, public libraries, arts, corrections, and human services.
MOU with Rutgers for Phase I; beginning to discuss Phase II
The two phases will be consolidated into one report
Must be completed for the Final Draft Plan

## Slide 5: Impact Assessment
Per NJAC 5:85-4.7, “…the Commission shall have prepared an assessment of the impacts of the draft Final State Development and Redevelopment Plan relative to the impacts that would likely occur without that draft Final State Development and Redevelopment Plan. The results of the assessment shall identify desirable changes to be incorporated into the Final State Development and Redevelopment Plan.”

## Slide 6: State Plan Policy Map
While the State Planning Act does not address the State Plan Policy Map (SPPM or the Map), the rules do. A valuable part of the State Plan, the Map is a geographic application of the goals, strategies, and policies of the Plan and is important in interpreting smart growth areas and areas that need protection. However, the implementation and development of the Map have historically had challenges. With input from a diverse set of stakeholders, recommendations on how best to utilize and implement the Official Map of the State Plan must be developed. Among the questions that will be answered include:
  Should definitions of planning areas, centers, cores, and nodes be changed?
  How should differences among different areas of the State be incorporated into these definitions?
  Should counties play an expanded role in determining the mapping boundaries?
  How do we reconcile the difference between conceptual ideology and the need to create boundaries as part of mapping protocols (where do you “draw the line”?)?
  How do you avoid “mapping by permits” if regulating agencies that utilize the State Plan to determine where to permit (for example, CAFRA)?
Invariably, there will be other questions that develop and the above questions will lead to how the Map is developed and utilized going forward in the new Plan. These discussions will run concurrently with the Preliminary Plan development.

## Slide 7: State Planning Commission
Restart the Plan Development Committee
  Made up of some or all of the public and county/municipal members
    The time commitment for those members will include approximately one meeting a month, attendance at some public hearings, and review and input of the drafts of the plan and mapping proposals
Ex-Officio members to provide input through the interagency workgroup and departmental-specific meetings
Many Commission presentations throughout the process on topic details!

## Slide 8: Process Improvements
Rule Changes in process
  Allows for some virtual meetings
  Municipal and County submissions can be received electronically
  Distribution of the Preliminary Plan can be sent electronically
  Municipal master plans and other documentation are no longer required
  Provision of an electronic format for written comments
Procurement of software for recording, tracking, and consolidating public comment

## Slide 9: Outreach Plan
Required by the Rules:
  21 public hearings after the Preliminary Plan is published
  6 public hearings after the Final Plan is published
But, that’s not enough and it’s too late in the process, so….
  This process began with the listening session provided to us by the NJ Planning and Redevelopment Forum where invited stakeholders provided input into the Plan structure and several Commissioners were able to listen and respond. Audience members were also able to listen and/or provide written comments.
  Additional conference sessions and stakeholder engagement opportunities will be pursued in the coming months.
    By topic
    By interested party group

## Slide 10: Outreach Plan, Continued
Dedicated email address for public comments:
  stateplan.comments@sos.nj.gov
Interagency Workgroup to facilitate State agency comments
County Planners early involvement
  State Planning Subcommittee
  Early discussions on concerns and issues
  Facilitating early informational meetings with counties that request one

## Slide 11: Timeline
So many moving parts, and so little time!
  The target completion date is December 2024
    The proposed timeline is an aggressive one, but it is doable.
    There are numerous requirements for public notice that vary regarding the notice timeframes, based on scheduled public meetings. For that reason, some later dates are not specific but are estimated by month or quarter.
    As the process moves along, more specificity will be provided when public hearings are scheduled and other variables become more definitive
  The four paths will occur concurrently with constant feedback loops where information, public input, and analyses need to inform other paths.
    In short, coordination and communication are critical.

## Slide 12: Timeline, Continued
  Through the end of 2023
    Stakeholder sessions will be scheduled, advertised, and convened
    Interagency workgroup meetings will be scheduled
    County informational meetings held
    Continued conversations with county planners
    Research on population trends
    Complete Preliminary Plan
    Infrastructure Needs Assessment
      Phase I: Develop methodology, State agency and other outreach and initial meetings, literature review, growth scenario assumptions, preliminary assessments sent to State agencies, and receive comments
      Phase II: Execute MOU, kickoff project, begin background research and scoping outreach
    Determine mapping protocols
    Procurement of public comment software

## Slide 13: Timeline, Continued
  First half, 2024
    Publish Preliminary Plan and preliminary mapping
    Cross Acceptance
      21 Public Hearings
      Cross Acceptance Reports/Statements of Agreements and Disagreements
      Negotiations
      State Agency Reports and responses
    Complete INA, Phase I
    Begin, INA, Phase II
    Begin Impact Assessment activities
  Second half, 2024
    Complete INA, Phase II; consolidate into one report
    Incorporate results of Cross Acceptance into the Final Draft
    6 more public hearings
    Produce the Final Draft
    ADOPT!

## Slide 14: Implementation
A Plan is only as good as its implementation. Critical to the success of the Plan is working with our State agency partners. The Statute envisions that individual departmental plans be aligned with the State Plan so that a “whole of government” approach is taken.
Further discussion around incentives should be included in our update of the State Plan in recognition that good land use planning has many factors, and the State Plan can be a valuable tool in driving by informing programs and incentives.
There are many opportunities to modernize New Jersey’s land use discussion to ensure that New Jersey remains a great place to live, work, and play. This update gives elected officials at all levels of government the ability to do that.