## Sheet1
SAMPLE ACTION PLAN
Italics = DEP CAFRA Requirements
Item No. | Subject | Action Item | Deliverable | Timetable (Days) | Deadline*
A1 | State Plan Policy Map | The Township shall work with state agencies to revise boundaries for the Centers to be consistent with the State Plan goals, policies, and delineation criteria. The Township will need to clarify what types of development is proposed for these centers. | Center boundaries
A2 | State Plan Policy Map | The Township shall work with state agencies to revise boundaries for Planning Areas to account for existing environmental resources. | Planning area and CES boundaries
A3 | State Plan Policy Map | The Township shall work with state agencies to revise boundaries for Planning Areas based on discussion of Cross-acceptance proposed changes. | Planning area and CES boundaries
B1 | Master Plan | The Township shall update its Master Plan as necessary based on the discussion of other action items in this table, as well as any information available on water supply and allocation prior to the preparation of the final plan. | Master plan update adopted.
C1 | Open Space & Recreation | The Township shall prepare a statement discussing open space and recreation issues as outlined in the review letter. | Narrative statement.
C2 | Center Concepts | The Township shall prepare concepts, both in text and graphics if possible, to provide detail about the future development/redevelopment of the proposed Centers, including considerations for TOD cores. | Narrative statement (and graphics if feasible).
C3 | Road Network | The Township shall work with NJDOT in the Route 9 corridor study to identify and conceptually plan for a network of roadways. | Narrative statement and map(s).
D1 | Affordable Housing | The Township shall work with COAH to determine the status of its prior round and growth share obligations, with particular regard to LIHTC. | Revision to COAH plan calculations as necessary.
D2 | Affordable Housing | The Township shall work with DEP to ensure that all sites identified for affordable housing will be workable in relation to environmental constraints. | Narrative statement and map of affordable housing sites and environmental resources.
D3 | Affordable Housing | The Township shall ensure that its Plan Endorsement petition and COAH petition are generally consistent with each other in terms of where development will be focused and how much growth will be accomodated. The COAH petition will incorporate relevant agreements and information arising from Plan Endorsement negotiations taking place through this Action Plan. | Revised housing element
E1 | Emergency Planning | The Township shall provide evidence that it has an Emergency Operating Plan approved by the NJ State Police. | Copy of approval from NJ State Police.
F1 | Threatened & Endangered Species Habitat | The Township shall work with DEP on protecting habitat of threatened and endangered species. This information will be part of discussion in making any adjustments to center boundaries and planning areas. | Proposed habitat protection strategy and draft ordinance.
G1 | Petition Report Update | Elements of the petition report will be accurately updated based on the fulfillment of this action plan. These elements may include but are not limited to: consistency with State Plan goals and policies, PIA, population projections, center delineation criteria, references to new documents. | Petition report.
G2 | Petition Report Update | Due to the extent of change involved to make the petition consistent with the State Plan, the Township shall provide detail of public participation for the various action items, and in the end pass a resolution supporting the revised petition. | Petition report.
G3 | Petition Report Update | The Township shall improve the Statement of Planning Coordination section to discuss how future center-based development, infrastructure & capacity, and environmental protection will be coordinated with adjacent municipalities. This section shall also address cross-border issues such as development impacts and potential for shared services. | Petition report.
H1 | Coastal Consistency Statement | The Township shall prepare a statement that addresses natural resource protection and coastal management demonstrating consistency of local plans and ordinances with the goals of the Coastal Zone Management Program. | Coastal Consistency Statement.
H2 | Ocean County Wastewater Management Plan | The Township shall work with Ocean County to prepare an updated Wastewater Management Plan that address the wastewater and water quality management needs of the Township under the endorsed plan. The updated Wastewater Management Plan must be noticed for approval by DEP prior to CAFRA center designation. | Updated Water Quality Management Plan through municipal amendment.
H3 | Land Use / Zoning Regulations | The zoning ordinance revisions and/or new ordinances must implement the policies and recommendations of the master plan, and accurately reflect center boundaries and/or planning area changes (if applicable), and ordinances that implement appropriate environs protection measures, including zoning, resource protection, and site plan and subdivision ordinance revisions. | Zoning amendments implementing the land use plan element to support development of centers and TOD cores as well as protection of rural and environmentally sensitive areas.
H4 | Water Supply Information | The Township must provide documentation that water supply capacity exists for the amount of growth detailed in the Master Plan, including existing and proposed water supply sources. The Township should identify the available approved allocations and firm capacity. In addition, the Township must identify local water conservation measures. | [Need to clarify with DEP]
*NOTE: The above deadlines are subject to negotiation.