## Sheet1
DENNIS TOWNSHIP ACTION PLAN
Italics = DEP CAFRA Requirements |  |  | 2/14/2007 Township Revision
Item No. | Subject | Action Item | Timetable (Days) | Deadline | Deadline State Agencies | Status
A1 | Proposed Centers | The Township shall work with state agencies to finalize boundaries for its proposed centers. The boundaries will take into account existing environmental resources and capacity constraints. | 180 | 2007-09-01 | 180
A2 | Petition Report Update | Elements of the petition report will be accurately updated based on the fulfillment of this action plan. These elements may include but are not limited to: PIA, population projections, center delineation criteria data, references to new documents. | 60 days after completion of Item A6. |  | 30 days after Township Completion of A2
A3 | Petition Report Update | Due to the extent of change involved to make the petition consistent with the State Plan, the Township shall provide evidence of public participation for the various action items, and in the end pass a resolution supporting the revised petition. | 60 days after completion of Item A8
A4 | Petition Report Update | The Township shall update the Petition Report to improve the Statement of Planning Coordination section to discuss how future center-based development, infrastructure & capacity, and environmental protection will be coordinated with Upper & Dennis Townships and other adjacent municipalities. This section shall also address cross-border issues such as development impacts and potential for shared services. | 60 days after completion of Item A6. |  | 30 days after Township Completion of A4
A5 | Reexamination Report | Township shall prepare a Draft Master Plan Reexamination Report. | 180 | 2007-09-01 | 30 days after Township Completion of A5
A6 | Land Use Plan Element | The Township shall produce a draft Land Use Plan element that takes into account information from the NRI in defining areas for development and preservation. | 360 | 2008-03-01 | 30 days after Township Completion of A6
A7 | Land Use Plan Element | The draft Land Use Plan element shall outline measures for the Township to implement through ordinances to protect environmentally sensitive areas outside centers. | 360 | 2008-03-01 | 30 days after Township Completion of A7
A8 | Land Use Element | The Township Planning Board shall adopt the Reexamination Report and Land Use Plan Element of the Master Plan | 450 | 2008-06-01
A9 | Land Use / Zoning Regulations | The zoning ordinance revisions and/or new ordinances must implement the policies and recommendations of the master plan, and accurately reflect center boundaries and/or planning area changes (if applicable), and ordinances that implement appropriate environs protection measures, including zoning, resource protection, and site plan and subdivision ordinance revisions. | Ordinances to be adopted within 180 days after completion of Item A8. | 2008-12-01
B1 | State Plan Policy Map | The Township will work with State Agencies to refine planning area changes in conjunction with the centers. | 360 | 2008-03-01
C1 | Centers Design | The Township shall provide more detailed concepts of land use patterns in its Petition and Land Use Plan. | 360 | 2008-03-01 | 30 days after Township Completion of C1
C2 | Transportation, Infrastructure, Capacity | Township shall ensure that its Stormwater Management Plan is in compliance with DEP's regulations. |  | SUBMITTED
C3 | Transportation, Infrastructure, Capacity | The Township shall prepare a new Capital Improvement Program aligned with its planned development. This shall be an action item in the PIA. | PIA item
D1 | Housing Element & Fair Share Plan | The Township shall prepare a Draft HEFSP. The Township shall ensure that its Plan Endorsement Petition and COAH petition are generally consistent with each other in terms of where development will be focused and how much growth will be accommodated. The COAH petition will incorporate relevant agreements and information arising from Plan Endorsement negotiations taking place through this Action Plan. This Action Item shall be subject to resolution of COAH regulations. | 360 days or subject to resolution of COAH third round rules | 3/1/2008 or 120 days after resolution of COAH third round rules. | 30 days after Township Completion of D1
DEP1 | Coastal Consistency Statement | The Township shall prepare a statement that addresses natural resource protection and coastal management demonstrating consistency of local plans and ordinances with the goals of the Coastal Zone Management Program. | To be prepared within 60 days after SPC approval of the Plan Endorsement Petition |  | 30 days after Township Completion of DEP1
DEP2 | Cape May County Wastewater Management Plan | The Township shall prepare a Draft Wastewater Management Plan Amendment that address the wastewater and water quality management needs of the Township under the endorsed plan. The Draft Wastewater Management Plan Amendment must be submitted to DEP prior to CAFRA center designation or as early item in the PIA. | 450 | 2008-06-01 | 90 days after Township Completion of DEP2
E1 | Transportation, Infrastructure, Capacity | In order for state agencies to consider enhanced transit service as part of the PIA, the Township must develop the planning and design concepts necessary to show how the service will be viable. These concepts should specify where appropriate development will be focused and how it will be oriented (e.g. pedestrian linkages) to ensure accessibility to transit. | 360 | 2008-03-01
E2 | Transportation, Infrastructure, Capacity | The Township shall provide an overview of transportation issues discussing road networks and alternative modes of transportation such as transit, bicycling and walking. This item should link transportation to land use context in a strategic manner to support center-based development. | 360 | 2008-03-01
F1 | Water Supply | Township will continue its participation in water supply studies and will identify as an action item in the PIA. | PIA item
G1 | Natural Resource Inventory | The Township shall work with OSG and DEP to create a comprehensive NRI. Draft NRI shall be used to develop the Land Use Plan. | 120 | 2007-07-01 | 30 days after Township Completion of G1
G2 | Natural Resource Inventory | The Township’s Planning Board shall adopt the NRI as part of its master plan. | 450 | 2008-06-01
H1 | Environmental Protection Ordinance | The Township shall work with DEP to produce an environmental protection ordinance that contains the measures necessary to protect environmentally sensitive areas within the centers. | 270 | 2007-12-01 | 30 days after Township Completion of H1
H2 | Environmental Protection Ordinance | The Township shall refine its draft ordinance and formally adopt the ordinance to protect environmentally sensitive areas in the Centers and other parts of the Township. | Ordinances to be adopted within 180 days after Twp. Planning Board adoption of Master Plan Land Use Element.
I1 | Emergency Planning | The Township shall provide evidence that it has an Emergency Operating Plan approved by the NJ State Police. (Plan has been approved.) |  | COMPLETE
* The deadlines of the proposed action plan are subject to agreement between the Township and the state agencies.