## Sheet1
MIDDLE TOWNSHIP ACTION PLAN |  |  | 2006-04-26
Italics = DEP CAFRA Requirements
Item No. | Subject | 18/06Action Item | Timetable (Days) | Middle Township Timetable (Days) | Middle Township Deadline | State Agencies Timetable (Days) | State Agencies Deadline | Status | Notes as per 2/20/07 Township Comments
A1 | Natural Resource Inventory | The Township shall work with OSG and DEP to create a comprehensive NRI. | 60 | 150 | 2007-06-01 | 30 days after Township completion of A1 | 2007-07-01 |  | 1 Month extension
A2 | Natural Resource Inventory | The Township’s planning board shall adopt the NRI as part of its master plan. | 90 | 510 | 2008-06-01
B1 | Proposed Centers | The Township shall work with state agencies to finalize boundaries for its proposed centers. The boundaries will take into account existing environmental resources and capacity constraints. | 165 | 150 | 2007-06-01 | 150 | 2007-06-01 |  | 1 Month extension
B2 | Proposed Centers | The Township shall work with OSG and DEP to produce an environmental protection ordinance that contains the measures necessary to protect environmentally sensitive areas within the centers. | 90 | 150 | 2007-06-01 | 150 | 2007-06-01
C1 | Transportation, Infrastructure, Capacity | In order for state agencies to consider enhanced transit service as part of the PIA, the Township must develop the planning and design concepts necessary to show how the service will be viable. These concepts should specify where development will be focused and how it will be oriented (e.g. pedestrian linkages) to ensure accessibility to transit. | 105 | 240 | 2007-09-01 | 30 days after Township completion of C1 | 2007-10-01
C2 | Transportation, Infrastructure, Capacity | Township shall ensure that its Stormwater Management Plan is in compliance with DEP's regulations. The revised Stormwater Management Plan will be filed with NJDEP. | 60 | 90 | 2007-03-01 |  |  |  | (Related ordinances were adopted on 2/7/07.)
C3 | Transportation, Infrastructure, Capacity | The Township shall begin work with Cape May County to revise the Middle Township portion of the Wastewater Management Plan. Completion of this plan will be a condition in the PIA. | 120 | 450 | 2008-04-01 | 60 days after Township completion of C3 | 2008-06-01
C4 | Transportation, Infrastructure, Capacity | Recommendations from the negotiation of the issues described in C1 through C3 will be incorporated into the housing and land use plan elements as needed. | 150 | 360 | 2008-01-01 | 30 days after Township completion of C4 | 2008-02-01
C5 | Transportation, Infrastructure, Capacity | The Township shall prepare a new Capital Improvement Program aligned with its planned development. This shall be included as a PIA item based upon the results of the Land Use Plan recommendations. | 165 |  | PIA ITEM
C6 | Transportation, Infrastructure, Capacity | The Township shall provide an overview of transportation issues discussing road networks and alternative modes of transportation such as transit, bicycling and walking. This item should link transportation to land use context in a strategic manner to support center-based development. | Updated circulation plan element or narrative statement and maps/graphics. | 360 | 2008-01-01 | 30 days after Township completion of C6 | 2008-02-01 |  | Revise item eliminating phrases - at least (if not a full circulation plan); Date should be linked to completion of Draft Land Use Plan.
D1A | Land Use Plan Element | The Township shall prepare a Draft Master Plan Reexamination Report. |  | 360 | 2008-01-01 | 30 days after Township completion of D1A | 2008-02-01
D1B | Land Use Plan Element | The Township shall produce a new land use plan element that takes into account information from the NRI in defining areas for development and preservation. | 165 | 360 | 2008-01-01 | 30 days after Township completion of D1B | 2008-02-01
D2A | Land Use Plan Element | The land use plan element shall outline measures for the Township to implement through ordinances to protect environmentally sensitive areas outside centers, particularly the SL and RR zones. | 120 | 360 | 2008-01-01 | 30 days after Township completion of D2A | 2008-02-01
D2B | Land Use Plan Element | The Township Planning Board shall adopt the Reexamination Report and Land Use Plan Element of the Master Plan. |  | 510 | 2008-06-01
D3 | Land Use / Zoning Regulations | The zoning ordinance revisions and/or new ordinances must implement the policies and recommendations of the master plan, and accurately reflect center boundaries and/or planning area changes (if applicable), and ordinances that implement appropriate environs protection measures, including zoning, resource protection, and site plan and subdivision ordinance revisions. |  | 510 | 2008-06-01
E1 | Housing Element & Fair Share Plan | The Township shall ensure that its Plan Endorsement petition and COAH petition are generally consistent with each other in terms of where development will be focused and how much growth will be accommodated. The COAH petition will incorporate relevant agreements and information arising from Plan Endorsement negotiations taking place through this Action Plan. This item shall be subject to resolution of COAH third round rules. | 165 | 360 days or subject to resolution of COAH third round rules | 1/1/2008 or subject to resolution of COAH third round rules | 30 days after Township completion of E1 | 2008-02-01 |  | Added statement re subject to resolution of COAH third round rules.
F1 | Air Safety and Zoning Compliance | The Township shall correct its petition to address the Cape May County Airport and to affirm that the Township has indeed adopted the proper ordinance. | 30 | 420 | 2008-03-01 | 30 days after Township completion of F1 | 2008-04-01
F2 | Emergency Planning | The Township shall provide evidence that it has an Emergency Operating Plan approved by the NJ State Police. | 30 |  | COMPLETE
F4 | Threatened & Endangered Species Habitat | The Township shall work with DEP on protecting habitat of threatened and endangered species. This information will be part of discussion in finalizing center boundaries and planning areas. | 150 | 150 | 2007-06-01 | 150 | 2007-06-01 |  | 1 month extension
G1 | Petition Report Update | Elements of the petition report will be accurately updated based on the fulfillment of this action plan. These elements may include but are not limited to: PIA, population projections, center delineation criteria data, references to new documents. Draft petition report shall be provided for OSG review. | 180 | 420 | 2008-03-01 | 30 days after Township completion of G1 | 2008-04-01 |  | Petition Report Update shall be completed witiin 90 days of completion of Draft Land Use Plan.
G2 | Petition Report Update | Due to the extent of change involved to make the petition consistent with the State Plan, the Township shall provide evidence of public participation for the various action items, and in the end pass a resolution supporting the revised petition. | 180 | 510 | 2008-06-01 | 30 days after Township completion of G2 | 2008-07-01
G3 | Petition Report Update | The Township shall improve the Statement of Planning Coordination section to discuss how future center-based development, infrastructure & capacity, and environmental protection will be coordinated with Upper & Dennis Townships and other adjacent municipalities. This section shall also address cross-border issues such as development impacts and potential for shared services. | 180 | 420 | 2008-03-01 | 30 days after Township completion of G3 | 2008-04-01
H1 | Coastal Consistency Statement | The Township shall prepare a statement that addresses natural resource protection and coastal management demonstrating consistency of local plans and ordinances with the goals of the Coastal Zone Management Program. |  | 420 | 2008-03-01 | 30 days after Township completion of H1 | 2008-04-01
H2 | Cape May County Wastewater Management Plan | The Township shall work with Cape May County to prepare a Draft Wastewater Management Plan Amendment that addresses the wastewater and water quality management needs of the Township under the endorsed plan. The complete updated Wastewater Management Plan must be noticed for approval by DEP prior to CAFRA Center Designation |  | 450 | 2008-04-01 | 90 days after Township completion of H2 | 2007-07-01 |  | DEP has requested 90 days to review the WMA. This would change the Agency review date to 7/1/2007.
H4 | Environmental Protection Ordinance | The Township shall refine its draft ordinance and formally adopt the ordinance to protect environmentally sensitive areas in the Centers and other parts of the Township. |  | 510 | 2008-06-01
H5 | Water Supply Information | The Township shall coordinate with DEP in the final phase of the study of the Cohansey aquifer to determine best scenario(s). Pending the results of the study, and the choosing of the preferred water supply scenario, the Township will work with the water purveyors to provide an assessment of existing public water supply wells with current allocation(s) and ability to accommodate projected growth. | Documentation of adequate water supply from utilities authority and/or private purveyor(s). | 360 | 2008-01-01 | 30 days after Township completion of H5 | 2008-02-01 |  | This is a new item. The Township will work with the utilities (NJAmerican and Wildwood Water) to prepare an assessment of water supply and allocation capacity.