## Sheet1
Stafford Township - Planning and Implementation Agreement (DRAFT) | [5 empty] | 2007-03-28 | Monitoring
May 4, 2007 (revised from March 14, 2007)
NOTE: Wholly new or deleted items identified under Topic column in brackets and capital letters [THUS]; other additions indicated in boldface and underlined thus; other deletions indicated in brackets [thus].
Topic | # | Subtopic | Activity (local action unless otherwise indicated) | State/County Assistance | Timetable (MM/DD/YY) |  | Status Notes | Complete?
General | A1 | CAFRA Center Boundary, revised planning area boundaries | Township to submit drafts of all new and revised planning documents required by this PIA to OSG, DEP and the Pinelands Commission. | OSG, DEP and Pinelands Commission to provide technical assistance | 20 days prior to adoption by township
General | A2 | Management area changes in Pinelands National Reserve | The Township will submit to the Pinelands Commission, with a copy to DEP and OSG, a completed application to amend its certified master plan and land use ordinances for that portion of the Township located within the Pinelands National Reserve but not located within the Pinelands Area. The submission shall be consistent with the petition for plan endorsement and PIA approved by the State Planning Commission. All areas proposed to be Planning Area 5 in the petition shall be proposed to be Forest, Preservation or other appropriate Area and all areas proposed to be Planning Area 2 or a designated center in the petition shall be proposed as a Regional Growth Area in the submission to the Pinelands Commission. The submission shall include all documents adopted pursuant to this PIA as of the date of the submission to the Pinelands Commission. | DEP and the Pinelands Commission will coordinate their respective reviews | [7/18/07] 8/16/07
General | A3 | CAFRA Center Boundary, revised planning area boundaries |  | DEP to provide the requisite notice concerning designated center and revised planning area boundaries in the NJ Register | [9/1/07] 10/1/07
General | A4 | Plan Endorsement review | By [March 28, 2008] May 16, 2008 and biennially thereafter, Stafford Township shall submit a report to OSG and the public concerning the terms of this PIA and related efforts pursuant to NJAC 5:85-7.12(c). Pursuant to N.J.A.C. 5:85-7.12(c), the first review is scheduled for one year after Endorsement due to significant PIA items that must be adopted within that timeframe. |  | [3/28/08] 5/16/08 and ongoing
General | A5 | Inter-governmental coordination | Coordinate with planning efforts of adjoining municipalities, the County and State and regional planning efforts particularly concerning: regional planning, transportation, economic development, tourism, natural resource protection and open space and recreation. | County Planning Board, OSG, DOT, DEP | Ongoing
General | A6 | Revised Plan Endorsement Process | Once the new Plan Endorsement process is in place, the Township will have the option to work with state agencies to outline an action plan and timetable to attain the new standard for the benefit of additional state assistance. This action plan may be merged with this PIA, due to overlapping activities. | OSG and other state agencies | 90 days after new rules and guidelines are adopted
Land Use & Zoning | B1[.2] | Master Plan update | Update Master Plan so that it is consistent with the revised Center and Planning Area boundaries and related State Plan criteria. The Master Plan should also include the Stafford Business Park redevelopment area in its analysis. | OSG | [7/18/07] 8/16/07
Land Use & Zoning [DELETED ITEM] | B1.1 | Draft Land Use Plan | Work with OSG and DEP to resolve any significant consistency issues in the draft plan prior to Plan Endorsement.??? | OSG, DEP | [4/1/07]
Land Use & Zoning | B2 | Master Plan update | The Master Plan should incorporate growth projections that the Township used in its Plan Endorsement and COAH petitions. If there are significant revisions, the Township shall inform OSG and COAH and provide justification. | COAH and OSG | [7/18/07] 8/16/07
Land Use & Zoning | B3 | General zoning update | Manage growth within Regional Center through zoning, density controls, and ensuring consistency with the existing sewer service areas. | DEP and OSG | [12/31/2007] Ongoing
Land Use & Zoning | B4 | General zoning update | Continue coordination with Pinelands Commission; ensure preservation and conservation of PA5, lower density in PA4, and medium density of mixed uses in PA2. | Pinelands Commission, OSG | 2007-12-31
Land Use & Zoning | B5 | Interim zoning update | The Township will revise any zoning and redevelopment plans for areas outside the Center and Suburban Planning Area to prohibit uses and development that would adversely affect the environmentally sensitive features in those areas. | DEP and OSG | [7/18/07] 8/16/07
Land Use & Zoning | B6 | Regulations | Ordinances for zoning, resource protection, and site plan and subdivision review revisions shall provide for the implementation of appropriate environs protection measures. | DEP and OSG | [7/18/07] 8/16/07 and ongoing
Housing | C1 | Affordable housing | [File a petition with COAH for substantive certification.] Revise petition filed in July 2005 as necessary pursuant to any relevant COAH rule changes following the January 2007 Appellate Court decision. | COAH | 180 days after resolution of COAH third round rules
Housing | C2 | Affordable housing | Ensure appropriate levels of affordable housing through implementation of COAH-certified Housing Plan. | COAH | Ongoing
Housing | C3 | General | Provide for areas of concentrated growth, including senior and affordable housing accessible to basic public and retail services, primarily in the Center[s] and Pinelands Regional Growth Area. | OSG and COAH | [7/18/07] Ongoing
Redevelopment | D1 | Stafford Business Park | Implement Stafford Business Park Redevelopment Plan. | Pinelands Commission, OSG, DOT, COAH | Ongoing
Open Space & Recreation | E1 | Open Space & Recreation Plan update | Produce open space & recreation element for Master Plan to ensure provision of accessible regional- and neighborhood-level open space and recreation facilities to serve existing population and new growth. The plan must identify and examine open space and recreation resources important to the municipality, and map out an implementation strategy to protect, manage and improve them. | DEP | [7/18/07] 8/16/07
Open Space & Recreation | E2 | Open Space | Continue to preserve and acquire open space parcels through open space trust funds and Green Acres Program. | DEP and Ocean County | Ongoing
Environmental Resources | F1 | Stormwater Management | Review and evaluate changes to Stormwater Management Regulations | DEP and Ocean County | [7/18/07] 8/16/07
Environmental Resources [DELETED ITEM] | F2 | C1 Waterways | [Designate] Apply for C1 status for Mill Creek and other appropriate waterbodies. | DEP | 2007-09-24
Environmental Resources | F3 | Wellhead Protection Plan | [Create and implement a Wellhead Protection Plan to protect water supply wells.] Revise and implement Wellhead Protection Plan in accordance with DEP model plans and ordinances. The Wellhead Protection Plan shall manage potential sources of contamination and threatening activities that occur within a source water protection area. Plans shall include delineation of the source water protection area, an inventory of known and potential contamination sources, a determination of water supply system susceptibility to these contaminates, public outreach and education about threats, implementation measures to prevent, reduce or eliminate threats, and contingency planning strategies to address with water supply contamination or service interruption emergencies. Source Water Protection Plans can be developed for the protection of either groundwater supplies of drinking water, wellhead protection areas or surface water supplies, intakes and reservoirs and their drainage. | DEP | 2009-03-28
Environmental Resources | F4 | Coastal Consistency Statement | The Township shall prepare a statement that addresses natural resource protection and coastal management demonstrating consistency of local plans and ordinances with the goals of the Coastal Zone Management Program. | DEP | [5/27/07] 8/16/07
Environmental Resources | F5 | Habitat Conservation [Plan] | [The Habitat Conservation Plan specifies conservation requirements and implementation measures to fully mitigate any incidental take of the suitable habitat of state-listed Endangered or Threatened species. Conservation Plan requirements may include a mix of options that include the creation, enhancement, restoration, acquisition or preservation of habitat and/or monetary contributions for these purposes.] The Township shall work with DEP on habitat conservation and incorporate this issue into the Conservation Element of the master plan, to be followed by implementation measures as necessary. | DEP | 2010-03-28
Environmental Resources | F6 | Water Conservation [Plan] | [Prepare and implement Water Conservation Plan to:] The Township shall incorporate water conservation into the Conservation Element of the master plan, to be followed by implementation measures to: • reduce water consumption levels • reduce the loss and waste of water • improve efficiency in the use of water • increase recycling and reuse in the water supply • extend the life of current water supplies by reducing the rate of growth in demand - water conservation measures through twp mua. | DEP | 2009-03-28
Environmental Resources | F7 | Stream Corridor Protection Plan | [The] Revise and update Stream Corridor Protection Plan according to new DEP regulations. The plan shall establish the basis for a municipal Stream Corridor Protection Ordinance. The plan shall consider all waterways within or forming the boundary of a municipality and any State-required stream setback, wetland transition area, and riparian buffer. The plan shall also: • establish a comprehensive waterways map which will denote the standard limits of construction disturbance for each waterway based upon the best currently available information. • identify areas where existing or proposed development patterns conflict with and any State required stream setback, wetlands transition area, and riparian buffer. • provide for a systematic procedure to allow for alternative stream corridor construction setbacks based on an evaluation of the specific stream corridors in the study area to determine the extent of the features critical to supporting the functions of a healthy riparian buffer for the stream corridors in question and the requirements of applicable State statutes and regulations. • identify and prioritize locations for rehabilitation of areas with disturbed stream corridors. | DEP | 2009-03-28
Transportation & Circulation | G1 | Circulation Plan Update | Update circulation plan to incorporate concepts and standards from DOT's Mobility and Community Form guidelines. | DOT* | [7/18/07] 8/16/07
Transportation & Circulation | G2 | Integrated Transportation - Land Use | Selectively accommodate commercial development as appropriate in the Route 9 and Route 72 Corridors in a manner consistent with compact, mixed use patterns that enhance transportation mode choice and maximize the efficiency of the existing roadway network by distributing traffic more evenly among state, count and local roadways. Future planning in the Route 9 and 72 corridors principally will center on revitalization, redevelopment and infill development. The vision for these corridors should emerge in concert with the work of the related corridor studies. | DOT* | Ongoing
Transportation & Circulation | G3 | Integrated Transportation - Land Use | Implement strategies identified in the Route 9 Corridor Study to alleviate traffic congestion, reduce accident rates, improve traffic calming, and support mixed-use commercial development. | DOT* | 3/28/2010 Ongoing
Transportation & Circulation | G4 | Pedestrian | Increase pedestrian connectivity between parks, and open space, residential neighborhoods and commercial centers. | DOT* | Ongoing
Transportation & Circulation | G5 | Strategic improvements | Implement roadway and intersection improvements on Routes 9 and 72 in conjunction with G1, G2. Certain improvements shall meet DOT Traffic Engineering guidelines as part of the scoping process for any new projects. | DOT* | 2010-03-28
Transportation & Circulation | G6 | Road capacity / buildout analysis | Prepare an analysis to determine whether enough capacity exists on the state highways and their immediately adjacent roadway network to accommodate the traffic generated by build-out based upon the current zoning. | DOT* | [7/18/07] 8/16/07
Transportation & Circulation | G7 | Goods movement | As part of Circulation Plan update, incorporate a strategy for dealing with retail, commercial or truck freight traffic along state, county and municipal roadways as it relates to existing and future land use patterns. | DOT* in conjunction with Route 9 Study | [7/18/07] 8/16/07
Transportation & Circulation | G8 | Transportation Demand Management (TDM) | As part of Circulation Plan update, incorporate a strategy to utilize transportation demand management (TDM) measures for trip reduction where applicable, such as ridesharing, vanpooling, transit and park-and-rides. | DOT* in conjunction with Route 9 Study | [7/18/07] 8/16/07
Transportation & Circulation | G9 | Improved Pedestrian Crossings | Partner with NJ DOT to improve pedestrian crossings at key nodal locations on Route 9. | DOT* | Ongoing
Transportation & Circulation | G10 | Access Management | Partner with NJ DOT to create an Access Management Plan along the Route 9 Corridor. The Township will incorporate any necessary changes to the Township's Zoning Ordinance so that it is in conformance with the Highway Access Code for lands adjacent to Routes 9 and 72. The Township will also conditionally approve subdivision and site plans based on consistency with the requirements of the Highway Access Code. The Township will also undertake a capacity analysis that addresses traffic generation under build-out scenarios for current zoning and proposed redevelopment. | DOT* in conjunction in Route 9 study | 2008-09-28
Transportation & Circulation [NEW ITEM] | G11 | Bus transit | If the bus priority shoulder lane project on Route 9 extends to this part of the County, the Township shall work with NJ TRANSIT and DOT to ensure that any future plans for the re-design of the carriage way and/or intersections incorporate bus priority traffic signal improvements (e.g., queue jumps and/or green time extensions) and/or bus pull-ins and pull-outs in key locations. | NJ TRANSIT, DOT* | Conditional / Ongoing
Infrastructure | H1.1 | Wastewater Management Plan | [Update] Review Wastewater Management Plan annually to ensure sewer service area is consistent with designated growth area. Amend as needed, with a comprehensive update ever six years, consistent with Master Plan updates. | DEP, Ocean County | [Annual] Review annually and amend as needed. Update every six years.
Infrastructure | H1.2 | Draft Wastewater Management Plan | Work with DEP to resolve any significant consistency issues in the draft plan prior to Plan Endorsement. | DEP | [4/1/2007] Township has submitted septic suitability report and had a pre-application meeting with DEP.
Infrastructure | H2 | Draft Wastewater Management Plan | Submit to Ocean County and DEP a draft amended Wastewater Management Plan for [Central Ocean County] Stafford Township that accommodates new development and redevelopment within the limits of the Center and Planning Area 2 and removes lands that are outside these areas from the sewer service area limits, unless already served by existing sewer connections or have a documented pre-existing sanitary health problem due to on-site wastewater disposal. [The updated Wastewater Management Plan must be noticed for approval by DEP prior to CAFRA center designation.] | Ocean County, NJDEP | [7/18/07] 6/15/2007
Infrastructure | H3 | Wastewater Management Plan |  | DEP review and action on the amended Wastewater Management Plan | 6 months after County submits to DEP
Infrastructure | H4 | Sewer & Water Connections | Provide sewer and water connections as needed within the Center and Planning Area 2, and also in outside existing developed areas such as Mayetta, Royce Run, and Mallard Island if public health and safety issues arise (e.g. from failed septic systems). | DEP | Ongoing
Infrastructure | H5 | Septic Management Plan | The Septic Management Plan shall establish the strategies and implementation measures necessary to ensure that septic systems are properly maintained and that new systems are located, designed, installed and maintained in accordance with State statute and regulation so as to protect ground water quality and to ensure the continuing viability of this means of wastewater management. | DEP | 2009-03-28
Urban Design / Sense of Place | I1.1 | Revitalization | Identify areas for economic revitalization within Regional Center. | OSG | [12/31/2007] Ongoing
Urban Design / Sense of Place | I1.2 | Revitalization | As any new redevelopment, infill and/or rehabilitation opportunities arise, work with OSG to plan for high-quality design and development consistent with other elements of this PIA. | OSG and interagency teams (DOIT, BRIT) | [12/31/2009] Ongoing
Urban Design / Sense of Place | I2 | Historic Preservation Plan | As part of the new Master Plan, prepare and adopt a Historic Preservation [Plan] Element based upon a Cultural Resources Inventory. | DEP and OSG | [7/18/07] 8/16/07
Urban Design / Sense of Place | I3 | Historic Preservation Plan | Adopt a historic preservation ordinance that sets forth a process for designation and protection of historic sites and districts. The ordinance must articulate the design guidelines or standards for regulating these properties in order to prevent their unauthorized loss, alteration, or demolition, and where applicable, empower a local historic preservation commission to administer the Historic Preservation Plan. See N.J.S.A. 40:55D-28. | DEP and OSG | 3/18/[2007] 2008
Emergency Planning | J1 | Inter-municipal coordination | Coordinate hazard mitigation and evacuation planning with Long Beach Island municipalities. This activity should include consideration of strategic improvements on Route 72 as well as appropriate land use planning along the corridor. | NJ State Police, DOT, OSG | Ongoing
* When requested, NJDOT will give priority consideration to providing technical assistance consistent with program requirements and subject to the availability of state resources.