## Sheet1
City of Asbury Park Planning and Implementation Agreement (DRAFT)
May 20, 2009 (revised from 12/5/07 PIA)
NOTE: Additions indicated in boldface and underlined thus; deletions indicated in brackets [thus].
Topic | Item No. | Activity | Local Effort | State Assistance | Time Frame
Land Use | A1 | -Use the County Ecological Resource Inventory when issues surrounding land use planning and development review arise | -City Planning Board and Board of Adjustment | N/A | Immediate and Ongoing
Land Use | A2 | -Amend the Land Development Regulations to be consistent with the Residential Site Improvement Standards where appropriate | -City Council and Planning Board to consider drafting of ordinances | -OSG Technical Assistance | 1 year
Land Use | A3 | -Create a telecommunications ordinance, inclusive of protective conditions designed to minimize visual impact of any equipment | -City Council and Planning Board to consider drafting of ordinances | -OSG Technical Assistance | 2007-12-07
Land Use | A4 | -Review the City Zoning Ordinance for consistency with bulk standards | -City Council and Planning Board to consider amending ordinance accordingly | -OSG Technical Assistance | [Draft ordinance by Dec-07, adopted by Mar-08] Draft ordinances by Sept 30, 2009; adopted by December 31, 2009
Land Use | A5 | -Consider the extension of Steiner Place to create additional parking opportunities and access to existing businesses | -City Council to consider strategy as part of a Main Street Redevelopment Plan | -OSG Technical Assistance | Draft work products by Dec-07, final plan and accompanying items adopted by Apr-08
Land Use | A6 | -Examine land uses around the transportation center (public transit hub) and change to be more consistent with transit oriented development principles | ­Include appropriate densities in the planned Main Street Redevelopment Plan ­City Council and Planning Board to consider revising zone regulations for areas adjacent to the transportation center ­Completion of the “Transportation Improvement Study” funded partially by the NJTPA and administered by the Monmouth County PB | ­NJ Transit and OSG technical assistance ­Smart Futures Planning Grant Assistance ­NJTPA funds (received for “Transportation Improvement Study” by the Monmouth County PB) | Draft work products by Dec-07, final plan and accompanying items adopted by Apr-08
Land Use | A7 | -Implement a variety of techniques to mitigate areas of the city that have demonstrated environmental justice issues | -City Council and Planning Board | -NJDEP technical assistance | Ongoing
Land Use | A8 | -Update the master plan to include all redevelopment areas | -City Planning Board |  | Ongoing
Land Use | A9 | -Evaluate transit friendly development techniques and capitalize on the City’s mass transit resources through a Circulation Plan Element of the Master Plan | -City Planning Board |  | Ongoing
Land Use | A10 | -Locate and potentially purchase additional properties for active recreation | -Work with Monmouth County | -Green Acres Funding | Ongoing
Land Use | A11 | -Promote beachfront activities | -Media promotions and advertisements | -Technical and financial assistance | Ongoing
Land Use | A12 | -Maintain/operate existing facilities | -Consider recreation department | -Technical and financial assistance | Ongoing
Land Use | A13 | -Evaluate use of school facilities | -Strengthen relationship with the Board of Education |  | Ongoing
Land Use | A14 | -Determine the level of change to land uses that have occurred since the last Master Plan update, revise zoning map accordingly | -City Planning Board to update the land use element of the master plan |  | Ongoing
Land Use | A15 | -Develop and adopt a Recreation Element of the Master Plan which includes an inventory City recreational space and project needs | -City Planning Board |  | Ongoing
Land Use | A16 | -Create a senior citizens center | -Department of Social Services | -Technical and financial assistance
Land Use | A17 | -Build on work started this summer on expanding recreation activities in the West Side Recreation Center and Boys Club facilities | -Department of Social Services |  | Ongoing
Housing | B1 | -Develop a Housing Element and Fair Share Plan in accordance with third round COAH regulations | -City Planning Board |  | [Draft work products by Jan-08, final items adopted by Apr-08] Draft work products by June 15, 2009; Final items adopted by December 31, 2009
Housing | B2 | -Identify opportunities to create diverse housing opportunities and affordable housing | -Prepare a Housing Element, Fair Share Plan, and Affordable Housing Strategy |  | [Draft work products by Jan-08, final items adopted by Apr-08] Draft work products by June 15, 2009; Final items adopted by December 31, 2009
Housing | B3 | -Estimate affordable housing needs and targets and an action plan to meet goals | -Prepare a Housing Element, Fair Share Plan, and Affordable Housing Strategy |  | [Draft work products by Jan-08, final items adopted by Apr-08] Draft work products by June 15, 2009; Final items adopted by December 31, 2009
Housing | B4 | -Continue to rehabilitate housing units | -Maintain RCA program | -Technical assistance | Ongoing
Housing | B5 | -Update the Housing Element of the Master Plan and determine the City’s affordable housing obligation | -City Planning Board |  | [Ongoing] Draft work products by June 15, 2009; Final items adopted by December 31, 2009
Transportation | C1 | -Draft zoning regulations consistent with the State Highway Access Management Code | -Main Street Redevelopment Plan, City Council and Planning Board | -When requested, NJDOT will give priority consideration to providing technical assistance consistent with program requirements and subject to the availability of state resources. | Draft work products by Dec-07, final plan and accompanying items adopted by Apr-08
Transportation | C2 | -Develop a plan and schedule for the repair and upgrade of the Transportation Center | -Capital Improvement plan, Main Street redevelopment plan, County Transportation Improvement Study, city Council and Planning Board ­Apply for appropriate funding programs or seek NJDOT or NJ Transit technical assistance | -When requested, NJDOT and NJ Transit will give priority consideration to providing assistance consistent with program requirements and subject to the availability of funding and staff resources. | 1-3 years
Transportation | C3 | -Implement Recommendations from the County Transportation Improvement Study | -Main Street Redevelopment Plan, Capital Improvement Plans, City Council and Planning Board ­Apply for appropriate funding programs or seek NJDOT or NJ Transit technical assistance | -When requested, NJDOT will give priority consideration to providing assistance consistent with program requirements and subject to the availability of Funding and staff resources, OSG | 1-5 years
Transportation | C4 | -Implement the recommendations in the Walkability Audit | -Capital Improvement Plan, City Council and Planning Board ­Monmouth County PB and Engineering Assistance ­Apply for appropriate funding programs or seek NJDOT technical assistance | -When requested, NJDOT will give priority consideration to providing assistance consistent with program requirements and subject to the availability of funding and staff resources, OSG | 1-5 years
Transportation | C5 | -Complete a build out analysis or assessment of the ability of the roadway network to accommodate projected development. | -City Planning Board and City Council ­Apply for appropriate funding programs or seek OSG or NJDOT technical assistance | -When requested, OSG and NJDOT will give priority consideration to providing assistance consistent with program requirements and subject to the availability of funding and staff resources | 2-5 years
Transportation | C6 | -Examine traffic calming measures along Main Street (S.R. 71) | -City Council (Main Street Redevelopment Plan) ­Apply for appropriate funding programs or seek NJDOT assistance | -When requested, OSG and NJDOT will give priority consideration to providing assistance consistent with program requirements and subject to the availability of funding and staff resources | Draft work products by Dec-07, final plan and accompanying items adopted by Apr-08
Transportation | C7 | -Improve pedestrian mobility between Ocean Grove and Asbury Park | -City Engineer, City Council ­Apply for appropriate funding programs or seek NJDOT technical assistance | -When requested, NJDOT will give priority consideration to providing assistance consistent with program requirements and subject to the availability of funding and staff resources | 3 to 4 years
Transportation | C8 | -[Explore, where applicable, the appropriateness of developing Access Management Plans for pertinent sections of state highways as provided for in the state Highway Access Management Code] Explore the appropriateness of developing an access management plan for pertinent sections of Route 71 | -City Council and Planning Board to consider drafting of plan ­Apply for appropriate funding programs or seek NJDOT assistance | When requested, NJDOT will give priority consideration to providing assistance consistent with program requirements and subject to the availability of funding and staff resources | [3 to 4 years] Ongoing
Transportation | C9 | -Inventory existing roadway system and classify roadways (include in Circulation Element of Master Plan) | -City Planning Board |  | Ongoing
Transportation | C10 | -Inventory public transportation facilities and services and increase accessibility | -Monmouth County (Transportation Improvement Study) ­City Council and administration to work with County and NJ Transit to enhance existing transit facilities as identified in the study | -Existing NJTPA funded study ­When requested, NJ Transit will give priority consideration to providing technical assistance consistent with program requirements and subject to the availability of staff resources | Ongoing
Transportation | C11 | -Capitalize on opportunities for jitney/shuttle bus service in the City | -UEZ Board and City Council to assess opportunities and apply for appropriate funding opportunities | -When requested, NJ Transit will give priority consideration to providing assistance consistent with program requirements and subject to the availability of funding and staff resources | Ongoing
Transportation | C12 | -Incorporate the street hierarchy system found in the RSIS into the Circulation Element of the Master Plan | -City Planning Board |  | Ongoing
Infrastructure | D1 | -Develop and adopt Stormwater Pollution Prevention Plan and Stormwater Management Plan | -City Engineer, Council and Planning Board | -DEP and Monmouth County technical assistance | February 2, 2006
Infrastructure | D2 | - Enhance gateways into the City visually and provide wayfinding signage | -UEZ Board, Planning Board and City Council ­Apply for appropriate funding programs or seek NJDOT technical assistance | -When requested, NJDOT will give priority consideration to providing assistance consistent with program requirements and subject to the availability of funding and staff resources | [2 to 3 years] Ongoing
Infrastructure | D3 | -Develop a five year capital improvement plan with a 6 year planning horizon per the Municipal Land Use Law 40:55D-29 | -City Planning Board | -Technical assistance | [2 to 3 years] March 31, 2011
Infrastructure | D4 | -Confirm the condition and capacity of the City’s stormwater drainage system through creation of a Utilities Element of the Master Plan | -City Planning Board |  | Ongoing
Infrastructure | D5 | -Confirm the condition and capacity of existing sanitary sewer lines through creation of a Utilities Element of the Master Plan | -City Planning Board |  | Ongoing
Infrastructure | D6 | -Enhance streetscape in the Historic Central Business District | -City Planning Board to finalize design, City Council to adopt | -Identification of grant sources | Ongoing
Economic Development | E1 | -Assess the City’s businesses and industries and identify market segments which enjoy competitive advantages in Asbury through an Economic Plan Element in the Master Plan | -City Planning Board |  | Ongoing
Economic Development | E2 | -Continue to actively utilize and promote the UEZ façade grant program while updating the design regulations | -UEZ Board | -Main Street NJ technical assistance | Ongoing
Economic Development | E3 | -Promote public art in public spaces | -City Council could place provision in redeveloper agreements ­Council to require in redevelopment plans |  | Ongoing
Economic Development | E4 | -Consider the creation of special improvement districts | -Promote public and business participation | -Technical Assistance | Ongoing
Economic Development | E5 | -Continue to strengthen job-creation strategies and job training | -UEZ Board to continue with efforts to create a employment center, hire a human resource coordinator |  | Ongoing
Intergovernmental Coordination | F1 | -Designation of Asbury Park as a CAFRA Urban Center |  | -DEP to provide the requisite notice in the NJ Register | 90 Days
Intergovernmental Coordination | F2 | -Continue communication with and build stronger relationships with the City Housing Authority | -City Council and City Administration to work with Housing Authority on new housing and housing rehabilitation activities |  | Ongoing
Intergovernmental Coordination | F3 | -Coordinate with surrounding municipalities, County, State and regional planning efforts, RE: transportation, park system, regional planning | -City Council and Planning Board, Redevelopment Director, to coordinate with Monmouth County, neighboring municipalities ­Attend County meetings addressing regional and local planning issues | -County PB, OSG, COAH | Ongoing
Intergovernmental Coordination | F4 | -By May 18, 2007 and biennially thereafter and within 6 months after adoption of any new or significantly reexamination report, land use ordinance or other planning document submitted as part of the petition for plan endorsement, the City of Asbury Park shall submit a report to OSG and the public concerning the statues of the City’s Planning and Implementation Agreement efforts pursuant to NJAC 5:85-7.12(c). | -City Council and City Administration |  | Ongoing
Historic Preservation | G1 | -Encourage the preservation of bluestone and slate sidewalks | ­Drafting of ordinance protecting existing bluestone sidewalks and consideration of requiring them as part of all new developments where bluestone sidewalks are prevalent (Planning Board, Board of Adjustment, City Engineer, Redevelopment Director) ­City Council to consider amending ordinance |  | [Draft ordinance by Dec-07 for consideration by City Council] Community outreach to commence by January 31, 2010; Draft ordinance by October 30, 2010 for consideration by City Council
Historic Preservation | G2 | -Update Historic Preservation Element of the Master Plan | -City Planning Board | -SHPO, OSG technical assistance | 2 years
Historic Preservation | G3 | -Encourage/promote preservation of historic properties | -City Historical Society | -SHPO, Monmouth County | Ongoing
Historic Preservation | G4 | -Continue to develop and refine design standards for historic districts | -City Council and Planning Board | -SHPO, OSG technical assistance | Ongoing
Historic Preservation | G5 | -Ensure that all housing rehabilitation programs follow existing community design regulations | -RCA program, City Planning Board, Board of Adjustment |  | Ongoing
Historic Preservation | G6 | -Redefine historic districts and identify additional properties eligible for historic designation in the refined historic Preservation Element of the Master Plan | -City Planning Board |  | Ongoing
Historic Preservation | G7 | -Consider the creation of a historic preservation ordinance and historic preservation commission | -City Council and Planning Board | -SHPO, OSG technical assistance | [Draft ordinance by Dec-07 for consideration by City Council] Community outreach to commence by January 31, 2010; Draft ordinance by October 30, 2010 for consideration by City Council
Historic Preservation | G8 | -Evaluate the benefits of Certified Local Government (CLG) Status | -City Council and Planning Board | -SHPO, OSG technical assistance | Ongoing