## PIA
MIDDLE TOWNSHIP PIA: Adopted by the SPC on 9/28/2011
Item No. | Activity | Responsible Party | Deadline |  | State Deadline | STATUS w/ date submitted
TRANSIT AND TRANSPORTATION
NJT1 | Explore the feasibility of different seasonal transportation options in order to reduce seasonal traffic congestion. | SJTPO, County, Middle Township in consultation with NJDOT and NJ TRANSIT | Medium | 2014-10-01
NJT2 | Explore vehicular at grade crossings across the existing rail ROW that coordinate directly with the Township's Transportation Analysis in order to provide more efficient local circulation and alternatives to Rt 9. | Middle Township in consultation with the County, NJDOT and NJ TRANSIT | Short | 2012-10-01
NJT3 | Pursue improved bus transit facilities to increase route headways, increase bus pickup locations, develop central transit locations coordinated with parking. | Middle Township and County to coordinate with NJT. | Short | 2012-10-01
NJT4 | Determine feasibility of private east-west shuttle service in coordination with the mainland and barrier island municipalities. The goal of this regional service would be to enhance transit service between campgrounds, mainland attractions and barrier island destinations. | The County will assist in an effort to determine feasibility of private east-west shuttle service in coordination with the mainland municipalities. | Medium | 2014-10-01
NJDOT1 | Construct key paper streets Improvements listed in the Transportation Improvement Study | Middle Township Responsible Party | Long | 2017-10-01
NJDOT2 | Develop western alternative roadway to Route 9 | Middle Township, coordinating with landowners | Long | 2017-10-01
NJDOT3 | Develop new roadway of Honeysuckle Lane extension | Middle Township | Long | 2017-10-01
NJDOT4 | Develop new roadway of Shunpike Road extension | Cape May County or Middle Township | Long | 2017-10-01
NJDOT5 | Plan for other roadway connections in general locations | Middle Township, coordinating with landowners | Long | 2017-10-01
NJDOT6 | Coordinate with K-Mart Plaza landowners to plan alternative access | Middle Township; NJDOT | Long | 2017-10-01
NJDOT7 | Explore installation of new median on Route 47 in coordination with prospective developers and other agencies | NJDOT | Long | 2017-10-01
NJDOT8 | Install signage directing motorists to Rio Grande Avenue | Cape May County | Short | 2012-10-01
NJDOT9 | Pursue addition of southbound left turn lane, modify signal timing at Route 9 and Route 47 | NJDOT, and coordination with Wal-Mart developers | Medium | 2014-10-01
NJDOT10 | Investigate modification of signal timing at Route 9 and Stone Harbor Boulevard | NJDOT | Short | 2012-10-01
NJDOT11 | Evaluate one-way treatment for Mechanic Street and Hand Avenue | Cape May County; Middle Township | Short | 2012-10-01
NJDOT12 | Pursue installation of bulb-outs or median islands on Route 9 in Cape May Court House, and stripe parking spaces through state and federal funding sources | NJDOT | Short | 2012-10-01
NJDOT13 | Install parking lot signage to County Lot | Cape May County | Short | 2012-10-01
NJDOT14 | Adopt Complete Streets policy | Middle Township | Short | 2012-10-01
NJDOT15 | Adopt access management ordinance | Middle Township | Short | 2012-10-01
NJDOT16 | Adopt shared parking ordinance | Middle Township | Short | 2012-10-01
NJDOT17 | Adopt street connectivity ordinance | Middle Township | Short | 2012-10-01
NJDOT18 | Investigate development of bicycle network; phasing in physical improvements | NJDOT; Cape May County; Middle Township | Long | 2017-10-01
NJDOT19 | Pursue installation of sidewalks on priority roadways | NJDOT; Cape May County; Middle Township | Long | 2017-10-01
NJDOT20 | Investigate signal optimization along Route 9 on summer weekends | NJDOT | Short | 2012-10-01
NJDOT21 | Modify the Transportation Improvement Analysis by adding the MLUL requirements for a circulation element. Adopt the circulation element. | Middle Township | Short | 2012-10-01
NJDOT22 | Strongly request that New Jersey Highway Authority proceed with the planned grade separated interchange at Crest Haven Boulevard, Stone Harbor Boulevard and Shell Bay Avenue along with the elimination of other at-grade intersections. | NJDOT funding /SJTPO TIP - NJTPK Authority | Long | 2017-10-01
NJDOT23 | Extend Mechanic Street eastwardly to Bayberry Drive to provide secondary ingress/egress to schools and assess related access roads improvements. | NJ Turnpike Authority and County of Cape May | Long | 2017-10-01
NJDOT24 | Provide southbound on/off ramps at Shell Bay Avenue to reduce traffic through the Cape May Court House area. | NJDOT funding /SJTPO TIP - NJTPK Authority | Long | 2017-10-01
NJDOT25 | Revise the Township's LDO to comply with the MLUL requirement that municipal zoning conform with the State Highway Access Management Code. The Township can address this issue 4 different ways: Wait for main street designation in the access management code, create an access management plan, with NJDOT to make a DTS change or wait for NJDOT to create an access management guide. | NJDOT technical assistance and funding | Medium | 2014-10-01
NJDOT26 | Prepare and implement Route 9 Cape May County Access Management Plan with other Mainland Route 9 communities to reduce congestion along corridor. | County to coordinate regional access plan with Cape May mainland municipalities. NJDOT Local Planning Assistance funds. | Medium | 2014-10-01
INFRASTRUCTURE
DEP1 | Prepare and submit a Wastewater Management Plan for the Township that implements the 2011 Master Plan and Zoning ordinance; Expanding sewer service areas to include all lands within planned Centers except Goshen Hamlet and the Mattera Farm in Rio Grande. | NJDEP permits for sewer extension to service existing development. | Short | 2012-10-01
CMC1 | Complete Middle Township's chapter of the Wastewater Management Plan | Cape May County | Very Short | 2011-12-15
DEP2 | The USGS recently published its study, Future Water-Supply Scenarios, Cape May County, New Jersey, 2003-2050. Middle Township shall work with NJDEP and the County to determine the appropriate water supply strategy, and implement recommended water conservation measures. | Township and Cape May County; DEP | Short | 2012-10-01
DEP3 | Middle Township shall work with New Jersey American Water Company to support increased development density in centers and to improve fire suppression capabilities. Work with utility to plan and improve waterline network. | Township | Short | 2012-10-01
CONSERVATION
DEP4 | Open Space and Recreation Plan: Prepare Recreation and Open Space Inventory (ROSI) as an updated Master Plan element. Use Plan to prioritize open space and farmland preservation acquisition efforts. Coordinate efforts with County Farmland Preservation plan and County Open Space and Recreation Plan and other planning efforts including Priority Aquifer Recharge sites. Prioritize acquisition of open space in coordination with State and Federal agencies and not-for-profit groups. Prepare ROSI and submit to NJDEP to enable funding. | Middle Township | Short | 2012-10-01
DEP5 | Outline a strategy that allows developers in the center to share centralized stormwater collection basins that serve as pleasant water features for citizens to enjoy. These larger, shared water features will maximize efficiency by preventing unsightly retention basins in each development. | NJDEP technical assistance. | Short | 2012-10-01
HOUSING
DCA 1 | Continue to provide for the rehabilitation of affordable housing units through State and Federal grants | Township Committee will seek funding for rehabilitation grants for this area to support low/moderate income families. | Medium | 2014-10-01
DCA2 | Continue to foster innovative policies that enhance the diversity of housing products available in Middle Township, ensuring that Middle Township remains an attractive place for all people in all stages of life. | Middle Township | Medium | 2014-10-01