MEMORANDUM

To: 		Plan Implementation Committee of the State Planning Commission

From: 		Benjamin Spinelli, Executive Director

Date: 		October 10, 2007

Re: 		City of Asbury Park Plan Endorsement PIA Monitoring Report

On May 18, 2005, the State Planning Commission (SPC) approved the Plan Endorsement petition submitted by the City of Asbury Park of Monmouth County.  As required by N.J.A.C 5:85-7.12(b), the City recently submitted its biennial report (enclosed) detailing the status of its Planning and Implementation Agreement (PIA) efforts. Office of Smart Growth (OSG) staff has reviewed the submission and found that Asbury Park has made good progress on its PIA items.  Items due at or prior to this juncture are either fully implemented or expected to be complete by the end of the year.  The City also continues to move forward with both ongoing items and those with longer timeframes.

At the same time, it is worth mentioning that OSG is concerned about two issues pertinent to development in Asbury Park.  First, with the extensive redevelopment plans throughout the city, including the large-scale redevelopment of the city’s waterfront area, it remains unclear if Asbury Park will have enough wastewater capacity to treat increased flows, particularly during times of peak usage.  Given this, OSG intends to investigate the matter over the next few months to determine whether it requires action on the part of the City and relevant state agencies.

Second, OSG and the Department of Environmental Protection (DEP) are currently looking into potential environmental justice concerns in Asbury Park.  Item A7 of the City’s PIA requires it to “implement a variety of techniques to mitigate areas of the city that have demonstrated environmental justice issues.”  After the state agencies have a better understanding of the nature of the situation and its ramifications, OSG and DEP may work with the City to develop a course of action. The City has also requested a meeting with DEP through OSG in order to facilitate any additional action items, if required.

OSG is asking the Plan Implementation Committee to recommend and move to the SPC the noted timeline modifications for late items in the PIA, as well as those that have a specific deadline but are more suitable for ongoing implementation.  We believe these modifications are appropriate given that Asbury Park has made a good faith effort to implement its PIA and has generally met the requirements and deadlines.