| TOWNSHIP OF LAKEWOOD PLAN ENDORSEMENT PETITION PLANNING AND IMPLEMENTATION AGREEMENT (PIA) December 5, 2005 CONTENTS - General - Land Use / Zoning - Housing - Open Space / Recreation - Environs / Environmental - Transportation and Circulation - Infrastructure - Economic Development - Creating a Sense of Place /tmp/in/input.doc |  |  |  |  |
| --- | --- | --- | --- | --- |
| # | ACTIVITY | LOCAL EFFORT | STATE/COUNTY ASSISTANCE | TIME TABLE |
| ##### 1. General |  |  |  |  |
| #### 1.1 | #### CAFRA Center Boundary |  | DEP will provide notice of approved center boundaries to the New Jersey Register upon approval of SPC and Plan Endorsement petition. | 90 days |
| #### 1.2 | #### Plan Endorsement review | By a date agreed upon between the SPC and the Township and biannually thereafter and within 6 months after adoption of any new or significant change to the reexamination report, land use ordinance or other planning documents submitted as part of the Initial Plan Endorsement petition, the Township of Lakewood shall submit a report to OSG and the public concerning the status of the Township’s Planning Implementation Agreement efforts pursuant to N.J.A.C. 5:85-7.12(c) |  | Ongoing |
| 1.3 | Inter-governmental coordination | Coordinate with planning efforts of adjoining municipalities, the County and State and regional planning efforts particularly concerning: regional planning, transportation, economic development, tourism, natural resource protection and open space and recreation. | County Planning Board, OSG, DOT, DEP | Ongoing |
| 2. Land Use & Zoning |  |  |  |  |
| 2.1 | Master Plan | Review and update Master Plan goals and objectives as directed by the MLUL. |  | 6 months |
| 2.2 | General Zoning | The Township will revise any zoning and redevelopment plans for areas outside the Center and Suburban Planning Area to prohibit uses and development that would adversely affect the environmentally sensitive features in those areas. | DEP and OSG | 6 months |
| 2.3 | Zoning Map and Ordinances | Revise the official zoning map and ordinances based on the Future Land Use Plan. | OSG | 6 months |
| 2.4 | Impact Fees | Implement provisions of the Unified Development Ordinance to promote Township affordable housing goals and the use of impact fees for authorized development by the Township Committee. |  | 6 months |
| 2.5 | Open Space | Continually prioritize high value open space lands for acquisition. | County and DEP | 1 year |
| 2.6 | Community Facilities | Continue to review the needs of community facilities to determine the need for replacement or additions including, but not limited to: schools, fire substations, police station, highway department and recreational facilities. | OSG and DEP | 2-3 years |
| 2.7 | Educational Programs | Encourage educational programs for conservation of lands, historic resources, community facilities and local businesses. | County | 2-5 years |
| 2.8 | Plan Review | Establish a continuing program for re-evaluating the policies established by the Land Use Plan Element |  | Ongoing |
| 3. Housing |  |  |  |  |
| ##### 3.1 | ##### Affordable Housing | Prepare a Housing Plan and Fair Share Plan to determine the Township’s fair share obligations with assistance provided by the Township Committee and the Lakewood Housing Authority. | COAH, DEP will analyze proposed sites | ##### 1 year |
| 3.2 | Substantive Certification | File a petition with COAH for substantive certification. | COAH | 1 year after SPC approval |
| 3.3 | Rehabilitation | Partner with Ocean County and utilize the tax abatement process to rehabilitate the aging housing stock. | Ocean County | 2-3 years |
| 3.4 | Housing Mixture | Identify opportunities to create diverse housing mixture and affordable housing in the center. | COAH and OSG | Ongoing |
| 3.5 | Regional Contribution Agreements | The Township is currently exploring the RCA program and has hired an affordable housing consultant to identify appropriate RCA sites within the Township. | COAH | Ongoing |
| 4. Open Space/Recreation |  |  |  |  |
| 4.1 | Open Space Plan | Implement the Open Space Plan that identifies parcels for potential acquisition. | Ocean County and DEP-Green Acres | 1 year |
| 4.2 | Pedestrian Linkages | Design, obtain funding and construct the trail network and pedestrian linkages with assistance provided by Environmental Commission. | DOT, County | 1-2 years |
| 4.3 | Open Space Linkages | Create linkages between open space and recreation sites. | DEP | 2 years |
| 5. Environs/Environmental |  |  |  |  |
| 5.1 | Natural Resource Inventory | Prepare a Natural Resource Inventory with assistance provided by the Environmental Commission. | DEP | Prior to SPC approval |
| 5.2 | Stream Corridor Protection Plan | Create and implement a Stream Corridor Protection Plan to protect waterways located within the Township. | DEP | 2-5 years |
| 5.3 | Critical Area Protection | Preserve and protect environmentally sensitive lands. The Township will pursue Federal, State, County and private funds to acquire environmentally sensitive lands designated as PA5 or CES in the approved plan or designated as Forest Area in the Pinelands Area, particularly within the Oyster Creek watershed. | DEP | Ongoing |
| 5.4 | Environmental Justice | Implement a variety of techniques to mitigate areas identified as areas of concern in the Environmental Justice Inventory. | DEP | 2 years |
| 6. Transportation and Circulation |  |  |  |  |
| 6.1 | Access Management | Partner with NJ DOT to create an Access Management Plan along the Route 9 Corridor. The Township will incorporate any necessary changes to the Township’s Zoning Ordinance so that it is in conformance with the Highway Access Code for lands adjacent to Route 9. The Township also condition approvals of subdivision and site plans on consistency with the requirements of the Highway Access Code. The Township will also undertake a capacity analysis that addresses traffic generation under build-out scenarios for current zoning and proposed redevelopment. | DOT in conjunction in Route 9 study | 2-5 years |
| 6.2 | Goods movement | As part of Circulation Plan update, incorporate a strategy for dealing with retail, commercial or truck freight traffic along state, county and municipal roadways as it relates to existing and future land use patterns. | DOT in conjunction with Route 9 Study | 1.5 years |
| 6.3 | Transportation Demand Management (TDM) | As part of Circulation Plan update, incorporate a strategy to utilize transportation demand management (TDM) measures for trip reduction where applicable, such as ridesharing, vanpooling, transit and park-and-rides | DOT in conjunction with Route 9 Study | 1.5 years |
| 6.4 | Airport Activities | Prepare a discussion in the Land Use Element of the Master Plan that describes appropriate land uses adjacent to the airport. Market the airport for greater economic development in the Township. | DOT | 1 year |
| 6.5 | Passenger Rail Improvements | Remain actively engaged in the MOM Rail line activities and promote the creation of rail station as identified in the preferred alternative scenario in the Final Environmental Impact Statement. | NJ Transit | 2-5 years |
| 7. Infrastructure |  |  |  |  |
| 7.1 | Stormwater Management Plan | The Township will adopt a stormwater management ordinance and implement its stormwater management program in accordance with NJDEP regulations. | DEP and Ocean County | 1 year |
| 7.2 | Wellhead Protection Plan | Create and implement a Wellhead Protection Plan to protect water supply wells. | DEP | 2 years |
| 8. Economic Development |  |  |  |  |
| 8.1 | Urban Enterprise Zone | Continue to actively promote the UEZ programs (employment, financial, public safety). |  | Ongoing |
| 8.2 | Business Retention/ Expansion | Manage the business development and retention program in the Foreign Trade Zone, Industrial Park and Cedar Bridge Corporate Campus. | EDA | Ongoing |
| 8.3 | Revolving Loan Fund | Ensure that the evolving loan fund is promoting small business development with assistance provided by the Chamber of Commerce. | EDA | Ongoing |
| 8.4 | Tourism | Maximize the net capture of visitors to State, County and local open space areas. | DEP | Ongoing |
| 8.5 | Financial Assistance | Apply for public and private community development grants | EDA, OSG, NPP, HUD, CDBG and DOT | Ongoing |
| 8.6 | Entertainment/ retail/restaurant | Identify further retail opportunities adjacent to the BlueClaw stadium. | OSG, County | Ongoing |
| 8.7 | Farmers Market | Promote the creation of a Farmers Market to promote the Jersey Fresh brand in the Regional Center. | DOA | 1 year |
| 9. Creating a Sense of Place |  |  |  |  |
| 9.1 | Strengthen Regional Center Identity | Build upon Lakewood’s economic and cultural identity to establish a destination for Ocean County and Monmouth Counties. | DOT, DEP and OSG | Ongoing |
| 9.2 | Streetscape Design | Develop a streetscape design, which includes signage to identify the Center. | DOT, Ocean County and OSG | 2 years |
| 9.3 | Destination Guide | Publish an easy to use destination guide that lists events and places of interest to market the Regional Center | Ocean County | 2 years, ongoing |
| 9.4 | Educational Programs | Encourage educational programs for conservation of lands, historic resources, community facilities and local businesses. | SHPO | Ongoing |
| 9.5 | Transit Station | Examine land uses around the proposed rail station and propose transit-orientated development. | NJ Transit—Transit Village Initiative, OSG | 2-5 years |