## Sheet1
LAKEWOOD ACTION PLAN
Italics = DEP CAFRA Requirements |  |  |  | 2006-05-23
Item No. | Subject | Action Item | Deliverable | Timetable (Days) | Deadline*
A1 | State Plan Policy Map | The Township shall work with state agencies to revise boundaries for the Center(s) to be consistent with the State Plan goals, policies, and delineation criteria. The Township will need to clarify what types of development is proposed for these centers. | Center boundaries | 90 | 2006-08-23 01:41
A2 | State Plan Policy Map | The Township shall work with state agencies to revise boundaries for Planning Areas to account for existing environmental resources. | Planning area and CES boundaries | 90 | 2006-08-23 01:41
B1 | Master Plan Update | The Township shall update its Master Plan as necessary, in particular the Land Use Plan Element, based on the discussion of other action items in this table. | Master Plan update adopted. | 165 | 2006-11-07 19:05
B2 | Redevelopment | The Township shall supply updates on the status of redevelopment areas, and work with state agencies to ensure that redevelopment provide for Center-like developmentand does not impact existing environmnental resources. | Narrative statement to provide input for the SPPM boundaries, center concepts and Land Use plan. | 90 | 2006-08-23 01:41
C1 | Open Space & Recreation | The Township shall prepare a statement identifying opportunities for open space and recreation facilities, especially in conjunction with center proposals. | Narrative statement and map(s). | 120 | 2006-09-22 18:14
C2 | Center Concepts | The Township shall prepare concepts, both in text and graphics if possible, to provide detail about the future development/redevelopment of the proposed Center(s). These concepts should be linked to transportation, including transit and parking. | Narrative statement (and graphics if feasible). | 120 | 2006-09-22 18:14
C3 | Road Network | The Township shall work with NJDOT in the Route 9 corridor study to identify and conceptually plan for a network of roadways. | Narrative statement and map(s). | 120 | 2006-09-22 18:14
D1 | Draft Housing Element and Fair Share Plan | The Township shall work with DEP to ensure that all sites identified for affordable housing will be workable in relation to environmental constraints. | Narrative statement and map of affordable housing sites and environmental resources. | 90 | 2006-08-23 01:41
D2 | Draft Housing Element and Fair Share Plan | The Township shall ensure that its Plan Endorsement petition and COAH petition are generally consistent with each other in terms of where development will be focused and how much growth will be accomodated. The COAH petition will incorporate relevant agreements and information arising from Plan Endorsement negotiations taking place through this Action Plan. | Revised housing element | 150 | 2006-10-23 10:48
E1 | Emergency Planning | The Township shall provide evidence that it has an Emergency Operating Plan approved by the NJ State Police. | Copy of approval from NJ State Police. | 30 | 2006-06-22 16:34
F1 | Threatened & Endangered Species Habitat | The Township shall work with DEP on protecting habitat of threatened and endangered species. This information will be part of discussion in making any adjustments to center boundaries and planning areas. | Proposed habitat protection strategy and draft ordinance. | 90 | 2006-08-23 01:41
G1 | Petition Report Update | Elements of the petition report will be accurately updated based on the fulfillment of this action plan. These elements may include but are not limited to: consistency with State Plan goals and policies, PIA, population projections, center delineation criteria, references to new documents. | Petition report. | 180 | 2006-11-23 03:22
G2 | Petition Report Update | Due to the extent of change involved to make the petition consistent with the State Plan, the Township shall provide detail of public participation for the various action items, and in the end pass a resolution supporting the revised petition. | Petition report. | 180 | 2006-11-23 03:22
G3 | Petition Report Update | The Township shall improve the Statement of Planning Coordination section to discuss how future center-based development, infrastructure & capacity, and environmental protection will be coordinated with adjacent municipalities. This section shall also address cross-border issues such as development impacts and potential for shared services. | Petition report. | 180 | 2006-11-23 03:22
H1 | Coastal Consistency Statement | The Township shall prepare a statement that addresses natural resource protection and coastal management demonstrating consistency of local plans and ordinances with the goals of the Coastal Zone Management Program. | Coastal Consistency Statement. |  | To be determined
H2 | Ocean County Wastewater Management Plan | The Township shall work with Ocean County to prepare an updated Wastewater Management Plan that address the wastewater and water quality management needs of the Township under the endorsed plan. The updated Wastewater Management Plan must be noticed for approval by DEP prior to CAFRA center designation. | Updated Water Quality Management Plan through municipal amendment. |  | To be determined
H3 | Land Use / Zoning Regulations | The zoning ordinance revisions and/or new ordinances must implement the policies and recommendations of the master plan, and accurately reflect center boundaries and/or planning area changes (if applicable), and ordinances that implement appropriate environs protection measures, including zoning, resource protection, and site plan and subdivision ordinance revisions. | Zoning amendments implementing the land use plan element to support development of centers and TOD cores as well as protection of rural and environmentally sensitive areas. |  | To be determined
H4 | Water Supply Information | The Township must provide documentation that water supply capacity exists for the amount of growth detailed in the Master Plan, including existing and proposed water supply sources. The Township should identify the available approved allocations and firm capacity. In addition, the Township must identify local water conservation measures. | Documentation of adequate water supply from utilities authority and/or private purveyor(s). |  | To be determined
*NOTE: The above deadlines are subject to negotiation.
Formulas:
Deadline* = [Timetable (Days)]*1.023+E2