## From original
Item No. | Activity | Responsible Party | Deadline | Old Date (reset during last Biennial where applicable) | New Date | Middle Township Status Notes | MSA says
TRANSIT AND TRANSPORTATION
NJDOT1 | Construct key paper streets Improvements listed in the Transportation Improvement Study | Middle Township | Long | 2017-10-01 | 2017-10-01 | Under Evaluation | Under Evaluation | what does that mean?
NJDOT2 | Develop western alternative roadway to Route 9 | Middle Township, coordinating with landowners | Long | 2017-10-01 | 2017-10-01 | Under Evaluation | dot | does middle want it?
NJDOT4 | Develop new roadway of Shunpike Road extension | Cape May County or Middle Township | Long | 2017-10-01 | 2017-10-01 | The Cape May County Engineer reports that the County will participate in Township-led efforts. Under evaluation by Township | county | does middle want it?
NJDOT15 | Adopt access management ordinance | Middle Township | Short | 2012-10-01 | 2012-10-01 | In Progress | not complete | was short term, why not done?
NJDOT16 | Adopt shared parking ordinance | Middle Township | Short | 2012-10-01 | 2012-10-01 | Proposed Ordinance Drafted (Exhibit Y) | not complete | was short term, why not done?
NJDOT17 | Adopt street connectivity ordinance | Middle Township | Short | 2012-10-01 | 2012-10-01 | In Progress | not complete | was short term, why not done?
DJDOT 19 | Pursue installation of sidewalks on priority roadways | NJDOT, CM County, Middle Twp | [5 empty] | would including this help grant applications?
NJDOT20 | Investigate signal optimization along Route 9 on summer weekends | Middle Township, in coordination with NJDOT | Short | 2012-10-01 | 2017-10-01 | In Progress | check status/ dot juristiction? | does middle want it?
NJDOT21 | Modify the Transportation Improvement Analysis by adding the MLUL requirements for a circulation element. Adopt the circulation element. | Middle Township | Short | 2012-10-01 | 2017-10-01 | In Progress | not complete | was short term, why not done?
INFRASTRUCTURE
CMC2 | Prior to CAFRA center designation, the County, NJDEP and the Township shall identify existing and proposed water supply sources and strategies that document how water supply capacity will exist for the amount of growth detailed in the Endorsed Master Plan. The USGS recently published its study, Future Water-Supply Scenarios, Cape May County, New Jersey, 2003-2050. The County should refer to this study and 7:15-5.25(f) for guidance on the necessary submittals. | Township and Cape May County; DEP technical assistance | Very Short | 2011-12-15 | Ongoing | Reports that the Water Supply Plan is the responsibility of NJDEP and that they have been waiting for additional information, including cost estimates since 2010. The Township requests that the PIA be amended to reflect this responsibility. | dep | Please provide more detail on this status including correspondences if necessary so that OPA can assist in receiving answers.
HOUSING
DCA 1 | Continue to provide for the rehabilitation of affordable housing units through State and Federal grants | Township Committee will seek funding for rehabilitation grants for this area to support low/moderate income families. | Medium | 2014-10-01 | Ongoing | $200,000 CDBG Home Rehabilitation Grant secured for 2013 - 2014 funding round. (Exhibit V). Status: Ongoing (via annual Township funding request.) | requests $annually for rehab | would including this help gtant applications?

## 2023 PIA Actions
PIA Wildwood Crest DRAFT 6-13-23
# | Topic | Req (*) | Activity | Local Effort | Assistance | Time Frame | Comments
A1 | Administrative | * | One year from endorsement and biennially thereafter, report to the SPC about the status of planning efforts, ordinance adoption and other accomplishments from the PIA. | Planning Board and governing body | OPA | 1st Due July 5, 2024 (?); then July 5, 2025, 2027, 2029, 2031, 2033 | First year = Annual Report then Biennial Reports for the next 8 years. (Include status on PIA actions, any land use ordinances and site plan applications/approvals).
A2 | Administrative | * | After adoption, Wilwood Crest shall submit to OPA any new or modified land use ordinance and/or planning document. | Planning Board and governing body | Technical assistance | Include in Biennial Report. | Include in reports planning, land use or relevant items beyond the PIA actions.
B1 | Public Info & Community Engagement |  | Continue to support the Green Team and enlist them to work on the PIA actions as appropriate. |  | Governing body, Green Team | ongoing | Wildwood Crest was just Certified Bronze in 2022 and could hit Silver and maybe a Gold Star with this PIA.
B2 | Public Info & Community Engagement |  | Many of the following actions would benefit from public engagement, education about issues, resident assistance with actions, participation in decision making and support for a path to resiliency and sustainability. An early action should be a public forum(s) designed for short and long-term public engagement. | Governing body, Planning Board, Green Team, chamber(s), churches, schools, other local and regional organizations as partners/invitees. | OPA, DEP, local groups & regional NGOs/universities | Periodically thereafter to update/engage residents on progress on key issues. | Forum(s) should be designed with a well developed outreach element to ensure equitable inclusion and meaningful turn out and facilitated to maximize results.
C1 | Climate Resilience Planning | * | Develop, adopt, and implement a climate change-related hazard vulnerability assessment (CCRHVA) that meets the requirements of the MLUL per P.L.2021, c.6. | Planning Board, OEM, Green Team | DEP/SJ, NJ Adapt, OPA , DEP | Within 4 years | Gather the draft CCRHVA prepared by Rutgers, the HMP Annex and other maps/documents, and refine the vulnerability data for MLUL compliance. Must address climate impacts for temperature, precipitation, flooding, heat island, wildfire protection including vulnerability of public and private potable wells, utility sites, facilities, equipment, conveyance piping, overhead utility lines, etc. that may be vulnerable to climate impacts or other environmental hazards. Findings from the CCRHVA should guide strategies to increase resilience and reduce risk.
C2 | Climate Resilience Planning | * | Review/update the Flood Damage Protection Ordinance with the current NJ Coastal Model Ordinance (revised 2022) at https://www.nj.gov/dep/floodcontrol/modelord.htmin order to be NFIP compliant. | Planning Board and governing Body | DEP | 1-2 years contingent on DEP | WWC's Flood Loss ordinance is from 2015 and needs revision. NJDEP updated the model ordinance in 2022 to be compliant with NFIP.
C3 | Climate Resilience Planning |  | Review the Blue Acres Program and see if it might be an option for any Non-mitigated repetitive loss properties in the community. | Governing body | DEP, OEM, FEMA |  | WWC has 203 Repetititve loss properties and 75 Severe Repetitive Loss properties. 51 properties have been mitigated.(1,965 NFIP policies with $31,243 in losses during participation). Per 2021 HMP Annex. WWC is a member of the NJ Coastal Coalition, is CRS Level 6 and a member of the Multi-Juristictional Public Participation and Information group (MJPPI)
C4 | Climate Resilience Planning |  | Continue participating in the CRS program and potentially address Repetitive Loss (RL) and Severe Repetitive Loss (SRL) properties and other vulnerabilities. | Governing body | DEP, OEM, FEMA, NJCC
D1 | Land Use | * | Review plans and ordinances and remove impediments to, and encourage, green design throughout the community. Make necessary modifications to ensure that innovative and sustainable construction alternatives and materials (such as green roofs) are permitted. May also consider approving incentives for using innovative roofing alternatives and materials. | Planning Board, governing body & Green Team | OPA, NJDEP technical assistance | 1-3 years | Sustainable Jersey points and support. WWC has an active Green Team that could help with this and many other actions.) (See Downe Twp's green design ordinance.)
D2 | Land Use | * | Review and update Master Plan and all associated elements to consider climate resiliency and socially vulnerable populations. | Planning Board, governing body & Green Team | DEP, Sustainable NJ | 1-3 years after CCRHVA | Sustainable Jersey points and support. Address MLUL requirements.
D3 | Land Use | * | New construction or redevelopment of existing buildings should avoid high density concentration in areas of severe flooding. Placement of critical facilities and utilities in flood zones should be avoided whenever possible. Affordable housing should be sited to avoid flood zone and hazardous areas. | Planning Board | DEP (Bureau of Climate Resilience Planning) | 1-3 years After CCRHVA | Flood damage prevention ordinance was last revised in 2015 and needs revision (see C3). NJDEP Updated the model ordinance in 2022 to be compliant with NFIP.
D4 | Land Use |  | Consider adopting an Accessory Dwelling Unit (ADU) Ordinance in residential zones. | Planning Board
D5 | Land Use |  | Consider developing an Open Space & Recreation Plan (OSRP) including climate change considerations. | Work with County, neighboring communities, DEP, NGOs and OPA for planning/support. | County and Green Acres Funding as applicable. | 1-2 years for plan 1-3 years after plan for first projects implementaion. | Incorporate climate change considerations as needed into plan. Petitioner should work closely with Green Acres, local advisory committee, County, and property owners . Be sure to maintain consistency wtih the county OSRP.
D7 | Land Use | * | Implement affordable housing/ spending plan based on Settlement Agreement. | Governing body, planning board | DCA, Fair Shair | 1-3 years
D8 | Land Use |  | Develop a Vacant Land Inventory and identify any unoccupied structures that would lend themselves to affordable housing. | Planning Board, governing body & Green Team
D9 | Land Use | * | Periodically reconcile and update Area in Need of Redevelopment and Area in Need of Rehabilitation Data | Planning Board | DCA, OPA | Update ongoing | Ensure that data is maintained and accurate
D10 | Land Use | * | Pursue feasibility and potential construction of public restroom facility on Crest Pier where the Fishing Club once operated. Submit an application for SSA and work in good faith with DEP and relevant partners to provide public restrooms and and other beach/fishing ammenities. | Governing Body | DEP, OPA, NOAA, ACE
E1 | Energy | * | Public EV charging infrastructure feasibility and supporting ordinances | Governing body & Green Team | DCA, BPU, DEP, SJ possible $$ | 1-2 years | It looks like WWC still needs to adopt the required EV ordinance. Sustainable Jersey points and support.
E2 | Energy |  | Make your town EV Friendly (choose 3) *update zoning ordinances to require pre-wiring for EV chargers for a redevelopment plan or for a specific zone(1-2 yrs); *Adopt a PEV ordinance to include regulation/design standards for EVSE, EV parking spaces and design guidelines for installation of EVSE (1-2 yrs); * Training for local officials and require local first responders to participate in PE and EVSE education (1-2 yrs); *Incentivize EV ready - by reduce or waive permit fees and recognize businesses/entities that do it (2-3 yrs); *Commitment from 3 or more places for workplace or multi-family chargers (2-5 yrs). | Governing body & Green Team | BPU, DEP, SJ possible $$ | 1-2 years | Must meet the PE required 3 items in this action. Sustainable Jersey points and support.
E3 | Energy | * | Develop a community GHG Reduction Action Plan, including GHG reduction targets. GHG reduction actions should be incorporated into land use element of master plan. 1) Conduct Local Government Energy Audit (LGEA) of municipal facilities and operations, at a minimum, and community-wide audits, if feasible, and 2) using the results of these audits, develop action plans for reducing municipal energy consumption and GHG emissions - use NJ’s 2020 GHG emissions reduction target as a goal | Planning Board, governing body & Green Team | Bd of Public Utilities (BPU) Clean Energy Program | 3 years with phasing | The regional MPO prepared a greenhouse gas (GHG) inventory. This inventory provides county and municipal-level GHG emissions information for various major community sectors/activities (e.g., residential, transportation, waste generation). WWC can acquire its local inventory data and use it as a baseline Sustainable Jersey points and support BPU provides funding for municipal energy audits: (http://www.njcleanenergy.com/commercial-industrial/programs/local-government-energy-audit/local-government-energy-audit
E4 | Energy | * | Energy Tracking & Management - establish energy use baselines, tracking, mgt & reporting systems | Planning Board, governing body & Green Team |  | 2-3 years | https://www.sustainablejersey.com/actions/#open/action/482
E5 | Energy | * | Greening the municipal fleet: • Fleet Inventory and target for green fleet conversion. | Governing body & Green Team | BPU, DEP, SJ possible $$ | w/in 3 years | Sustainable Jersey points and support
E6 | Energy | * | Renewable Energy Generation: *Onsite Solar or *Geothermal system or *buy electric from a renewable source or *community solar project or *Renewable Energy Aggregation | Governing body & Green Team | BPU, DEP, SJ possible $$ | 1-3 within 6 years | Sustainable Jersey points and support
E7 | Energy | * | Implement energy efficiency Measure for facilities | Planning Board, governing body & Green Team |  | 1-4 yrs | Sustainable Jersey points and support
E8 | Energy |  | Greening the municipal fleet: * Trip optimization software * Proper vehicle maintenance * Driver training *purchase electric vehicles to achieve 20% reduction in fuel use w/in 4 years . | Governing body & Green Team | BPU, DEP, SJ possible $$ | recommended | Sustainable Jersey points and support
F1 | Conservation |  | NJUFCP accreditation, a Tree Protection Ordinance and/or Tree Risk Assessment Plan. | Planning Board, governing body & Green Team | DEP;Sustainable Jersey | 2-3 years | Consider developing
F3 | Conservation | * | Adopt a Water Conservation Ordinance that is mutually agreeable to the municipality and DEP | Governing body & Green Team | DEP, OPA, SJ | 2-3 years | Sample ordinance provided.
F4 | Conservation | * | Review existing plans and enhance Conservation/Habitat Conservation element and or a section in the OSRP Plan (see Action #D5, above) addressing conservation and habitat protection measures. Coordinate with county and surrounding municipalities to expand corridors of open space and natural features to support habitat connectivity. | Governing body & Open Space Preservation Committee, Planning Board, Green Team | DEP technical assistance and funding | Possibly in conjunction with OSRP and ERI. Complete in 1-4 years | NJDEP Connecting Habitats Across NJ (CHANJ) mapping can be of assistance to identify potential corridors https://www.njfishandwildlife.com/ensp/chanj.htm Be sure to incorporate climate change considerations and identify the CESs in relevant maps.
F5 | Conservation | * | Update the Environmental Resource Inventory ERI, especially climate change observations and concerns. DEP can assist with identifying what to include. | Planning board, Governing body & Green Team | DEP, ANJEC, SJ, Geoweb, NJ Adapt | 3-5 years After CCRHVA | ERI shouldinclude climate impact considerations, findings from the CCRHVA, and CES overlays as appropriate.
F6 | Conservation | * | Review and update as necessary the inventory of contaminated sites in WWC and identify if any of these Known Contaminated Sites (KCS) within the proposed center also meet the DEP definition of a brownfield site. | Planning Board, governing body & Green Team | Data miner | 1-4 years After CCRHVA | Review and update with climate impact considerations, findings from the CCRHVA, and CES overlays as appropriate. WWC should follow the mapping and inventory provided by the NJDEP.
F7 | Conservation | * | Adopt a Stream Corridor/Riparian Zone Ordinance | Governing Body |  | 1-2 years | Sample provided
GI | Transportation & Circulation | * | Adopt a Complete & Green Streets Policy and Implementation Plan into the Circulation Element of the Master Plan. | Planning Board, governing body & Green Team | NJDOT, SJ | 2-4 years | Model ordinances to be provided. Minor edits are acceptable.
G2 | Transportation & Circulation | * | Update the Circulation Element of Master Plan to address opportunities for shared parking, goods movement, and improvements to transit and circulation with continued growth in the community. Encourage non-vehicular transportation. | Planning Board | NJDOT, SJTPO | 4 years | Wildwood Crest agrees to work on the Circulation Element.
G3 | Transportation & Circulation |  | Coordinated assistance in preparation and implementation of bike/ped studies to update the vehicular and pedestrian circulation. | Planning Board | NJDOT, SJTPO, Cape May Co Planning, Voorhees Trans Ctr
G4 | Transportation & Circulation |  | WWC seeks assistance/parnership in Sunset Lake dredging and relocating the state channel to enhance recreational access | Governing Body | NJDOT |  | Location sought for beneficial sediment use; potentially coiuld be funded with Sandy resources
H1 | Transit |  | Improve transit options |  | NJT
I1 | Infrastructure | * | Review and update as necessary Utilities Element of the Master Plan and the 2019 Flood Mitigation and Storm Sewer Master Plan as needed. | Planning Board, water purveyor, county MUA, private water ompanies | DEP | 2-4 years after CCRHVA (With Reexam) | New utility lines and associated infrastructure should be planned to avoid flood prone areas and existing utility infrastructure currently in or projected to be flood prone in the future should be addressed.
I2 | Infrastructure | * | County should be currrent with its WMP with a local chapter and a new FWSA map pursuant to 7:15-4.2 (c) | County | NJDEP |  | WMP submitted in 2019.
I3 | Infrastructure | * | Evaluate and update regularly the Stormwater Management Plan and Ordinance for consistency with the current Stormwater Management Rules. Be sure to submit MS-4 Permit reports each May. Be aware of local TMDLs. |  | DEP and other agency technical & financial support for SW projects |  | SPPP should be up to date and submit MS4 reports each May. WWC updated its stormwater ordinance in 2021.
J1 | Sustainability |  | Develop green building and sustainable design guidelines for new development - consider requiring “green buildings” (LEED, Green Globes) in redevelopment areas, to the extent practicable. | Planning Board, governing body & Green Team | SJ |  | Sustainable Jersey points and support
J2 | Sustainability | * | Modify zoning code and permit forms/process to streamline to encourage solar, wind and geothermal. | Planning Board, governing body & Green Team | DEP, BPU, SJ | 1-3 years | Sustainable Jersey points and support. Address MLUL requirements.
J3 | Sustainability |  | MLUL encourages municipalities to include a Green Building & Sustainability Element in their master plan to help establish policies and initiatives for achieving sustainability goals. Components include:• Define what sustainability and resilience mean to your community • Statutory basis for a sustainability element and how it relates to other elements of the plan • Document public engagement activities • Summarize existing conditions and trends, including any environmental justice (EJ) concerns and any available baseline assessment like greenhouse gas • Document community’s existing sustainability policies and programs and accomplishments inventories, energy use assessments, or public health inventories • Establish a vision for local sustainability and resilience, expressed in a succinct statement • Establish sustainability and resilience goals and objectives • Develop strategies and actions for achieving sustainability objectives, typically organized by topic area, such as land use, transportation, energy, water, waste, etc. • Establish performance measures and metrics for tracking progress toward objectives • Assign responsible parties for implementation actions • This could be expanded to be a Climate Action Plan if so desired. |  | Green Team - DEP, Sustainable Jersey, OPA | Report on progress in biennial review | Sustainable Jersey points.
J4 | Sustainability | * | Review recycling code to ensure consistency. |  |  |  | Stone Harbor has an extensive recycling code, environmentally acceptable packaging and products ordinance and Green Team support for residents.
K1 | Economic Development |  | Promote economic sustainability through coordinated planning with business and property owners and neighboring communities. Develop plans for center-based/walkability improvements and support economic development initiatives including historic preservation, façade and rehabilitation grant program, wayfinding signs, coordinated marketing efforts, etc. |  | County, Chambers, NGOs, NJ Tourism, USDA, and others | Ongoing | Coordinate marketing efforts with neighboring communities. Engage NGO and business interestes in discussions, event coordination and marketing campaigns.
K2 | Economic Development |  | Consider coordinating with Wildwood and West Wildwood to ensure a maximized benefit as a multi-municipality Urban Enterprise Zone; review feasibility of establishing a Main Street program; and, consider a slight boundary modification with your UEZ fice-year plan to include Block 36, Lots 44, 45 and 46 if appropriate. |  | DCA |  | DCA/OPA to provide additional support as needed to review these opportunities.
L1 | Historic Resources |  | Consider developing an Historic Preservation element. Historic structures should be protected with enhanced stormwater management plans and flood minimization plans. | Governing body | SHPO, County, Historical Societies | Report on progress in biennial review | Review the NJ Historical Commission’s grants: https://nj.gov/state/historical/his-grants.shtml and Historic Trust https://www.nj.gov/dca/njht/ Work with SHPO to develop planning documents, guidance: https://www.nj.gov/dep/hpo/images/_MULT_DG_32_v2_ID14078r.pdf
L2 | Historic Resources |  | Prepare a Historic Preservation Plan, updating historic resources inventory, then prepare and adopt a historic preservation ordinance defining the roles and responsibilities of a potential Historic Preservation committee. | Governing Body, Planning board, Green Team | SHPO, County | Report on progress in biennial review
M1 | Planning | * | Update the Community Facilities Plan | Planning Board | Technical assistance | 3 years
M2 | Planning | * | 5 yr capital improvement plan per MLUL |  |  |  | WWC's 2020 plan is a three year plan.
N1 | Environmental Justice | * | Develop a Municipal EJ Action Plan. Follow the requirements of EO23 pursuant to NJDEP guidelines to review, identify, and update documents as necessary. |  | NJDEP | 1-3 years after provision of guidance | Monitor for changes in municipality that may warrant more environmental justice actions in the future. NJDEP EJ Guidance at https://dep.nj.gov/ej/