STATEWIDE TRANSPORTATION AND LOCAL BRIDGE BOND ACT OF  1999

STATUS REPORT

# May 2007

New Jersey Department of Transportation

Status Report

May 2007

Statewide Transportation and Local Bridge Bond Act of 1999

As directed by Section 26 of the Statewide Transportation and Local Bridge Bond Act of 1999 (P.L. 1999, c. 181), the Department of Transportation makes the following report on the status of funds provided by the act and the status of projects financed with those funds.

The bond act created a special fund to provide $250 million to the Department and NJ TRANSIT for statewide transportation projects and $250 million to be distributed to the counties for local bridge projects.  These funds were made available under three bond appropriations acts (P.L. 2000, c. 11, April 6, 2000; P.L. 2000, c. 155, November 13, 2000; P.L. 2001, c. 239, September 4, 2001).

Of the $250 million appropriated for statewide transportation projects, $240,822,320 (96%) has been expended.

Of the $250 million appropriated for local bridge projects, $158,389,169 (63%) has been expended.  For this purpose, “expended” means that funds have been paid or are under contract to the county vendor.  The remaining $91,610,831 has been sent to the counties for approved programs, but has not yet been expended.

The table on the following page summarizes expenditures for the Department, NJ TRANSIT and each county.  The following pages provide a detailed report on the status of funds and projects.

| Table of Contents Summary | Page 4 |
| --- | --- |
| Atlantic | 5 |
| Bergen | 9 |
| Bridge Bond Discretionary | 14 |
| Burlington | 20 |
| Camden | 25 |
| Cape May | 27 |
| Cumberland | 28 |
| Essex | 35 |
| Gloucester | 44 |
| Hudson | 47 |
| Hunterdon | 50 |
| Mercer | 54 |
| Middlesex | 56 |
| Monmouth | 58 |
| Morris | 63 |
| NJDOT Projects and Programs | 67 |
| NJ TRANSIT | 80 |
| Ocean | 81 |
| Passaic | 84 |
| Salem | 89 |
| Somerset | 92 |
| Sussex | 97 |
| Union | 101 |
| Warren | 105 |

Bridge Bond Summary

|  |  | Programmed | Expended | Percent Expended |
| --- | --- | --- | --- | --- |
|  | Atlantic | $8,061,000 | $3,083,677 | 38.3% |
|  | Bergen | $18,417,000 | $4,734,378 | 25.7% |
|  | Bridge Bond Discretionary | $25,000,000 | $7,563,214 | 30.3% |
|  | Burlington | $9,459,000 | $8,823,758 | 93.3% |
|  | Camden | $9,069,000 | $1,311,598 | 14.5% |
|  | Cape May | $6,000,000 | $6,000,000 | 100.0% |
|  | Cumberland | $6,000,000 | $4,866,887 | 81.1% |
|  | Essex | $16,077,000 | $11,405,665 | 70.9% |
|  | Gloucester | $6,000,000 | $2,419,939 | 40.3% |
|  | Hudson | $10,489,000 | $10,489,000 | 100.0% |
|  | Hunterdon | $7,739,000 | $7,157,012 | 92.5% |
|  | Mercer | $10,570,000 | $2,060,669 | 19.5% |
|  | Middlesex | $11,012,000 | $4,073,343 | 37.0% |
|  | Monmouth | $25,000,000 | $22,818,055 | 91.3% |
|  | Morris | $10,162,000 | $6,658,457 | 65.5% |
|  | NJDOT | $170,000,000 | $160,822,320 | 94.6% |
|  | NJ TRANSIT | $80,000,000 | $80,000,000 | 100.0% |
|  | Ocean | $9,690,000 | $9,690,000 | 100.0% |
|  | Passaic | $16,624,000 | $5,218,087 | 31.4% |
|  | Salem | $6,000,000 | $5,901,575 | 98.4% |
|  | Somerset | $14,593,000 | $14,593,000 | 100.0% |
|  | Sussex | $6,000,000 | $4,798,301 | 80.0% |
|  | Union | $12,038,000 | $11,891,684 | 98.8% |
|  | Warren | $6,000,000 | $4,794,717 | 79.9% |
|  | TOTAL | $500,000,000 | $399,211,489 | 79.8% |
|  | Date: May 9, 2007 |  |  |  |

Atlantic

Atsion/Middle Road Bridge

Project Description

This project will provide for the replacement of Bridge H12 over the Great Swamp Branch.  Work will

include permits, final design, construction and inspection costs.

Route:	CR 613	Structure No.:	01H0012

Project ID No.:	BATL06

Municipality:	Hammonton Town

Project Start Date:	1/20/2003

Programmed:	$469,239

Expended:	$0

Status:

Scoping contract 80% complete, funded with $122,500 in BB-89 funds. Final design ($217,500),

Construction (partial Bridge Bond Funding of $233,206) and Inspection ($18,533) are to be funded with

BB-99 funds. Additional construction and inspection funding to be determined. Design expected to start

in September 2007. Construction award targeted for January 2009.

Atsion-Pleasant Mill Road (Municipal Street) Bridge over

Nescochague Creek

Project Description

This project will provide for the replacement of Bridge M-30 over Nescochague Creek. Work will include

surveying, permitting, final design (County staff), construction & inspection. Atlantic County will design

the bridge with in-house staff.

Route:	Structure No.:	01M0030

Project ID No.:	BATL08

Municipality:	Mullica Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

This project has been removed from the 1999 Bridge Bond Program. All funds have been reallocated to

other projects.

Dorset Avenue Bridge over Inside Thorofare

Project Description

This project will provide for the replacement of the steel open grid deck system on the Dorset Avenue

Bridge (01V0001) over Inside Thorofare. Work will include design, construction & inspection.

Route:	 CR	Structure No.:	01V0001

Project ID No.:	BATL09

Municipality:	Ventnor City

Project Start Date:	1/1/2005

Programmed:	$1,333,030

Expended:	$1,333,030

Status:

Construction complete but closeout is pending. Total contract costs were $1,333,030.00 (BB99 funds)

including design, construction & inspection.

Eighth Street (Municipal Street) Bridge

Project Description

This project will provide for the replacement of Bridge BV-7 over Hospitality Branch.  Work will include

scoping, permits, final design and construction.

Route:	Structure No.:	01BV007

Project ID No.:	BATL04

Municipality:	Folsom Boro

Project Start Date:	1/20/2003

Programmed:	$240,000

Expended:	$0

Status:

Scoping contract is complete, funded with $34,077 and $115,863 in BB-83 and BB-89 funds,

respectively. Final design ($240,000) is funded with BB-99 funds. Construction ($1,355,000) and

Inspection ($110,000) shall be funded with other sources. Design expected to begin in June 2007.

Somers Point-Mays Landing Rd. Bridge over Patcong Creek

(Stab. Repairs)

Project Description

This project will provide for stabilization and repairs to Bridge EH-32 over Patcong Creek.  Work will

include replacement of four timber piles on two separate piers.

Route:	CR 559	Structure No.:	01EH032

Project ID No.:	BATL02

Municipality:	Egg Harbor Twp.	Somers Point City

Project Start Date:	6/1/2004

Programmed:	$1,464,670

Expended:	$1,464,670

Status:

Construction complete but closeout is pending. Total contract costs were $1,464,670.16 (BB99 funds)

including design, construction & inspection.

Somers Point-Mays Landing Road Bridge over Lakes Creek

Project Description

This project will provide for the replacement of Bridge EH-29 over Lakes Creek.  Work to be

accomplished will including scoping, permits, final design and construction.

Route:	CR 559	Structure No.:	01EH029

Project ID No.:	BATL01

Municipality:	Egg Harbor Twp.

Project Start Date:	11/1/2002

Programmed:	$2,179,719

Expended:	$0

Status:

Scoping contract awarded for $125,281.00 ($125,000 BB83 & $281.00 BB89 funds). Scoping is 85%

complete. Design anticipated to start in September 2007. Construction contract anticipated to be awarded

Somers Point-Mays Landing Road Bridge over Patcong Creek

Project Description

This project will provide for the scoping/preliminary design phase for the replacement of Bridge EH-32

over Patcong Creek.

Route:	CR 559	Structure No.:	01EH032

Project ID No.:	BATL07

Municipality:	Egg Harbor Twp.	Somers Point City

Project Start Date:	1/20/2003

Programmed:	$254,400

Expended:	$254,400

Status:

Scoping phase is 95% complete, funded with $254,400 BB-99 funds. Funding of future phases has not yet

been determined.

Weymouth Road Bridges

Project Description

This project will provide for the replacement of Bridges HML22 and HML23 over Great Egg Harbor

River.  Work will include scoping, permits, final design and construction.

Structure Nos.:  01HML22 and 01HML23.

Route:	CR 559	Structure No.:	See Descript.

Project ID No.:	BATL05

Municipality:	Hamilton Twp.

Project Start Date:	5/2/2003

Programmed:	$894,887

Expended:	$31,577

Status:

Scoping contract is 80% complete. Funded with $2,283 (BB-83), $10,290 (BB-89) and $31,577 (BB-99)

funds. Final design ($462,900), ROW ($20,000), Construction ($352,136) and Inspection ($28,274) are

to be funded with BB-99 funds. Additional Construction and Inspection funding to be determined. Design

expected to begin in January 2008. Construction award targeted for February 2010. County anticipates

using BB-99 funds ($200,000 est.) for emergency repairs.

Zion Road Bridge

Project Description

This project will provide for the replacement of Bridge EH-10 over Patcong Creek.  Work will include

scoping, permits, final design and construction.

Route:	CR 615	Structure No.:	10EH010

Project ID No.:	BATL03

Municipality:	Egg Harbor Twp.	Northfield City

Project Start Date:	11/1/2002

Programmed:	$1,225,055

Expended:	$0

Status:

Scoping contract is complete, funded with $125,000 and $24,945 in BB-83 and BB-89 funds,

respectively. Final design ($250,055), ROW ($20,000), Construction ($900,000) and Inspection

($75,000) are to be funded with BB-99 funds. Design expected to begin in June 2007. Construction award

Summary for 'COUNTY' =  Atlantic (9 detail records)

Sum	Programmed:	$8,061,000.00

Expended:	$3,083,677.00

Bergen

Brookside Avenue Bridge

Project Description

This project will provide for the replacement of the structure over the Ho-Ho-Kus Brook.

Route:	Structure No.:	020001B

Project ID No.:	BBER03

Municipality:	Allendale Boro

Project Start Date:

Programmed:	$880,000

Expended:	$731,900

Status:

Need ROW and new DEP permit.

Court Street Bridge

Project Description

This project will provide for the rehabilitation of the structure over the Hackensack River.

Route:	Structure No.:	020004A

Project ID No.:	BBER01

Municipality:	Hackensack City	Bogota Boro

Project Start Date:	4/11/2001

Programmed:	$6,097,000

Expended:	$663,000

Status:

Bids scheduled for April 25, 2007

Elm Street Bridge

Project Description

This project will provide for the rehabilitation of the structure over the Hackensack River.

Route:	Structure No.:	020044B

Project ID No.:	BBER10

Municipality:	Oradell Boro

Project Start Date:

Programmed:	$825,000

Expended:	$179,000

Status:

Project on temporary "Hold" until procedure issues are resolved.  Agreement with Public Service being

resolved as to placement and payment of overhead power lines.  Town to confer with County as to width

of bridge.  Public Service has rescinded its proposal with the County as to relocation of power poles.

Town wants existing width, County investigating rehabilitation of structure.

Lafayette Avenue Bridge

Project Description

This project will provide for the replacement of the structure over the Musquapsink Brook.

Route:	Structure No.:	020067C

Project ID No.:	BBER14

Municipality:	Washington Twp.	Westwood Boro

Project Start Date:

Programmed:	$660,000

Expended:	$691,867

Status:

Construction complete - 3/9/2006

Lake Avenue Bridge over Goffle Brook, Midland Park

Project Description

This project will provide for the replacement of the structure over the Goffle Brook.

Route:	Structure No.:	020035A

Project ID No.:	BBER09

Municipality:	Midland Park Boro

Project Start Date:	8/28/2001

Programmed:	$880,000

Expended:	$89,900

Status:

Under Design.  Design contract funded with $89,900.  Bridge is eligible therefore Historic Bridge

Alternatives Analysis was done, currently under review at SHPO.  Problem with utilities.  They want

consultant to design and county to pay for all relocations. Tentative construction start - spring 2008.

Lake Street Bridge over Ramsey Brook, Ramsey

Project Description

This project will provide for the replacement of the structure over the Ramsey Brook with a culvert.

Route:	Structure No.:	020048A

Project ID No.:	BBER11

Municipality:	Ramsey Boro

Project Start Date:

Programmed:	$880,000

Expended:	$101,150

Status:

Under Design.  In advanced stages of design. Need permits and ROW.

Maple Avenue Bridge

Project Description

This project will provide for the replacement of the structure over the Ho-Ho-Kus Brook.

Route:	Structure No.:	020028B

Project ID No.:	BBER07

Municipality:	Ho-Ho-Kus Boro

Project Start Date:

Programmed:	$1,100,000

Expended:	$161,529

Status:

Consultant wants to re-negotiate constract with County due to extra work involved with intersection

Paris Avenue Bridge

Project Description

This project will provide for the replacement of the structure over the Sparkill Brook.

Route:	Structure No.:	020055A

Project ID No.:	BBER13

Municipality:	Rockleigh Boro

Project Start Date:

Programmed:	$990,000

Expended:	$112,870

Status:

Under Design. Have stream encroachment permit.  Utility problems, hopefully resolved. Consultant will

have to redesign part of project to accommodate new housing developments on either side of bridge.

Passaic Avenue Bridge over Saddle River

Project Description

This project will provide for the replacement of the structure over the Saddle River.

Route:	Structure No.:	020031B

Project ID No.:	BBER02

Municipality:	Lodi Boro

Project Start Date:

Programmed:	$2,200,000

Expended:	$109,837

Status:

Consultant in the process of compiling all the preliminary design parameters for the project.  A.C.O.E.

requires a 4 foot increase in bridge elevation- this has caused the project to be held in abeyance.  Redesign

required.  No projection for bids.

Patterson Street Bridge

Project Description

This project will provide for the replacement of the structure over the Pascack Brook.

Route:	Structure No.:	020027C

Project ID No.:	BBER06

Municipality:	Hillsdale Boro

Project Start Date:

Programmed:	$770,000

Expended:	$91,800

Status:

Under Design, administered by Hillsdale. Consultant finalizing design-tentative construction start- spring

Pulis Avenue Bridge

Project Description

This project will provide for the replacement of the structure over the Ho-Ho-Kus Brook.

Route:	Structure No.:	020020B

Project ID No.:	BBER05

Municipality:	Franklin Lakes Boro	Mahwah Twp.

Project Start Date:

Programmed:	$1,100,000

Expended:	$103,500

Status:

Under Design.   Administered by Mahwah.  Project held in abeyance-town does not want to proceed.

Ramapo Valley Road Bridge

Project Description

This project will provide for the replacement of the structure over the Mahwah Creek.

Route:	Structure No.:	020033C

Project ID No.:	BBER08

Municipality:	Mahwah Twp.

Project Start Date:	4/15/2002

Programmed:	$990,000

Expended:	$70,050

Status:

Under Design.  Design contract funded with $70,050.  Consultant finalizing design- tentative construction

start - spring 2008.

Rivervale Road Bridge

Project Description

This project will provide for the rehabilitation of the structure over the Holdrum Brook.

Route:	Structure No.:	020053C

Project ID No.:	BBER12

Municipality:	River Vale Twp.

Project Start Date:

Programmed:	$660,000

Expended:	$924,507

Status:

Construction complete 5/27/2005

West Crescent Avenue Bridge

Project Description

This project will provide for the total replacement of the structure over Ramsey Brook.

Route:	Structure No.:	020001C

Project ID No.:	BBER04

Municipality:	Allendale Boro

Project Start Date:

Programmed:	$385,000

Expended:	$703,468

Status:

Project complete 2006

Summary for 'COUNTY' =  Bergen (14 detail records)

Sum	Programmed:	$18,417,000.00

Expended:	$4,734,378.07

Bridge Bond Discretionary

Alexander Road Bridge

Project Description

This project will address the replacement of the Alexander Road Bridge over Amtrak.  The overall

condition of this structure is listed as critical.  The bridge is structurally deficient with a sufficiency rating

of 3.3 and has deterioriated to the point that it requires replacement.

Route:	Structure No.:	1149173

Project ID No.:	99414

Municipality:	West Windsor Twp.

Project Start Date:	2/1/2002

Programmed:	$2,567,084

Expended:	$1,555,234

Status:

This project has been advanced to preliminary design.  Only the intersection immediately adjacent to the

bridge will be included in the project; the Bear Brook intersection will not be included.  Utility costs of

$466,850 and right of way costs of $545,000 are included in the programmed amount.

Colonial Way Culvert

Project Description

This project will provide for the replacement of the existing Colonial Way Culvert with a new culvert.

Route:	Structure No.:

Project ID No.:	BDIS11

Municipality:	Washington Twp.

Project Start Date:	7/29/2004

Programmed:	$150,000

Expended:	$106,521

Status:

Construction completed. Final invoice was processed in April 2005.

Corson Inlet Bridge

Project Description

This project will fund the replacement of the bridge rail system for the Ocean Drive Bridge over Corson

Inlet.  The bridge rail system is severely deteriorated and replacement is necessary.  The replacement of

the bridge rail system is part of the overall project that includes the rehabilitation of the existing Ocean

Drive Bridge.  The county will provide their own funds for the costs of the bridge rehabilitation and

anticipates contributing $3,180,000 of the overall construction cost estimate of $3,580,000.

Route:	Structure No.:	3100002

Project ID No.:	BDIS10

Municipality:	Upper Twp.

Project Start Date:

Programmed:	$400,000

Expended:	$0

Status:

The project is currently under design. The county is awaiting FHWA’s approval of historic/ornamental

bridge rail since June 2006. Request by County 3/07 to transfer funds to use on another bridge.

Franklin Viaduct (E-07)

Project Description

This structure is over the NYS&W RR and Wallkill River.  County Route 631 is a critical artery that

connects Routes 23 and 94 in the north central region of the county.  The bridge was built from spare

parts in 1927 and was rebuilt in 1974.  The structure was struck by a train in 1987 and was repaired.  It

has been recommended for replacement in the last several NBIS inspections.  Due to the many

undocumented repairs and reconstruction projects, there is a great potential for hidden flaws.  In 1997,

the NBIS brought forth a flag for such a potential hidden deficiency.  Subsequent to the NBIS inspection,

an in-depth inspection was performed that found a crack in one of the girder plates.  This resulted in an

emergency repair to the structure.  The bridge has a sufficiency rating of 2.4.  The County proposes to

replace the structure in the same vicinity but probably not on the same alignment.

Route:	CR 631	Structure No.:	1900E07

Project ID No.:	NS9910

Municipality:	Franklin Boro

Project Start Date:	6/25/2001

Programmed:	$10,000,000

Expended:	$275,000

Status:

Under design - anticipated construction award by 6/09

Ivy Avenue Bridge

Project Description

This project will provide for the replacement of a timber bridge.

Route:	Structure No.:	020026M

Project ID No.:	BDIS07

Municipality:	Haworth Boro

Project Start Date:

Programmed:	$750,000

Expended:	$0

Status:

under construction

Local Bridge Bond, Discretionary

Project Description

Under the Statewide Transportation and Local Bridge Bond Act of 1999, grants were appropriated to the

county governments for the cost of construction, reconstruction, demolition, removal, replacement,

improvement, repair or rebuilding of structurally deficient bridges carrying county or municipal roads.

Route:	Structure No.:	N/A

Project ID No.:	00354D1

Municipality:	Various

Project Start Date:

Programmed:	$5,722,701

Expended:	$0

Status:

Main Street Bridge

Project Description

This project will provide for emergency repairs to the Main Street bridge.  The raceway culvert collapsed

when a school bus traveling on Main Street passed over it.

Route:	CR 539	Structure No.:

Project ID No.:	BDIS14

Municipality:	Allentown Boro

Project Start Date:

Programmed:	$100,000

Expended:	$100,000

Status:

The construction contract in the amount of $32,514 was awarded on March 27, 2003.  An agreement

dated February 23, 2004 expanded the project limits for the county to use the remaining funds.  Contract

2 in the amount of $77,617 was approved.  Currently awaiting closeout document from the County in

order to process the final voucher.

Maple Lake Road

Project Description

This project will provide for roadway reconstruction of Maple Lake Road from Paterson-Hamburg

Turnpike to the municipal boundary.  This is necessary to provide for a detour route while the Paterson-

Hamburg Turnpike bridge is under construction.

Route:	Structure No.:	N/A

Project ID No.:	BDIS09

Municipality:	Butler Boro

Project Start Date:

Programmed:	$200,000

Expended:	$200,000

Status:

Construction completed substantially

Meadowlands Parkway Bridge

Project Description

This is a five-span, simply supported multiple rolled steel stringer structure over a railroad, ditch and

roadway.  The length of the structure is 316 feet.  This project will provide for the rehabilitation of the

Route:	Structure No.:	0908412

Project ID No.:	BDIS05

Municipality:	Secaucus Town

Project Start Date:

Programmed:	$1,900,000

Expended:	$2,347,656

Status:

contruction complete

New York Avenue Culvert

Project Description

This project will provide for the replacement of the New York Avenue culvert over a tributary of the

Hirschfield Brook.

Route:	Structure No.:	N/A

Project ID No.:	BDIS02

Municipality:	Dumont Boro

Project Start Date:	1/14/2003

Programmed:	$200,000

Expended:	$198,735

Status:

Construction completed on August 22, 2003.  The final payment was processed in July 2004, leaving a

balance of $1,265 in this project.

Nutley Park Bridges

Project Description

Bridge Bond Discretionary Funds have been provided to Nutley Township for the improvements to six

park bridges located in Booth Park, Memorial Park I, Memorial Park II, and Kingsland Park.

Route:	Structure No.:	N/A

Project ID No.:	BDIS04

Municipality:	Nutley Twp.

Project Start Date:

Programmed:	$150,000

Expended:	$0

Status:

Under Design.

Paterson-Hamburg Turnpike Bridge

Project Description

The Paterson-Hamburg Turnpike over Singac Brook was recently damaged by fire.  This project will

provide for necessary repairs to this structure.

Route:	Structure No.:	1600140

Project ID No.:	BDIS08

Municipality:	Wayne Twp.

Project Start Date:

Programmed:	$177,050

Expended:	$177,050

Status:

Construction complete.

River Street Railroad Bridge

Project Description

This is a joint venture between Bergen County, the City of Hackensack and the railroad to replace the old

railroad bridge that currently has low clearance.  The roadway under the bridge will be widened to four

lanes to match the adjacent approach roads.

Route:	Structure No.:	N/A

Project ID No.:	BDIS03

Municipality:	Hackensack City

Project Start Date:

Programmed:	$500,000

Expended:	$500,000

Status:

Construction is approximately 90% complete.  Total award is $4,167,456; only $500,000 in Bridge Bond

funds were used to fund this project, the remaining funds were provided from other NJDOT and County

Rockaway Road Bridge (Bridge T-80)

Project Description

This project will provide for the replacement of this structure over the north branch of the Rockaway

Route:	Structure No.:	1000039

Project ID No.:	BDIS01

Municipality:	Tewksbury Twp.

Project Start Date:	12/18/2001

Programmed:	$600,000

Expended:	$600,000

Status:

Project completed April 26, 2002.

Roosevelt Boulevard Bridge

Project Description

This project will provide for the rehabilitation of the Roosevelt Boulevard Bridge over Crook Horn

Thorofare.  This bridge will be used as a detour route when construction begins on the Route 52 Causeway

project which is planned in 2007.  In its present condition, the Roosevelt Boulevard bridge cannot safely

carry the anticipated traffic that will use this route as a result of the detour.

Route:	CR 623	Structure No.:	0500004

Project ID No.:	BDIS13

Municipality:	Ocean City	Upper Twp.

Project Start Date:	7/27/2004

Programmed:	$1,450,000

Expended:	$1,450,000

Status:

Construction complete in May 2006. Final invoice processed. Cape May County provided funding above

the $1,450,000  BB-Disc. allotment.

State Street Bridge

Project Description

This proejct will fund emergency repairs on the bridge deck.

Route:	CR 601	Structure No.:	042A001

Project ID No.:	BDIS12

Municipality:	Camden City

Project Start Date:	1/1/2004

Programmed:	$133,165

Expended:	$53,018

Status:

The emergency repairs were completed on April 14, 2004.  Final invoice was processed and project has

been closed.

Summary for 'COUNTY' =  Bridge Bond Discretionary (16 detail records)

Sum	Programmed:	$25,000,000.00

Expended:	$7,563,214.21

Burlington

Carranza Road Bridge

Project Description

This project will provide for the replacement of the Carranza Road bridge over Tributary Shane Branch.

Route:	Structure No.:	03F6001

Project ID No.:	BBUR13

Municipality:	Washington Twp.

Project Start Date:	9/1/2004

Programmed:	$0

Expended:	$0

Status:

County is designing and constructing this project with in-house personnel. Project is being funded with

County funds.

Cookstown-New Egypt Road Bridge

Project Description

This project will provide for the widening and deck replacement of the CR 616 bridge over Tributary

Route:	CR 616	Structure No.:	03G3005

Project ID No.:	BBUR14

Municipality:	North Hanover Twp.

Project Start Date:	5/15/2001

Programmed:	$1,014,372

Expended:	$875,323

Status:

Construction was completed in 2006.  Closing out project.

County Route 537 Bridge over Barkers Brook

Project Description

This project will provide for the rehabilitation of the CR 537 bridge over Barkers Brook.

Route:	CR 537	Structure No.:	03E3330

Project ID No.:	BBUR10

Municipality:	Springfield Twp.

Project Start Date:	10/16/2001

Programmed:	$19,160

Expended:	$19,160

Status:

Preliminary engineering and alternatives analysis report completed. Insufficient 99 - BB funds available

to proceed with project.

County Route 537 Bridge over Parkers Creek

Project Description

This project will provide for the replacement of the CR 537 bridge over Parkers Creek.

Route:	CR 537	Structure No.:	03C4150

Project ID No.:	BBUR04

Municipality:	Mount Laurel Twp.

Project Start Date:	8/1/2001

Programmed:	$3,187,063

Expended:	$3,106,897

Status:

Construction completed in Fall 2004.  Closing out project.

County Route 634 Bridge

Project Description

This project will provide for the rehabilitation of the CR 634 bridge over Rancocas Creek.

Route:	CR 634	Structure No.:	03C4004

Project ID No.:	BBUR03

Municipality:	Mount Laurel Twp.	Willingboro Twp.

Project Start Date:	11/26/2001

Programmed:	$98,015

Expended:	$96,175

Status:

Preliminary engineering and report being finalized. Structure is historically eligible pursuant to NJDOT

Historic Bridge Survey. Final Engineering contract was awarded in 2005; however funding source has not

been determined yet.

County Route 656 Bridge

Project Description

This project will provide for the replacement of the CR 656 bridge over US Pipe Siding.

Route:	CR 656	Structure No.:	03C2002

Project ID No.:	BBUR02

Municipality:	Burlington Twp.

Project Start Date:	10/15/2003

Programmed:	$393,200

Expended:	$102,972

Status:

Design is in progress. Construction targeted for July 2007 (funding not yet determined).

County Route 670 Bridge (Burlington Twp.)

Project Description

This project will provide for the replacement of the CR 670 bridge over Branch of the Assicunk Creek.

Route:	CR 670	Structure No.:	03D3540

Project ID No.:	BBUR05

Municipality:	Burlington Twp.

Project Start Date:	10/8/2002

Programmed:	$2,971,125

Expended:	$2,952,027

Status:

Construction completed in 2006. Closing out project.

County Route 670 Bridge (Springfield Twp.)

Project Description

This project will provide for the replacement of the CR 670 bridge over Branch of the Assicunk Creek.

Route:	CR 670	Structure No.:	03D3600

Project ID No.:	BBUR06

Municipality:	Springfield Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

Inactive - 99 BB funds insufficient to fund project.

Georgetown-Chesterfield Road Bridge

Project Description

This project will provide for the rehabilitation of the Georgetown-Chesterfield Road bridge over Blacks

Route:	Structure No.:	03F2280

Project ID No.:	BBUR12

Municipality:	Chesterfield Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

Inactive - 99 BB funds insufficient to fund project.

Hilliards Road Bridge

Project Description

This project will provide for the rehabilitation of the Hilliards Road bridge over South Branch Rancocas

Route:	Structure No.:	03E4400

Project ID No.:	BBUR11

Municipality:	Southampton Twp.

Project Start Date:	3/1/2000

Programmed:	$145,231

Expended:	$139,419

Status:

Construction completed in 2006.  Closing out project.  Design partially funded by Bridge Bond.

Construction partially funded by Bridge Bond.

River Road (AKA Foundry Road) Bridge over N. Branch

Rancocas Creek

Project Description

This project will provide for the replacement of the River Road Bridge.

Route:	Structure No.:	03D4140

Project ID No.:	BBUR15

Municipality:	Eastampton Twp.

Project Start Date:	12/1/2001

Programmed:	$1,413,851

Expended:	$1,413,851

Status:

Construction substantially completed in May 2006.

Washington Street Bridge over North Branch Rancocas Creek

Project Description

This project will provide for the deck replacement of the Washington Street bridge over North Branch

Rancocas Creek.

Route:	Structure No.:	03D410A

Project ID No.:	BBUR08

Municipality:	Mount Holly Twp.

Project Start Date:	4/2/2002

Programmed:	$137,983

Expended:	$54,734

Status:

Engineering funded by Bridge Bond.  Final construction documents being prepared.  Construction

anticipated Fall 2007.  Insufficient 99 BB funds available to fund construction.  Construction to be funded

be County using alternate funding sources.

White Street Bridge

Project Description

This project will provide for the replacement of the White Street bridge over North Branch Rancocas

Route:	Structure No.:	03D4108

Project ID No.:	BBUR07

Municipality:	Mount Holly Twp.

Project Start Date:	8/1/2001

Programmed:	$79,000

Expended:	$63,200

Status:

Preliminary engineering and report finalized. Structure is historically eligible pursuant to NJDOT Historic

Bridge Survey. Funding not yet determined for design.  County to evaluate alternative funding sources.

Summary for 'COUNTY' =  Burlington (13 detail records)

Sum	Programmed:	$9,459,000.00

Expended:	$8,823,758.00

Camden

Broadway Bridge over Little Timber Creek

Project Description

This project will replace the bridge on CR 551.

Route:	CR 551	Structure No.:	045A010

Project ID No.:	BCAM06

Municipality:	Gloucester City	Brooklawn Boro

Project Start Date:

Programmed:	$1,675,000

Expended:	$278,218

Status:

County has awarded design contract for $233,498. (Permit fees in the amount of $24,000.00 are

ineligible). Design is ongoing but additional work for soil borings is required to test soil contamination.

Estimated total Construction and inspection cost is $2,100,000.00, part of which are to be funded with

BB-99 funds. Construction award targeted for August 2007. County is waiting for NJDEP Permits

East Atlantic Avenue Bridge

Project Description

The existing two-span steel structure over Relief AKA Peter's Creek (Bridge No. 4B-15) will be replaced

with embankment fill and the construction of the roadway on new fill.

Route:	CR 727	Structure No.:	044B015

Project ID No.:	BCAM05

Municipality:	Audubon Boro	Oaklyn Boro

Project Start Date:

Programmed:	$1,894,000

Expended:	$0

Status:

Scoping completed using Federal funds. CED approved by BEPR. Design is ongoing. County's consultant

is preparing documentation for NJDEP permits. Additional funding (about $115,000) for design work

may be BB-99 funds. Total estimated Construction and inspection costs is $1,900,000.00 are to be

funded with BB-99 funds. Construction award targeted for November 2007.

State Street Bridge

Project Description

This project will provide for the rehabilitation of the inoperable two-span, swing truss structure over the

Cooper River (Bridge No. 2A1) according to SHPO directives, or replace it with a new structure if

Route:	CR 601	Structure No.:	042A001

Project ID No.:	BCAM02

Municipality:	Camden City

Project Start Date:

Programmed:	$5,500,000

Expended:	$1,033,380

Status:

Scoping completed using Federal Funds. CED approved by BEPR/FHWA. County has awarded design

contract ($930,580). Bridge Rehab. Program funds ($789,000) & BB-99 funds ($141,580) used for design

contract. Consultant is working on scope of rehabilitation of existing structure. Total estimated

construction cost including ROW, Construction and  Inspection is $8,500,000.00, part of which are to be

funded with BB-99 funds. Construction award targeted for November 2007. County is waiting for NJDEP

Permits approval and working on permit conflict issues associated with NJDOT Flood Tide Gate project.

Summary for 'COUNTY' =  Camden (3 detail records)

Sum	Programmed:	$9,069,000.00

Expended:	$1,311,598.00

Cape May

Ocean Drive Bridge

Project Description

This project will provide for the rehabilitation of Ocean Drive bridge over Great Channel.

Route:	CR 619	Structure No.:	0500028

Project ID No.:	BCAP02

Municipality:	Middle Twp.	Stone Harbor Boro

Project Start Date:	2/1/2001

Programmed:	$6,000,000

Expended:	$6,000,000

Status:

Design contract was completed, in the amount of $467,000 using BB-99 funds. A Construction

Engineering contract was awarded for $519,650 using BB-99 funds. A Construction contract was awarded

for $6,040,000, using $5,013,350 BB-99 and $500,000 Local Bridge FY00 funds; remaining balance of

$526,650 will be funded with BB-99 accrued interest and County funds.

Summary for 'COUNTY' =  Cape May (1 detail record)

Sum	Programmed:	$6,000,000.00

Expended:	$6,000,000.00

Cumberland

Almond Road Bridge

Project Description

This project will provide for the improvement of the functionally obsolete structure over Maurice River.

Route:	Structure No.:	0600014

Project ID No.:	BCUM18

Municipality:	Vineland City

Project Start Date:	1/23/2001

Programmed:	$1,922

Expended:	$1,922

Status:

Design Build Project completed at total cost of $587,843.00. Cost shared with Salem County.

Cumberland County used $1,921.50 (BB99), $8,701.76 (BB83), $243,621.60 (Bridge Rehab.) funds.

County's share of $333,598.14 included Salem County's share and County funds.

Barrett Run Road Bridge

Project Description

This project will provide for the replacement of the structures.

Route:	Structure No.:	0600101

Project ID No.:	BCUM19

Municipality:	Hopewell Twp.

Project Start Date:	7/5/2002

Programmed:	$555,366

Expended:	$555,366

Status:

Construction complete. Total construction cost was $555,365.56 (BB99 funds).

Bay Point Road Bridge

Project Description

This project will provide for the improvement of the functionally obsolete structure over Cedar Ditch.

Route:	Structure No.:	0600041

Project ID No.:	BCUM05

Municipality:	Lawrence Twp.

Project Start Date:	11/1/2004

Programmed:	$514,803

Expended:	$514,803

Status:

Construction complete. Total construction cost was $520,853.15 including $514,803.15 (BB99 funds).

County's share was $6,050.00 (Permits & other costs).

Brandriff Avenue Bridge

Project Description

This project will provide for the improvement of the functionally obsolete structure over Maurice River.

Route:	Structure No.:	0600009

Project ID No.:	BCUM02

Municipality:	Millville City

Project Start Date:	4/30/2003

Programmed:	$269,658

Expended:	$269,658

Status:

Construction complete. Total construction cost was $270,905.50 including $269,658.00 (BB99 funds).

County's share was $1,247.50 (Permits & other costs).

Buckhorn Road Bridge

Project Description

This project will provide for the rehabilitation of the Buckhorn Road bridge over Stow Creek.

Route:	Structure No.:	0600045

Project ID No.:	BCUM12

Municipality:	Stow Creek Twp.	Lower Alloway Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

No BB 1999 funds available to advance this project.

Canton Road Bridge

Project Description

This project will provide for the rehabilitation of the Canton Road bridge over Stow Creek.

Route:	Structure No.:	0600003

Project ID No.:	BCUM14

Municipality:	Stow Creek Twp.	Lower Alloway Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

No BB 1999 funds available to advance this project.

Commerce Street Bridge

Project Description

This project will provide for the rehabilitation of the Commerce Street bridge over the Cohansey River.

Route:	Structure No.:	0600022

Project ID No.:	BCUM09

Municipality:	Bridgeton City

Project Start Date:	2/1/2006

Programmed:	$385,990

Expended:	$385,990

Status:

Construction complete. Total construction cost was $391,014.65 including $385,989.65 (BB99 funds).

County's share was $5,025.00 (Permits & other costs).

Cooks Corner Bridge

Project Description

This project will provide for the replacement of the structurally deficient structure over Raccoon Ditch.

Route:	Structure No.:	0600046

Project ID No.:	BCUM01

Municipality:	Stow Creek Twp.	Greenwich Twp.

Project Start Date:	4/11/2002

Programmed:	$594,139

Expended:	$594,139

Status:

Construction complete. Total construction cost was $749,268.30, including $594,138.87 (BB99),

$67,553.67 (BB83), $17,775.76 (BB89) & $61,850 (BRIDGE REHAB.) funds. County's share was

$7,950.00 (Permits & other costs).

Dante Avenue Bridge

Project Description

This project will provide for the rehabilitation of the Dante Avenue bridge over Menantico Creek.

Route:	Structure No.:	0600012

Project ID No.:	BCUM15

Municipality:	Vineland City

Project Start Date:	7/18/2006

Programmed:	$200,000

Expended:	$89,000

Status:

County awarded a design contract for $89,000. Design is 100% complete. DEP Permit costs are

anticipated to be $8,500. Construction funding is yet to be determined.

Fortescue Road Bridge

Project Description

This project will provide for the rehabilitation of the structure over Fortescue.

Route:	Structure No.:	0600001

Project ID No.:	BCUM07

Municipality:	Downe Twp.

Project Start Date:	4/1/2003

Programmed:	$225,300

Expended:	$25,300

Status:

Design contract was awarded on April 1, 2003, using $25,300 in BB-99 funds. Construction funding has

not been determined (cost anticipated $270,000).

Glade Road Bridge

Project Description

This project will provide for the rehabilitation of the Glade Road bridge over Riggins Ditch.

Route:	Structure No.:	0600043

Project ID No.:	BCUM11

Municipality:	Maurice River Twp.

Project Start Date:	4/1/2003

Programmed:	$200,000

Expended:	$64,525

Status:

Design contract was awarded April 1, 2003, using $64,525 in BB-99 funds. Additional construction

funding is yet to be determined (cost anticipated > $135,000).

Harmony Road Bridge

Project Description

This project will provide for the rehabilitation of the Harmony Road bridge over the Cohansey River.

Route:	Structure No.:	0600048

Project ID No.:	BCUM16

Municipality:	Upper Deerfield Twp.	Hopewell Twp.

Project Start Date:	7/1/2005

Programmed:	$200,000

Expended:	$49,000

Status:

Design contract awarded in July 2006 using $49,000 in BB-99 funds. Design is 100% complete. DEP

permit fees anticipated to be $500.00. Construction funding is yet to be determined.

Lower Sharp Street Bridge

Project Description

This project will provide for the improvement of the functionally obsolete structure over Maurice River.

Route:	Structure No.:	0600054

Project ID No.:	BCUM06

Municipality:	Millville City

Project Start Date:	4/30/2003

Programmed:	$184,067

Expended:	$184,067

Status:

Construction complete. Total construction cost was $185,317.50 including $184,067.50 (BB99 funds).

County's share was $1,250.00 (Permits & other costs).

Mauricetown Road Bridge

Project Description

This project will provide for the rehabilitation of Maurictown Road bridge over Maurice River.

Route:	Structure No.:	0600008

Project ID No.:	BCUM08

Municipality:	Commercial Twp.	Maurice River Twp.

Project Start Date:	4/1/2003

Programmed:	$500,000

Expended:	$38,000

Status:

Design contract was awarded April 1, 2003, using $38,000 in BB-99 funds. Additional construction

funding is yet to be determined due to anticipated construction cost of $1.5 million.

Mayor Aitken Drive Bridge

Project Description

This project will provide for the improvement of the functionally obsolete structure over Cohansey

Route:	Structure No.:	0600023

Project ID No.:	BCUM04

Municipality:	Bridgeton City

Project Start Date:	11/14/2002

Programmed:	$784,515

Expended:	$784,515

Status:

Construction complete. Total construction cost was $785,065.21 including $784,515.21 (BB99 funds).

County's share was $550.00 (Permits & other costs).

New Jersey Avenue Bridge

Project Description

This project will provide for the rehabilitation of the New Jersey Avenue bridge over Oyster Creek.

Route:	Structure No.:	0600031

Project ID No.:	BCUM10

Municipality:	Downe Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

No BB 1999 funds available to advance this project.

Seeley-Lebanon Road Bridge

Project Description

This project will provide for the rehabilitation of the Seeley-Lebanon Road bridge over the Cohansey

Route:	Structure No.:	0600002

Project ID No.:	BCUM13

Municipality:	Upper Deerfield Twp.	Hopewell Twp.

Project Start Date:	4/1/2003

Programmed:	$420,926

Expended:	$420,926

Status:

Construction complete. Total construction cost was $421,413.24 including $420,925.74 (BB99 funds).

County's share was $487.50 (Permits & other costs).

West Avenue Bridge

Project Description

This project will provide for the improvement of the functionally obsolete structure over Irelands Mill

Route:	Structure No.:	0600020

Project ID No.:	BCUM03

Municipality:	Bridgeton City

Project Start Date:	9/12/2001

Programmed:	$813,676

Expended:	$813,676

Status:

Construction complete. Total construction cost was $817,863.30 including $813,675.80 (BB99 funds).

County's share was $4,187.50 (Permits & other costs).

West Park Drive Bridge

Project Description

This project will provide for the rehabilitation of West Park Drive Bridge over Sunset Lake Raceway.

Route:	Structure No.:	0600017

Project ID No.:	BCUM17

Municipality:	Bridgeton City

Project Start Date:	7/1/2005

Programmed:	$149,638

Expended:	$76,000

Status:

Design contract was awarded in July 2006, using $76,000 in BB-99 funds. Permit costs anticipated to be

$2,500.00. Construction funding is yet to be determined.

Summary for 'COUNTY' =  Cumberland (19 detail records)

Sum	Programmed:	$6,000,000.00

Expended:	$4,866,887.00

Essex

Baldwin Street Bridge

Project Description

This project will provide for the rehabilitation of the structure over the  JFK Drive.

Route:	Structure No.:	0700082

Project ID No.:	BESS02

Municipality:	Bloomfield Twp.

Project Start Date:	1/4/2005

Programmed:	$549,756

Expended:	$549,756

Status:

Construction complete.

Bloomfield Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Peckman River.

Route:	Structure No.:	0700012

Project ID No.:	BESS23

Municipality:	Verona Twp.

Project Start Date:	9/26/2005

Programmed:	$1,629,873

Expended:	$1,629,873

Status:

Construction complete.

Brookfield Avenue Bridge

Project Description

This project will provide for the rehabilitation of the structure over Third River.

Route:	Structure No.:	0700064

Project ID No.:	BESS19

Municipality:	Nutley Twp.

Project Start Date:

Programmed:	$200,000

Expended:	$0

Status:

Awaiting design.

Central Avenue Culvert

Project Description

This project will provide for the replacement of the culvert on Central Avenue over Green Brook.

Route:	Structure No.:	NC512GR

Project ID No.:	BESS18

Municipality:	North Caldwell Twp.

Project Start Date:	6/27/2002

Programmed:	$1,653,355

Expended:	$1,653,355

Status:

Design/inspection contract $130,653.60.  Construction completed.  Construction contract is

Chancellor Avenue & Springfield Avenue Culverts

Project Description

This project will provide for replacement of the culverts on Chancellor Avenue and Springfield Avenue

over Lightning Brook.

Structure Nos.:  MP308LT, MP413LT

Route:	Structure No.:	See Descript.

Project ID No.:	BESS13

Municipality:	Maplewood Twp.

Project Start Date:

Programmed:	$1,603,266

Expended:	$0

Status:

Awarded Dec. 19, 2006.  Construction to start on February 15,2007 contract award for $1,457,515.00

inspection 10%

Cleveland Street Bridge

Project Description

This project will provide for the replacement of the structure over Second River.

Route:	Structure No.:	0700074

Project ID No.:	BESS20

Municipality:	Orange Twp.

Project Start Date:

Programmed:	$507,072

Expended:	$0

Status:

Awarded November 13, 2006.  Construction on hold due to utility relocation.  Contract awarded for

East Northfield Road Bridge

Project Description

This project will provide for the replacement of the structure over Bear Brook.

Route:	Structure No.:	0700090

Project ID No.:	BESS11

Municipality:	Livingston Twp.

Project Start Date:	10/17/2005

Programmed:	$919,464

Expended:	$919,464

Status:

Construction complete.

Eisenhower Parkway Bridge

Project Description

This project will provide for the rehabilitation of the structure over South Branch of Foulerton's Brook.

Route:	Structure No.:	0700015

Project ID No.:	BESS22

Municipality:	Roseland Boro

Project Start Date:

Programmed:	$550,000

Expended:	$0

Status:

In design, construction to start in Summer '07

Essex Street Bridge

Project Description

This project will provide for the rehabilitation of the structure over West Branch of the Rahway River.

Route:	Structure No.:	0703065

Project ID No.:	BESS14

Municipality:	Millburn Twp.

Project Start Date:

Programmed:	$100,000

Expended:	$0

Status:

Awaiting design.

Franklin Avenue & Whittlessey Avenue Culverts

Project Description

This project will provide for the replacement of culverts on Franklin Avenue and Whittlessey Avenue

over Wigwam Brook.

Structure Nos.:  WO508WW, WO523WW

Route:	Structure No.:	See Descript.

Project ID No.:	BESS26

Municipality:	West Orange Twp.

Project Start Date:	7/16/2001

Programmed:	$507,644

Expended:	$461,494

Status:

Construction finish date 11-29-01  Construction cost $461,494.16.   Construction cost includes

inspection $46,149.42.

Glen Avenue Bridge

Project Description

This project will provide for the replacement of the structure over the West Branch of Rahway River.

Route:	Structure No.:	0700053

Project ID No.:	BESS15

Municipality:	Millburn Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

This project is being dropped from the Bridge Bond Program.

Hillside Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Toney's Brook.

Route:	Structure No.:	0700088

Project ID No.:	BESS09

Municipality:	Glen Ridge Twp.

Project Start Date:	12/5/2004

Programmed:	$1,212,096

Expended:	$1,212,096

Status:

Construction complete.

Hoover Avenue Bridge

Project Description

This project will provide for the rehabilitation of the structure over the Third River.

Route:	Structure No.:	0700086

Project ID No.:	BESS03

Municipality:	Bloomfield Twp.

Project Start Date:

Programmed:	$431,571

Expended:	$0

Status:

Awaiting design.

James Street Bridge

Project Description

This project will provide for the rehabilitation of the structure over JFK Drive.

Route:	Structure No.:	0700081

Project ID No.:	BESS04

Municipality:	Bloomfield Twp.

Project Start Date:

Programmed:	$567,315

Expended:	$567,315

Status:

Rehabilitation completed January 2003.  Construction cost $567,314.70.

Linden Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Peckman River.

Route:	Structure No.:	0700103

Project ID No.:	BESS24

Municipality:	Verona Twp.

Project Start Date:

Programmed:	$715,000

Expended:	$0

Status:

Design complete.  To be advertised in June 2007.  Construction to start in 2008 as requested by

Madison Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Elizabeth River.

Route:	Structure No.:	0700094

Project ID No.:	BESS10

Municipality:	Irvington Twp.

Project Start Date:	12/5/2004

Programmed:	$550,007

Expended:	$550,007

Status:

Construction complete.

Mill Street Bridge

Project Description

This project will provide for the rehabilitation of the structure over the Second River.

Route:	Structure No.:	0700060

Project ID No.:	BESS01

Municipality:	Belleville Twp.

Project Start Date:

Programmed:	$100,000

Expended:	$0

Status:

Awaiting design.

Nassau Street, Watchung Street & Joyce Street Culverts

Project Description

This project will provide for the replacement of the culverts on Nassau Street, Watchung Street and Joyce

Street over the East Branch of the Rahway River and Second River.

Structure Nos.:  OR405EB, OR508SR, WO511B

Route:	Structure No.:	See Descript.

Project ID No.:	BESS21

Municipality:	Orange Twp.	West Orange Twp.

Project Start Date:	4/23/2001

Programmed:	$566,151

Expended:	$566,151

Status:

Construction completed 10/24/01.  Construction final cost $540,352.16.  Inspection costs $25,799.32.

Ozone Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Peckman River.

Route:	Structure No.:	0700042

Project ID No.:	BESS25

Municipality:	Verona Twp.

Project Start Date:

Programmed:	$100,000

Expended:	$0

Status:

Awaiting design.

Parsonage Hill Road & White Oak Ridge Road Culverts

Project Description

This project will provide for the replacement of the culverts on Parsonage Hill Road and White Oak

Ridge Road over Taylor's Brook.

Structure Nos.:  ML309TY, ML413TY

Route:	Structure No.:	See Descript.

Project ID No.:	BESS16

Municipality:	Millburn Twp.

Project Start Date:	8/26/2002

Programmed:	$481,905

Expended:	$438,905

Status:

Construction complete.  Final inspection pending.  Construction contract is $438,905.15. Construction

inspection $43,000.00.

Pier Lane, Kirkpatrick Lane & Washington Street Culverts

Project Description

This project will provide for the replacement of culverts on Pier Lane, Kirkpatrick Lane and Washington

Street over three brooks.

Structure Nos.:  FR314DP, WC418LN, MN534NS

Route:	Structure No.:	See Descript.

Project ID No.:	BESS08

Municipality:	Fairfield Twp.	West Caldwell Twp.

Montclair Twp.

Project Start Date:	7/22/2002

Programmed:	$827,803

Expended:	$752,603

Status:

Construction completed.  Construction contract is $752,603.26.  Construction inspection cost $75,200.00

Ridgewood Road Bridge

Project Description

This project will provide for the replacement of the structure over West Branch of Rahway River.

Route:	Structure No.:	0700054

Project ID No.:	BESS17

Municipality:	Millburn Twp.

Project Start Date:	5/7/2003

Programmed:	$724,632

Expended:	$724,556

Status:

Construction completed 12/5/03.  Construction contract  $658,755.99.  Inspection cost $65,800.00.

Runnymede Road Bridge

Project Description

This project will provide for the replacement of the structure over Pine Brook.

Route:	Structure No.:	0700104

Project ID No.:	BESS07

Municipality:	Essex Fells Twp.

Project Start Date:

Programmed:	$724,626

Expended:	$724,626

Status:

Design paid for by others. Construction Contract  $658,755.99. Construction completed 11/5/03.

Inspection cost $65,870.00.

Watchung Avenue Bridge over Third River

Project Description

This project will provide for the replacement of the structure over Third River.

Route:	Structure No.:	0700033

Project ID No.:	BESS05

Municipality:	Bloomfield Twp.

Project Start Date:

Programmed:	$100,000

Expended:	$0

Status:

Awaiting design.

West Oakwood Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Canoe Brook.

Route:	Structure No.:	0700102

Project ID No.:	BESS12

Municipality:	Livingston Twp.

Project Start Date:	11/29/2004

Programmed:	$655,464

Expended:	$655,464

Status:

Construction complete.

West Street Bridge

Project Description

This project will provide for the rehabilitation of the structure over Second River.

Route:	Structure No.:	0700055

Project ID No.:	BESS06

Municipality:	Bloomfield Twp.

Project Start Date:

Programmed:	$100,000

Expended:	$0

Status:

Awaiting design.

Summary for 'COUNTY' =  Essex (26 detail records)

Sum	Programmed:	$16,077,000.00

Expended:	$11,405,665.00

Gloucester

Coles Mill Road Bridge

Project Description

This project will provide for the replacement of the Coles Mill Road bridge over the Hospitality Branch

of the Great Egg Harbor River.  The existing reinforced concrete slab structure will be replaced with a

wider precast concrete arch structure.

Route:	CR 538	Structure No.:	0809P02

Project ID No.:	BGLO06

Municipality:	Monroe Twp.

Project Start Date:	2/5/2001

Programmed:	$778,857

Expended:	$778,857

Status:

County used own funds for Design. Construction is completed at a final cost of $778,857 in BB-99 funds.

Project is complete.

County Route 553 Alt. Bridge

Project Description

This project will provide for the replacement of CR 553 Alternate over Chestnut Branch of Mantua

Creek.  The existing reinforced concrete arch structure will be replaced with a wider precast concrete arch

Route:	CR 553 Alt.	Structure No.:	0805I03

Project ID No.:	BGLO03

Municipality:	Mantua Twp.

Project Start Date:	3/1/2005

Programmed:	$1,400,000

Expended:	$264,624

Status:

County has completed survey of the existing structure, roadway, stream channel & general topography.

Preliminary Permit & Construction Plans are 30% complete. Project is under design contract ($264,624

in BB-99 funds). Construction will commence upon securing ROW and obtaining Permits (cost estimate =

$1,525,000 BB-99 funds).

County Route 640 Bridge

Project Description

This project will provide for the replacement of the bridge over Matthew's Branch (AKA Starr's Ditch) of

the Woodbury Creek.  The existing reinforced concrete arch structure (20-foot span) will be replaced

with a wider and significantly longer (110 foot) prestressed concrete "I" girder structure.

Route:	CR 640	Structure No.:	0802H03

Project ID No.:	BGLO01

Municipality:	West Deptford Twp.

Project Start Date:	3/1/2006

Programmed:	$1,850,000

Expended:	$350,000

Status:

Design is 100% complete and permits are completed. Construction cost estimate has been revised to

$3,870,000. County will be unable to bid construction project due to high cost estimate. Construction will

be using BB-99 funds.

Glen Echo Avenue Bridge

Project Description

This project will provide for the replacement of CR 538 bridge over Narraticon Run of Raccoon Creek.

The existing reinforced concrete arch structure will be replaced with a wider precast concrete or structural

plate arch structure.

Route:	CR 538	Structure No.:	0805D05

Project ID No.:	BGLO02

Municipality:	Swedesboro Boro

Project Start Date:	3/1/2005

Programmed:	$221,143

Expended:	$170,694

Status:

County has completed survey of the existing structure, roadway, stream channel & general topography.

Project is under design ($170,694 in BB-99 funds).  Revised cost estimate $1,722,000.

Washington Avenue Bridge over Scotland Run

Project Description

This project will provide for the replacement of the bridge over Scotland Run.  The existing two-span

timber stringer structure will be replaced with a wider one-span timber stringer structure.

Route:	Structure No.:	0808L02

Project ID No.:	BGLO04

Municipality:	Franklin Twp.

Project Start Date:	1/1/2003

Programmed:	$850,000

Expended:	$749,374

Status:

Construction is 100% complete with final cost $749,373.50. Construction and Inspection cost ($34,000)

were funded with BB-99 funds.

Whitehall Road Bridge

Project Description

This project will provide for the replacement of the Whitehall Road bridge over the Hospitality Branch

of Great Egg Harbor River.  The existing reinforced concrete slab structure will be replaced with a wider

box culvert or arch structure.

Route:	Structure No.:	0808O01

Project ID No.:	BGLO05

Municipality:	Monroe Twp.

Project Start Date:	1/1/2003

Programmed:	$900,000

Expended:	$106,390

Status:

Design contract awarded for $106,390 using BB-99 funds. Final design is 100% complete. All permits

have been obtained.

Summary for 'COUNTY' =  Gloucester (6 detail records)

Sum	Programmed:	$6,000,000.00

Expended:	$2,419,939.00

Hudson

14th Street Viaduct

Project Description

This project will provide for the interim rehabilitation of a 1460-foot, 31-span bridge over Conrail and

local street.

Route:	Structure No.:	0900016

Project ID No.:	BHUD14

Municipality:	Hoboken City

Project Start Date:	4/10/2002

Programmed:	$53,500

Expended:	$53,500

Status:

This funding covered construction engineering and inspection costs on this project, actual construction

funding was provided through another source.  Construction completed November 15, 2002.

Bergen Avenue Bridge

Project Description

This project will provide for the rehabilitation of a 54-foot, single-span bridge over an abandoned railroad.

Route:	Structure No.:	0900011

Project ID No.:	BHUD10

Municipality:	Jersey City

Project Start Date:	2/22/2005

Programmed:	$36,800

Expended:	$36,800

Status:

Design cost $36,800.00.

JFK Boulevard (Columbus Bridge)

Project Description

This project will provide for the rehabilitation of a 487-foot, two-span concrete arch bridge over Conrail.

Route:	Structure No.:	0900008

Project ID No.:	BHUD07

Municipality:	Jersey City

Project Start Date:

Programmed:	$103,450

Expended:	$103,450

Status:

Design contract funded with $103,450.00.  Project under design.

JFK Boulevard East

Project Description

This project will provide for the rehabilitation of a 135-foot, single-span truss bridge over cliff at the

extension of 77th Street.

Route:	Structure No.:	0900007

Project ID No.:	BHUD06

Municipality:	North Bergen Twp.

Project Start Date:

Programmed:	$82,625

Expended:	$82,625

Status:

Design contract funded with $82,625.00.  Project under design.

Kearny Avenue (Jones Memorial)

Project Description

This project will provide for the rehabilitation of a 193-foot, three-span bridge over NJ TRANSIT

Route:	Structure No.:	0900014

Project ID No.:	BHUD12

Municipality:	Kearny Town

Project Start Date:	2/22/2005

Programmed:	$47,800

Expended:	$47,800

Status:

Design cost $47,800.00

Nelson Avenue Bridge

Project Description

This project will provide for the rehabilitation of a 65-foot, single-span bridge over Secaucus Road.

Route:	Structure No.:	0900010

Project ID No.:	BHUD09

Municipality:	Jersey City	North Bergen Twp.

Project Start Date:	2/22/2005

Programmed:	$665,755

Expended:	$665,755

Status:

Construction complete.

Palisade Avenue Bridge

Project Description

This project will provide for the repair of a 35-foot, single-span bridge over New York Avenue.

Route:	Structure No.:	0900028

Project ID No.:	BHUD22

Municipality:	Jersey City

Project Start Date:

Programmed:	$19,650

Expended:	$19,650

Status:

Design contract funded with $19,650.00.  Project under design.

Park Avenue Bridge over Weehawken Branch

Project Description

This project will provide for the rehabilitation of the 848-foot, 16-span bridge over Weehawken Branch.

Route:	Structure No.:	0900001

Project ID No.:	BHUD01

Municipality:	Hoboken City	Weehawken Twp.

Project Start Date:	2/22/2005

Programmed:	$3,888,689

Expended:	$3,888,689

Status:

Construction complete.

Willow Avenue Bridge

Project Description

This project will provide for the rehabilitation of the 731-foot, 22-span bridge over Weehawken Branch,

18th and South Street.

Route:	Structure No.:	0900002

Project ID No.:	BHUD02

Municipality:	Hoboken City	Weehawken Twp.

Project Start Date:	6/16/2003

Programmed:	$5,590,731

Expended:	$5,590,731

Status:

Contruction complete.

Summary for 'COUNTY' =  Hudson (9 detail records)

Sum	Programmed:	$10,489,000.00

Expended:	$10,489,000.00

Hunterdon

Arch Street Bridge (X-12)

Project Description

This project will provide for the rehabilitation of the structure over the South Branch of the Raritan

Route:	Structure No.:	1000055

Project ID No.:	BHUN06

Municipality:	High Bridge Boro

Project Start Date:	7/1/2003

Programmed:	$1,550,000

Expended:	$1,448,321

Status:

Construction completed 6/16/06.

County Route 513 Bridge (L-4)

Project Description

This project will provide for the replacement of the structure over Little Brook.

Route:	CR 513	Structure No.:	1000005

Project ID No.:	BHUN07

Municipality:	Lebanon Twp.

Project Start Date:	7/1/2003

Programmed:	$300,000

Expended:	$300,000

Status:

Award amount was 457,551.41 (funding through BB99 and other funding).  Construction completed

County Route 609 Bridge (E-239)

Project Description

This project will provide for the replacement of the structure over the Neshanic River.

Route:	CR 609	Structure No.:	100E239

Project ID No.:	BHUN08

Municipality:	East Amwell Twp.

Project Start Date:	10/1/2001

Programmed:	$800,000

Expended:	$800,000

Status:

Construction completed 04/20/2002

County Route 614 Bridge (A-4)

Project Description

This project will provide for the replacement of the structure over the Hakihokake Creek.

Route:	CR 614	Structure No.:	100A004

Project ID No.:	BHUN01

Municipality:	Alexandria Twp.

Project Start Date:	8/1/2003

Programmed:	$360,000

Expended:	$360,000

Status:

Construction completed 9/20/05.

Everitts Road Bridge (Q-1)

Project Description

This project will provide for the replacement of the structure over the Neshanic River.

Route:	Structure No.:	10XX0Q1

Project ID No.:	BHUN03

Municipality:	Raritan Twp.

Project Start Date:	6/25/2001

Programmed:	$650,000

Expended:	$546,684

Status:

Project completed 11/5/01.

Halsted Street Bridge (N-2)

Project Description

This project will provide for the replacement of the structure over the South Branch of the Raritan River.

Route:	Structure No.:	1000097

Project ID No.:	BHUN09

Municipality:	Clinton Town

Project Start Date:	10/1/2003

Programmed:	$750,000

Expended:	$750,000

Status:

Construction completed 3/01/07.

Hamden Road Bridge (FC-62)

Project Description

This project will provide for the replacement of the structure over the South Branch of the Raritan River.

Route:	Structure No.:	10XXF62

Project ID No.:	BHUN10

Municipality:	Franklin Twp.

Project Start Date:	5/1/2003

Programmed:	$1,000,000

Expended:	$1,000,000

Status:

Construction completed 11/23/05.

Manners Road Bridge (E-240)

Project Description

This project will provide for the replacement of the structure over the Neshanic River.

Route:	Structure No.:	100E240

Project ID No.:	BHUN02

Municipality:	East Amwell Twp.

Project Start Date:	10/1/2001

Programmed:	$500,000

Expended:	$500,000

Status:

Construction completed 4/20/02.

Old York Road Bridge (R-147)

Project Description

This project will provide for the replacement of the structure over Pleasant Run.

Route:	Structure No.:	1000041

Project ID No.:	BHUN04

Municipality:	Readington Twp.

Project Start Date:	8/1/2003

Programmed:	$500,000

Expended:	$500,000

Status:

Construction completed 11/26/05.

Pottersville Road Bridge (T-61)

Project Description

This project will provide for the replacement of the structure over the Musconetcong River.

Route:	Structure No.:	10XXB26

Project ID No.:	BHUN11

Municipality:	Bethlehem Twp.	Franklin Twp.

Project Start Date:	4/1/2004

Programmed:	$600,000

Expended:	$600,000

Status:

4/06 awarded

Rocktown-Lambertville Road Bridge (W-45)

Project Description

This project will provide for the replacement of the structure over Swan Creek.

Route:	Structure No.:	1000049

Project ID No.:	BHUN05

Municipality:	West Amwell Twp.

Project Start Date:	4/3/2002

Programmed:	$729,000

Expended:	$352,007

Status:

Construction completed 07/25/2002

Summary for 'COUNTY' =  Hunterdon (11 detail records)

Sum	Programmed:	$7,739,000.00

Expended:	$7,157,011.68

Mercer

Alexander Road Bridge

Project Description

This project will address the replacement of the Alexander Road Bridge over Amtrak.  The overall

condition of this structure is listed as critical.  The bridge is structurally deficient with a sufficiency rating

of 3.3 and has deterioriated to the point that it requires replacement.

Route:	Structure No.:	1149173

Project ID No.:	BMER06

Municipality:	West Windsor Twp.

Project Start Date:	2/1/2002

Programmed:	$1,600,000

Expended:	$1,600,000

Status:

This project has been awarded for construction.  NJDOT is completing the project.

Bear Tavern Road Bridge

Project Description

This project will provide for the replacement of the structure over Jacob Creek at the same location.

The existing steel truss with timber deck structure is 75 feet long and 17 feet wide.

Route:	Structure No.:	11000060

Project ID No.:	BMER01

Municipality:	Hopewell Twp.

Project Start Date:

Programmed:	$1,000,000

Expended:	$0

Status:

No status has been provided by the county.

Mercer County Bridge Bond Projects

Project Description

Mercer County has submitted a partial list of bridges for their $10.57 million allocation.  This record

represents the balance of Bridge Bond funds available for allocation in Mercer County.

Route:	Structure No.:	N/A

Project ID No.:	BMER05

Municipality:	Various

Project Start Date:

Programmed:	$1,800,000

Expended:	$0

Status:

Nottingham Way Bridge

Project Description

This project will provide for the replacement of the existing structure over the Assunpink Creek on the

same alignment.  The existing steel girder structure is 81 feet long and 49 feet wide.

Route:	Structure No.:	1100057

Project ID No.:	BMER02

Municipality:	Hamilton Twp.	Trenton City

Project Start Date:

Programmed:	$1,700,000

Expended:	$206,153

Status:

No updated status has been provided by the county.

Quakerbridge Road Bridge

Project Description

This project will provide for the replacement of the structure over the Assunpink Creek at the same

location.  The existing reinforced concrete slab structure is 80 feet long and 50 feet wide.

Route:	Structure No.:	1100016

Project ID No.:	BMER04

Municipality:	Hamilton Twp.	Lawrence Twp.

Project Start Date:

Programmed:	$2,670,000

Expended:	$175,025

Status:

No updated status has been provided by the county.

Wall Street Bridge

Project Description

This project will provide for the replacement of the existing structure over the Assunpink Creek at the

same location.  The existing steel with concrete deck structure is 84 feet long and 60 feet wide.

Route:	Structure No.:	1100058

Project ID No.:	BMER03

Municipality:	Trenton City

Project Start Date:

Programmed:	$1,800,000

Expended:	$79,491

Status:

No updated status has been provided by the county.

Summary for 'COUNTY' =  Mercer (6 detail records)

Sum	Programmed:	$10,570,000.00

Expended:	$2,060,669.00

Middlesex

Behmer Road Bridge

Project Description

This project will provide for the replacement of the single-span structure over Ambrose Brook.

Route:	Structure No.:	122B133

Project ID No.:	BMID04

Municipality:	Piscataway Twp.

Project Start Date:	2/1/2001

Programmed:	$1,250,000

Expended:	$419,000

Status:

County soliciting new consulting engineering services due to SHPO requirements. Construction award

targeted for 2008

Davidson's Mill Road Bridge

Project Description

This project will provide for the replacement of the single-span structure over Oakley's Brook.

Route:	Structure No.:	124B034

Project ID No.:	BMID02

Municipality:	South Brunswick Twp.

Project Start Date:	2/1/2001

Programmed:	$1,477,342

Expended:	$1,477,342

Status:

Construction completed and final inspection held. Project close-out is proceeding.

New Brunswick Avenue Bridge

Project Description

This project will provide for the replacement of the single-span structure over Bound Brook.

Route:	Structure No.:	122B093

Project ID No.:	BMID01

Municipality:	Piscataway Twp.	South Plainfield Boro

Project Start Date:	3/1/2001

Programmed:	$2,500,000

Expended:	$435,000

Status:

The project will include design ($600,000) and construction ($1,900,000).  The design contract was

awarded to Richard A. Alaimo Associates in the amount of $435,000. County working to resolve issues

with CONRAIL. Design on hold until this matter resolved.

Park Avenue Bridge over Conrail

Project Description

This project will provide for the replacement of the three-span structure over CONRAIL (AKA Lehigh

Valley Main Line).

Route:	Structure No.:	1253163

Project ID No.:	BMID03

Municipality:	South Plainfield Boro

Project Start Date:	12/21/2000

Programmed:	$3,534,658

Expended:	$1,052,500

Status:

Funding will be provided for construction.The design contract was awarded to Maser Consulting in the

amount of $1,052,530.  CONRAIL issues delaying completion of design phase. Construction award

Spotswood-Gravel Hill Road Bridge

Project Description

This project will provide for the replacement of the two-span bridge over Manalapan Brook.

Route:	Structure No.:	125B083

Project ID No.:	BMID06

Municipality:	Monroe Twp.

Project Start Date:	1/18/2001

Programmed:	$1,250,000

Expended:	$321,501

Status:

Funding will be provided for design ($325,000) and construction ($925,000). The design contract was

awarded to Schoor DePalma in the amount of $321,501.

Wedgewood Avenue Bridge

Project Description

This project will provide for the replacement of the single cell, reinforced concrete box culverts over

Wedgewood Brook.

Route:	Structure No.:	121B019

Project ID No.:	BMID05

Municipality:	Woodbridge Twp.

Project Start Date:	2/1/2001

Programmed:	$1,000,000

Expended:	$368,000

Status:

Funding will be provided for design ($375,000) and construction ($625,000).  The design contract was

awarded to Frederic R. Harris, Inc. in the amount of $368,000.

Summary for 'COUNTY' =  Middlesex (6 detail records)

Sum	Programmed:	$11,012,000.00

Expended:	$4,073,342.67

Monmouth

Atlantic Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Troutmans Creek.

Route:	CR  29	Structure No.:	1300O35

Project ID No.:	BMON10

Municipality:	Long Branch City

Project Start Date:	8/10/2000

Programmed:	$2,690,513

Expended:	$2,609,513

Status:

The design contract was awarded 8-10-00.Construction contract awarded on  3/4/05. Construction

complete and County pursuing project closeout.

Brighton Avenue Bridge

Project Description

This project will provide for the replacement of the structure over the Shark River.

Route:	Structure No.:	1300W35

Project ID No.:	BMON06

Municipality:	Neptune Twp.	Wall Twp.

Project Start Date:	5/9/2001

Programmed:	$3,536,096

Expended:	$3,536,096

Status:

The design contract was awarded on 4-12-01to HNTB Corporation.Construction completed.

Georgia Road Bridge

Project Description

This project will provide for the replacement of the structure over Manasquan River.

Route:	Structure No.:	1300F45

Project ID No.:	BMON13

Municipality:	Freehold Twp.

Project Start Date:	4/13/2000

Programmed:	$869,416

Expended:	$869,416

Status:

Project built and open to traffic. County pursuing project closeout.

Iron Ore Road Bridge

Project Description

This project will provide for the replacement of the structure over Manalapan Brook.

Route:	CR 527A	Structure No.:	130MN29

Project ID No.:	BMON01

Municipality:	Manalapan Twp.

Project Start Date:	2/22/2001

Programmed:	$263,830

Expended:	$261,177

Status:

The design contract was awarded to Bay Pointe Engineering,( now Schoor DePalma), in the amount of

$198,930. Construction awarded targeted for june 2007. County decreased total bridge bond funding and

will use other source of funds for construction.

Lakewood-Farmingdale Road Bridge

Project Description

This project will provide for the replacement of the structure over Hay Stack Brook.

Route:	CR 547	Structure No.:	130HL53

Project ID No.:	BMON14

Municipality:	Howell Twp.

Project Start Date:	4/13/2000

Programmed:	$1,188,928

Expended:	$1,188,928

Status:

Project built and open to traffic. County pursuing project closeout.

Main Street Bridge over Deal Lake

Project Description

This project will provide for the replacement of the structure over Deal Lake.

Route:	Structure No.:	1300O11

Project ID No.:	BMON07

Municipality:	Interlaken Boro	Loch Arbour Village

Project Start Date:	4/12/2001

Programmed:	$297,460

Expended:	$280,800

Status:

The design contract was awarded to HNTB Corporation on 4/12/01.Construction award targeted for July

2007. To be funded from other sources.

Main Street Bridge over Pemberton Creek

Project Description

This project will provide for the replacement of the structure over Pemberton Creek.

Route:	Structure No.:	1300E14

Project ID No.:	BMON04

Municipality:	Oceanport Boro

Project Start Date:	3/22/2001

Programmed:	$2,942,080

Expended:	$2,942,080

Status:

The design contract was awarded to Greenman-Pedersen Inc. in the amount of $273,541. The County

awarded a construction contract in the amount of $ 2,737,112.00 to Marbro, Inc. on 7/10/03. Project

Monmouth Road Bridge

Project Description

This project will provide for the replacement of the structure over Deal Lake.

Route:	CR  15	Structure No.:	1300O13

Project ID No.:	BMON11

Municipality:	Interlaken Boro	Ocean Twp.

Project Start Date:	8/13/1998

Programmed:	$2,314,656

Expended:	$2,314,656

Status:

The design contract was awarded 8/13/98;  The County awarded a construction contract in the amount of

$ 2,051,117.00 on 1/23/03 to Marbro, Inc. Construction completed and County pursuing project closeout

Patten Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Manahasset Creek.

Route:	Structure No.:	1300O40

Project ID No.:	BMON03

Municipality:	Long Branch City	Monmouth Beach Boro

Project Start Date:	4/26/2001

Programmed:	$4,960,056

Expended:	$4,960,056

Status:

The design contract was awarded 12/21/00.  Design is funded from non-Bridge Bond sources. The design

phase is 100% complete. County expended $ 34,287.50 for ROW. Project construction completed and

close-out is underway.

Seven Bridges Road Bridge

Project Description

This project will provide for the replacement of the structure over Silver Creek.

Route:	CR  33	Structure No.:	1300S27

Project ID No.:	BMON02

Municipality:	Little Silver Boro

Project Start Date:	3/8/2001

Programmed:	$240,618

Expended:	$240,316

Status:

The design contract was awarded to Greenman-Pedersen Inc. in the amount of $240,618.  The design

phase is 100% complete. Construction award is targeted for December  2007.County to use other source

of funds for construction.

Stone Road Bridge

Project Description

This project will provide for the replacement of the structure over Chingarora Creek.

Route:	CR   6	Structure No.:	13000R4

Project ID No.:	BMON08

Municipality:	Keyport Boro	Union Beach Boro

Project Start Date:	3/8/2001

Programmed:	$2,821,416

Expended:	$2,591,801

Status:

The design contract was awarded to Parsons-Brinkerhoff. Construction award on August 24, 2006.

Construction contract combined with Bridge R-7 and completion anticipated 9/2007

Tinton Avenue Bridge

Project Description

This project will provide for the replacement of the structure over NJ TRANSIT.

Route:	CR 537	Structure No.:	1300E24

Project ID No.:	BMON12

Municipality:	Eatontown Boro

Project Start Date:	11/10/1999

Programmed:	$55,236

Expended:	$55,236

Status:

The design contract was awarded on 11/10/99.  County now using 55,236.00 of 1999 Bridge Bd for

design. Construction award targeted for October 2008 using other funding sources.

Union Avenue Bridge over Flat Creek

Project Description

This project will provide for the replacement of the structure over Flat Creek.

Route:	CR  39	Structure No.:	13000R7

Project ID No.:	BMON09

Municipality:	Union Beach Boro

Project Start Date:	3/22/2001

Programmed:	$1,825,000

Expended:	$318,276

Status:

The design contract was awarded to Parsons-Brinkerhoff. Construction award on August 24,2006.

Contract combined with Bridge R-4. Completion anticipated 9/2007

Water Street Bridge

Project Description

This project will provide for the replacement of the structure over Weamaconk Creek.

Route:	CR 522	Structure No.:	130MN30

Project ID No.:	BMON05

Municipality:	Englishtown Boro

Project Start Date:	4/12/2001

Programmed:	$994,695

Expended:	$649,703

Status:

The design contract was awarded on 4/12/01 to Greenman-Pedersen, Inc..Construction award is targeted

for June 2007. County to use other sources of funds for construction. Funds expended to date are for

design, right-of-way and permits .

Summary for 'COUNTY' =  Monmouth (14 detail records)

Sum	Programmed:	$25,000,000.00

Expended:	$22,818,054.50

Morris

Mosele Road Bridge

Project Description

This project will provide for the replacement of the bridge (Bridge No. 636) over the North Branch of

the Raritan River.

Route:	Structure No.:	1400636

Project ID No.:	BMOR08

Municipality:	Mendham Twp.

Project Start Date:	6/12/2002

Programmed:	$1,685,000

Expended:	$1,685,000

Status:

Construction complete

Mount Vernon Avenue Bridge

Project Description

This project will provide for the replacement of the bridge (Bridge No. 520) over the Passaic River.

Route:	Structure No.:	1400520

Project ID No.:	BMOR05

Municipality:	Chatham Twp.	Summit City

Project Start Date:	11/28/2001

Programmed:	$952,000

Expended:	$952,000

Status:

Construction complete

Passaic Avenue Bridge over Passaic River

Project Description

This project will provide for the replacement of the bridge (Bridge No. 461) over the Passaic River.

Route:	Structure No.:	070M065

Project ID No.:	BMOR03

Municipality:	Florham Park Boro	Millburn Twp.

Project Start Date:	5/27/1998

Programmed:	$1,200,000

Expended:	$1,200,000

Status:

Project commencement date July 5, 2006. 96.50% completed. Stage 2 construction underway

Paterson Hamburg Turnpike Bridge

Project Description

This project will provide for the replacement of the Paterson Hamburg Turnpike Bridge (Bridge No. 140)

over the Pequannock River.

Route:	Structure No.:	1400140

Project ID No.:	BMOR12

Municipality:	Butler Boro	West Milford Twp.

Project Start Date:	1/9/2002

Programmed:	$970,000

Expended:	$286,739

Status:

Under design. Design funded with BB funds. ROW acquisition in progress. Construction to start Summer

South Beverwyck Road Bridge

Project Description

This project will provide for the replacement of the bridge over Troy Brook (Bridge No. 417).

Route:	Structure No.:	1400417

Project ID No.:	BMOR02

Municipality:	Parsippany-Troy Hills Twp

Project Start Date:	4/14/1997

Programmed:	$750,000

Expended:	$750,000

Status:

Construction complete

Stephensburg Road Bridge

Project Description

This project will provide for the replacement of the bridge (Bridge No. 1191) over Stephensburg Brook.

Route:	Structure No.:	1401191

Project ID No.:	BMOR10

Municipality:	Washington Twp.

Project Start Date:	8/14/2002

Programmed:	$575,000

Expended:	$113,530

Status:

Under design. Design funded with 1999 Bridge Bond funds.  Construction anticipated Spring 2008.

Stone House Road Bridge

Project Description

This project will provide for the replacement of the bridge (Bridge No. 540) over the Passaic River.

Route:	Structure No.:	1400540

Project ID No.:	BMOR06

Municipality:	Long Hill Twp.	Bernards Twp.

Project Start Date:	6/25/2003

Programmed:	$830,000

Expended:	$54,112

Status:

Under design. Design funded with 1999 Bridge Bond funds.  Construction anticipated Spring 2008.

Tingley Road Bridge

Project Description

This project will provide for the replacement of the bridge (Bridge No. 669) over a Tributary of the

Whippany River.

Route:	Structure No.:	1400669

Project ID No.:	BMOR09

Municipality:	Mendham Twp.

Project Start Date:	5/22/2002

Programmed:	$600,000

Expended:	$180,107

Status:

Under design. Design funded with 1999 Bridge Bond funds.  Construction anticipated 07/2007.

Watchung Avenue/River Road Bridge (See also Union Cty.

portion)

Project Description

This project will provide for the replacement of the bridge (Bridge No. 515) over the Passaic River.

Route:	Structure No.:	1400515

Project ID No.:	BMOR01A

Municipality:	Chatham Boro	Summit City

Project Start Date:	9/1/2001

Programmed:	$1,250,000

Expended:	$1,250,000

Status:

Design funded with 1999 Bridge Bond funds.  Construction funded with 1999 Bridge Bond funds.  Bridge

construction complete.

West Valley Brook Road Bridge

Project Description

This project will provide for the replacement of the bridge (Bridge No. 1268) over the South Branch of

the Raritan River.

Route:	Structure No.:	1401268

Project ID No.:	BMOR11

Municipality:	Washington Twp.

Project Start Date:	12/23/2002

Programmed:	$850,000

Expended:	$73,310

Status:

Under design. Design funded with 1999 Bridge Bond funds.  Construction anticipated 07/2008

Whitebridge Road Bridge

Project Description

This project will provide for the replacement of the bridge (Bridge No. 563) over the Passaic River.

Route:	Structure No.:	1400563

Project ID No.:	BMOR07

Municipality:	Long Hill Twp.	Bernards Twp.

Project Start Date:	10/22/2003

Programmed:	$500,000

Expended:	$113,659

Status:

Under Design. Design funded with 1999 Bridge Bond funds.  Construction anticipated 07/2008

Summary for 'COUNTY' =  Morris (11 detail records)

Sum	Programmed:	$10,162,000.00

Expended:	$6,658,457.35

NJ DOT

Airport Safety Fund

Project Description

This is an ongoing program of safety and other improvements at New Jersey's public-use airports.

Route:	Structure No.:	N/A

Project ID No.:	X02

Municipality:	Various

Project Start Date:

Programmed:	$5,000,000

Expended:	$4,639,431

Status:

Betterments, Bridge Preservation

Project Description

This is an ongoing program of minor improvements to the state highway system, for bridge maintenance

repair contracts, repair parts, and miscellaneous needs for emergent projects.

Route:	Structure No.:	N/A

Project ID No.:	X72A

Municipality:	Various

Project Start Date:

Programmed:	$10,959,068

Expended:	$10,842,517

Status:

Betterments, Roadway Preservation

Project Description

This is an ongoing program of minor improvements to the state highway system, for miscellaneous

maintenance repair contracts, repair parts, miscellaneous needs for emergent projects, handicap ramps,

and drainage rehabilitation/maintenance.

Route:	Structure No.:	N/A

Project ID No.:	X72B

Municipality:	Various

Project Start Date:

Programmed:	$6,700,540

Expended:	$6,681,266

Status:

Betterments, Safety

Project Description

This is an ongoing program of minor improvements to the state highway system such as beam guide rail

and impact attenuators, as well as safety fencing.

Route:	Structure No.:	N/A

Project ID No.:	X72C

Municipality:	Various

Project Start Date:

Programmed:	$5,015,177

Expended:	$4,721,048

Status:

Bicycle Projects, Local System

Project Description

This program will address locally initiated bicycle accommodation projects.

Route:	Structure No.:	N/A

Project ID No.:	99357

Municipality:	Various

Project Start Date:

Programmed:	$5,000,000

Expended:	$5,000,000

Status:

Bridge Maintenance, Movable Bridges

Project Description

This program will provide funding for minor improvements, repair, and preventive maintenance by

NJDOT maintenance crews for drawbridges on the state highway system.  Improvements may include

lubrication of drawbridges, diesel engine maintenance, and system repairs.

Route:	Structure No.:	N/A

Project ID No.:	98318

Municipality:	Various

Project Start Date:

Programmed:	$727,504

Expended:	$727,504

Status:

Bridge, Emergency Repair

Project Description

This program will allow NJDOT  to obtain emergency, technical consultant assistance for inspection and

repair design when the safety of a bridge(s) is compromised due to a collision or flood damage, etc.  These

consultants will be available to assist Department personnel on an as-needed basis.

Route:	Structure No.:	N/A

Project ID No.:	98315

Municipality:	Various

Project Start Date:

Programmed:	$13,831,864

Expended:	$13,684,134

Status:

Construction Inspection

Project Description

In order to provide for inspection of construction projects on an as-and-where-needed basis, the

Department has provided term agreements, lasting one year, for inspection of projects when and where

needed.  This service will also include out-of-state materials plant inspection of structural steel and pre-

Route:	Structure No.:	N/A

Project ID No.:	X180

Municipality:	Various

Project Start Date:

Programmed:	$1,000,000

Expended:	$900,000

Status:

Culvert Inspection Program

Project Description

This program will provide for the inspection of state-owned highway bridges less that 20 feet.

Route:	Structure No.:	N/A

Project ID No.:	99322

Municipality:	Various

Project Start Date:

Programmed:	$200,000

Expended:	$200,000

Status:

Design, Emerging Projects

Project Description

This program will provide initial funding for task order agreements as well as projects emerging from the

Scoping Work Program.  Funding is also provided for advance design services which include, but are not

limited to, the following functions--development of base plan for final design; location of existing

features within footprints, such as utilities and drainage; geotechnical work, specifically soil borings;

administrative work needed to set budgets and manpower for right of way acquisition.

Route:	Structure No.:	N/A

Project ID No.:	X106

Municipality:	Various

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

$1,000,000 transferred to Resurfacing Program.

Doremus Avenue Bridge

Project Description

The existing structure which carries two 12-foot travel lanes with no shoulders will be replaced with a new

structure that will carry four 12-foot travel lanes and two 8-foot shoulders.  This project is a part of

Phase I of Portway, New Jersey's Intermodal Connection to World Trade.

Route:	Structure No.:	0751160

Project ID No.:	L020

Municipality:	Newark City

Project Start Date:

Programmed:	$24,800,000

Expended:	$23,529,064

Status:

Drainage Rehabilitation and Maintenance, State

Project Description

This program will provide for the rehabilitation and maintenance of state highway drainage systems,

which may include drainage clean out, removal and disposal of material, sweeping, video inspection, salary

costs, and acquisition and maintenance of specialized equipment.

Route:	Structure No.:	N/A

Project ID No.:	X154

Municipality:	Various

Project Start Date:

Programmed:	$3,310,795

Expended:	$3,309,165

Status:

Economic Development

Project Description

This program will provide assistance to counties and/or municipalities for Economic Development

Authority projects, as well as provide funding for Public/Private Partnerships.

Route:	Structure No.:	N/A

Project ID No.:	X186A

Municipality:	Various

Project Start Date:

Programmed:	$5,400,000

Expended:	$3,400,000

Status:

$400,000 was transferred from the Route 33 Business, Howell Road project.

Electrical Facilities

Project Description

This program will provide for the replacement, repair, preservation, and installation of electrical facilities

along the state highway system.  Included in this program is highway lighting, sign lighting, cathodic

protection for bridges, road weather information systems, traffic counting/monitoring sites, and

Route:	Structure No.:	N/A

Project ID No.:	X241

Municipality:	Various

Project Start Date:

Programmed:	$800,000

Expended:	$798,985

Status:

Environmental Investigations

Project Description

This program will provide funding for environmental assessment work products provided on a quick-

response basis through specialized, task order, consultant agreements in such areas as ecology permits,

wetlands delineation and mitigation monitoring, hazardous waste investigations, cultural resource

investigations and mitigation, and NEPA and Section 4(f) documentation.  Funding is also provided for

environmental permit fees, laboratory fees, and other environmental consultant agreements requiring

Route:	Structure No.:	N/A

Project ID No.:	X75

Municipality:	Various

Project Start Date:

Programmed:	$451,790

Expended:	$228,884

Status:

Freight Program

Project Description

This program will provide for the rehabilitation and improvement of key elements of the State's freight

network, including acquisition, rehabilitation, facility construction, and substitute service assistance under

the State Freight Assistance Program, matching of federal funds, and participation in other projects and

programs for improvement of the intermodal goods movement network and support of economic

Route:	Structure No.:	N/A

Project ID No.:	X34

Municipality:	Various

Project Start Date:

Programmed:	$14,386,633

Expended:	$13,097,803

Status:

The program was originally programmed for $9,100,000; $5,286,633 is being transferred from the Route

130, Burlington County Access Improvements; Route 130, Westfield; Route 1 Meadow Road and the

Doremus Avenue projects.

Good Neighbor Landscaping

Project Description

This program will provide funding for open-ended landscaping contracts to permit the Department to

address landscaping needs on a timely basis, or install functional plantings and landscape elements to

minimize adverse effects of the highway where engineering solutions are prohibitive.

Route:	Structure No.:	N/A

Project ID No.:	X200A

Municipality:	Various

Project Start Date:

Programmed:	$500,000

Expended:	$500,000

Status:

North Avenue Bridges, Phase 3

Project Description

This project will address the widening of eastbound bridges on North Avenue as part of a cost-sharing

agreement with the Port Authority of New York and New Jersey.

Route:	Structure No.:	3800070

Project ID No.:	00309

Municipality:	Elizabeth City

Project Start Date:

Programmed:	$3,500,000

Expended:	$3,500,000

Status:

The Bond funding represents NJDOT portion of cost-sharing agreement on this project.  The Port

Authority of NY & NJ is the lead for the project.

Orphan Bridge Emergency Repairs

Project Description

This program will provide funding for emergency repairs to orphan bridges over railroads which are

identified during ongoing bridge inspections.  These repairs will be accomplished by a DOT contractor

through work orders as priority situations are identified.

Route:	Structure No.:	N/A

Project ID No.:	99372

Municipality:	Various

Project Start Date:

Programmed:	$918,136

Expended:	$907,858

Status:

Of the original amount programmed, $750,000 was transferred to Betterments, Bridge and $3,031,864

was transferred to Bridge Emergency Repairs.

Pedestrian Projects, Local System

Project Description

This program will address locally initiated pedestrian access and safety projects.

Route:	Structure No.:	N/A

Project ID No.:	99358

Municipality:	Various

Project Start Date:

Programmed:	$4,000,000

Expended:	$3,534,989

Status:

Planning and Research, State

Project Description

This program will provide for planning activities which include needs assessments, geometric deficiencies,

local aid assistance, congestion management, travel market analysis, formulation of a new statewide plan,

facilitating/implementing intermodalism, demographics, access management plans, transportation policy,

equipment, modelling, clean air initiatives, data collection equipment, deployment of new technology

initiatives, and research initiatives.

Route:	Structure No.:	N/A

Project ID No.:	X140

Municipality:	Various

Project Start Date:

Programmed:	$2,000,000

Expended:	$1,880,358

Status:

Project Development, Preliminary Engineering

Project Description

This program will provide funding for Feasibility Assessment work on various identified needs on the state

transportation system.  Functions to be performed include, but are not limited to, determination of

whether concept submitted with a Problem Statement can feasibly evolve into a project in light of

environmental and community constraints and issues.  Feasibility Assessment can also include

environmental analysis to determine the environmental constraints in a project area, and community

Route:	Structure No.:	N/A

Project ID No.:	X32

Municipality:	Various

Project Start Date:

Programmed:	$2,925,000

Expended:	$2,925,000

Status:

Resurfacing Program, State

Project Description

This is a systemwide program to improve state highways through the application of a new surface course

and minor safety improvements to highway segments identified by the NJDOT Pavement Management

Route:	Structure No.:	N/A

Project ID No.:	X03D

Municipality:	Various

Project Start Date:

Programmed:	$37,701,822

Expended:	$37,579,924

Status:

Route   1&9T, Hackensack River Bridge

Project Description

This project will provide for emergency repairs to the structure to keep it in service.

Route:	Structure No.:	0905152

Project ID No.:	98382

Municipality:	Kearny Town

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

Route   1, Meadow Road

Project Description

Construction of a full grade-separated interchange at Meadow Road will include new ramps, a

collector/distributor roadway, realignment of existing ramps, and new highway lighting installation.

Route:	  1	Structure No.:	N/A

Project ID No.:	97110

Municipality:	West Windsor Twp.

Project Start Date:	6/26/2000

Programmed:	$10,307,378

Expended:	$10,307,378

Status:

This project has been opened to traffic.  The balance of $292,622 was transferred to the Freight line

Route  28, Bridgewater Twp., Drainage

Project Description

This project will address an identified drainage problem on westbound Route 28 which causes flooding

during moderate rainfalls.  Conditions noted include a pavement depression that causes ponding up to the

centerline of the roadway; runoff from local businesses onto the roadway; inlets that are partially clogged

Route:	 28	Structure No.:	N/A

Project ID No.:	96026

Municipality:	Bridgewater Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

The original amount programmed ($290,000) has been transferred to the Freight Program.

Route  28, Somerset County Resurfacing

Project Description

This project will include resurfacing, minor intersection improvements, and other minor improvements in

support of Somerset County's regional center transportation plan.

Route:	 28	Structure No.:	N/A

Project ID No.:	99371

Municipality:	Raritan Boro	Bridgewater Twp.

Somerville Boro

Project Start Date:

Programmed:	$3,500,000

Expended:	$902,487

Status:

Route  33 Business, Howell Road

Project Description

The proposed improvements will include exclusive left-turn lanes for each approach and also exclusive

right-turn lanes for the Route 33 approaches.  The Oakerson Road terminus will be relocated to the west

by approximately 460 feet.

Route:	 33 Bus.	Structure No.:	N/A

Project ID No.:	174D

Municipality:	Howell Twp.

Project Start Date:

Programmed:	$837,516

Expended:	$837,516

Status:

This represents cost for right of way acquisition.  $400,000 was transferred to the Economic

Development line item.

Route  33 Business, Route 79 (South Street)

Project Description

The proposed improvements will include exclusive left-turn lanes for the Route 79 approaches.

Route:	 33 Bus.	Structure No.:	1332150

Project ID No.:	174C

Municipality:	Freehold Boro

Project Start Date:

Programmed:	$150,000

Expended:	$150,000

Status:

This represents cost for right of way acquisition on this project.

Route  46 (43)

Project Description

This project will include signing upgrades, installation of new lighting, geometric improvements, new

guide rail installation, roadway resurfacing, bridge deck replacements, and acceleration/deceleration lane

construction.

Route:	 46	Structure No.:	Various

Project ID No.:	9116

Municipality:	Wayne Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

Route  47, Main Street

Project Description

This project will address intersection improvements at Route 47 and Main Street (CR 610), including left-

turn slots, center-turn lane, new traffic signals, and restriping.

Route:	 47	Structure No.:	N/A

Project ID No.:	2149C

Municipality:	Dennis Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

The original amount programmed ($750,000) has been transferred to the Freight Program.

Route  73, Edgewood Avenue, Drainage

Project Description

This project will address an identified drainage problem that results in flooding on the northbound side of

Route 73.  Conditions noted include an outfall pipe which is partially buried, as well as the grass berm

adjacent to the outside shoulder which restricts water from flowing downstream into the existing ditch.

Route:	 73	Structure No.:	N/A

Project ID No.:	96000

Municipality:	Berlin Twp.

Project Start Date:

Programmed:	$0

Expended:	$0

Status:

Of the original amount programmed ($100,000), $60,000 was transferred to the Freight Program and

$40,000 was transferred to Betterments, Bridge.

Route 130, Burlington County Access Improvements

Project Description

This project will provide for construction of access improvements on  Route 130 along with associated

roadway improvements to serve a station and park and ride on the SNJLRTS as well as the Food

Route:	130	Structure No.:	N/A

Project ID No.:	891

Municipality:	Burlington Twp.	Florence Twp.

Project Start Date:

Programmed:	$879,052

Expended:	$879,052

Status:

Of the original $5,000,000 programmed, the balance of $4,120,948 was transferred to the Freight line

Route 130, Westfield Avenue/Pochack Creek, Drainage

Project Description

This project will provide for drainage improvements along Route 130 and Westfield Avenue.  Flooding

occurs approximately three to five times a year along Pochack Creek, often resulting in the closure of

Route 130.  Drainage basins will be constructed along Pochack Creek, upstream and downstream of Route

130.  The project begins at Walnut Avenue and continues downstream to Route 90.  A culvert will be

constructed to allow excess stormwater to bypass an industrial park, Route 130, and an adjoining

cemetery.  The existing creek flows through the Crescent Burial Park and causes extensive flooding; a

basin within the cemetery will reduce the flooding in the cemetery.  No disturbance of graves is

Route:	130	Structure No.:	0422155

Project ID No.:	9303

Municipality:	Pennsauken Twp.

Project Start Date:

Programmed:	$34,315

Expended:	$34,315

Status:

1-15-03 This project was withdrawn due to lack of community support for the project.  Of the original

$1,200,000 programmed, the balance of $1,165,685 was transferred to the Freight line item.

Sign Structure Inspection

Project Description

This program will provide for the inspection of overhead and cantilever sign structures on state roadways.

The latest inventory indicates there are over 1175 sign structures, including overhead, cantilever, and

variable sign message (VMS) structures, on state routes.  There have been several near failures of these

Route:	Structure No.:	N/A

Project ID No.:	X239

Municipality:	Various

Project Start Date:

Programmed:	$1,000,000

Expended:	$985,962

Status:

Signs Program, Statewide

Project Description

This program will provide for the systematic upgrade of state highway signs, including refurbishing of

deteriorated signs, installation of new signs, and improvement and updating of messages.

Route:	Structure No.:	N/A

Project ID No.:	X39

Municipality:	Various

Project Start Date:

Programmed:	$1,000,000

Expended:	$985,707

Status:

Traffic Signal Replacement

Project Description

This program will provide for the purchase of materials and installation of new and upgraded traffic

signals statewide and related improvements to the operation of signals.

Route:	Structure No.:	N/A

Project ID No.:	X47

Municipality:	Various

Project Start Date:

Programmed:	$3,163,410

Expended:	$3,151,973

Status:

Summary for 'COUNTY' =  NJ DOT (37 detail records)

Sum	Programmed:	$170,000,000.00

Expended:	$160,822,320.00

Page 13

NJ TRANSIT

Bergen Tunnel

Project Description

This project will provide for the rehabilitation and waterproofing of the 124 year old north tube of the

Bergen Tunnel on the Morris & Essex Lines to replace brick liner and install new lighting, ventilation and

emergency egress in anticipation of increased train traffic as a result of the Secaucus Transfer Station.

Route:	Structure No.:	N/A

Project ID No.:	BNJT01

Municipality:	Jersey City

Project Start Date:	4/1/2001

Programmed:	$32,488,515

Expended:	$32,488,515

Status:

Construction is underway; work is progressing.

Hoboken Yard "B"

Project Description

This project will provide for the expansion of the train storage yard serving Hoboken Terminal to

accommodate increased storage (from 42 to 56 train sets) which will be needed to provide additional rail

service when the Secaucus Transfer Station is opened.  The project includes construction of two bridges

Route:	Structure No.:	N/A

Project ID No.:	T82

Municipality:	Hoboken City

Project Start Date:	3/1/2001

Programmed:	$24,721,118

Expended:	$24,721,118

Status:

Union Station, Raritan Valley Line

Project Description

This project will provide for construction of a new station complex, including commuter parking for 484

vehicles, on the Raritan Valley Line.  The project includes construction of a bridge for the railroad tracks

over Morris Avenue.

Route:	Structure No.:	N/A

Project ID No.:	BNJT02

Municipality:	Union Twp.

Project Start Date:	2/1/2000

Programmed:	$22,790,367

Expended:	$22,790,367

Status:

Bridge construction is complete; construction of station, parking lot and access drive ongoing.

Summary for 'COUNTY' =  NJ TRANSIT (3 detail records)

Sum	Programmed:	$80,000,000.00

Expended:	$80,000,000.00

Ocean

Allen's Bridge

Project Description

This project will provide for the replacement of the arch bridge and roadway approaches over the Toms

Route:	CR 528	Structure No.:	1511015

Project ID No.:	BOCE02

Municipality:	Jackson Twp.

Project Start Date:	8/26/2003

Programmed:	$1,614,696

Expended:	$1,614,696

Status:

County awarded a construction contract in the amount of $ 1,448,665.50 to Cruz Construction

Corporation on 8/6/03. Contract used $ 19,993.55 for 1999 Bridge Bond funds for design contract with

DMJM /Harris. Construction completion 10/25/04.

County Route 537 over Crosswicks Creek

Project Description

This project will provide for the construction of a new structure in the same location.  The existing

structure is a seven-span timber structure.  The new structure will be prestressed concrete beam on

Route:	CR 537	Structure No.:	1523001

Project ID No.:	BOCE04

Municipality:	Plumsted Twp.

Project Start Date:	11/15/2004

Programmed:	$2,393,760

Expended:	$2,393,760

Status:

Construction of project completed and open to traffic. County pursuing project close-out.

County Route 547 (AKA Whites Bridge) over main branch of the

Toms River

Project Description

This project will provide for a new structure to be constructed at the same location.  The existing three-

span structure will be replaced with prestressed concrete beams on treated timber piles.

Route:	CR 547	Structure No.:	1511028

Project ID No.:	BOCE05

Municipality:	Jackson Twp.

Project Start Date:	6/18/2003

Programmed:	$1,189,570

Expended:	$1,189,570

Status:

Design of the project is completed It was funded from non-bridge source, ( $ 192,000.00) County awarded

a construction contract on 6/18/03 to Agate Construction in the amount of $

1,105,445.00.Construction completed 7/7/04

Great Bay Boulevard Bridge #1 over Little Sheepshead Creek

Project Description

This project will provide for repairs to the existing structure over Little Sheepshead Creek.  Repairs will

include strengthening of timber bearing piles, soil anchors, bulkhead replacement, beam guide rail, slope

stabilization, and approach roadway paving.

Route:	Structure No.:	1516001

Project ID No.:	BOCE01

Municipality:	Little Egg Harbor Twp.

Project Start Date:	8/15/2002

Programmed:	$100,933

Expended:	$100,933

Status:

County awarded construction contract in amount of $212,180.00 to Sparks Contractors, Inc. on July 2,

2002.  The County used $104,000 of 1983/1989 Bridge Bond balances to fund the construction phase.

The remainder will be from the FY 1999 Local Bridge Bond Act.

Mantoloking Bridge

Project Description

The Mantoloking Bridge carries CR 528 over Barnegat Bay; the project will extend from 600 feet west of

the westerly shoreline to 400 feet east of the easterly shoreline.  The bridge provides access to northern

Ocean County beach communities and is an escape route in the event of coastal storms. The structure will

be replaced; the movable span will be replaced with a double-leaf bascule structure with a vertical

clearance in the closed position of 29 feet and a horizontal clearance of 80 feet.  The roadway width will

be 40 feet from curb to curb.  The total project length is approximately 2200 feet; the new bridge length

Route:	CR 528	Structure No.:	1506006

Project ID No.:	NS9309

Municipality:	Brick Twp.	Mantoloking Boro

Project Start Date:	7/17/2002

Programmed:	$3,023,042

Expended:	$3,023,042

Status:

County awarded design contract on June 19, 2002 to HNTB in amount of $ 1,682,000.00.The County

designated $ 800,000.00 of Bridge Bond funds to acquire necessary right of way. The Department on

August  6, 2003 obtained FHWA authorization construction funding in the amount of $ 21 million

dollars, ( Federal funds). This consisted of $ 11 million from the FY 2003 Capital Program and advance

construction of $ 10 million from the FY 2004 Program. Construction award date is 10/15/03 in the

amount of $ 21,417,611.96 to JH Reid . Project construction completed and ceremony held 6/26/06 to

Meadow Avenue Bridge, Cedar Bridge Avenue

Project Description

This project will proivde for the replacement of the existing bridge over the South Branch of the

Metedeconk River as well as the roadway approaches.

Route:	Structure No.:	1514006

Project ID No.:	BOCE03

Municipality:	Lakewood Twp.

Project Start Date:	11/25/2002

Programmed:	$1,368,000

Expended:	$1,368,000

Status:

County awarded a construction contract to Rencor, Inc on 11/6/02. Bridge is included in County Route

528 reconstruction project. Construction contrat award amount is $ 2,956,969.45. Bridge Bond share is

1,368,000.00. Completion date is 8/28/04.

Summary for 'COUNTY' =  Ocean (6 detail records)

Sum	Programmed:	$9,690,001.00

Expended:	$9,690,000.54

Passaic

Belmont Avenue and Prospect Avenue Bridges

Project Description

This project will provide for the replacement of the Belmont Avenue structure over Meadow Brook as

well as the Prospect Avenue structure over Meadow Brook.

Structure Nos.:  1600158, 1600363

Route:	Structure No.:	See Description

Project ID No.:	BPAS14

Municipality:	Wanaque Boro

Project Start Date:	5/7/2001

Programmed:	$2,110,000

Expended:	$300,065

Status:

Design completed. Awaiting DEP Permit. Anticipated construction start on 8/07

Center Street and Second Street Bridges

Project Description

This project will provide for superstructure replacement and substructure repair to the Center Street

structure over Weasel Brook.  The superstructure and substructure of the Second Street structure over

Weasel Brook will also be repaired.

Structure Nos.:  1600059; 1600063

Route:	Structure No.:	See Description

Project ID No.:	BPAS02

Municipality:	Clifton City

Project Start Date:	10/23/2001

Programmed:	$1,520,000

Expended:	$1,520,000

Status:

Awarded 5/9/06. Under construction - Anticipated completion date 6/07

Clinton Road Bridge

Project Description

This project will provide for the replacement of the structure over Mossman's Brook.

Route:	Structure No.:	1600175

Project ID No.:	BPAS17

Municipality:	West Milford Twp.

Project Start Date:	6/12/2001

Programmed:	$1,874,000

Expended:	$253,563

Status:

Under design - 50% completed. Anticipated award date 6/08

Crosby Avenue Bridge

Project Description

This project will provide for superstructure replacement and substructure repair to the structure over

Molly Ann's Brook.

Route:	Structure No.:	1600476

Project ID No.:	BPAS09

Municipality:	Paterson City

Project Start Date:

Programmed:	$1,010,000

Expended:	$0

Status:

County funds will be used for this bridge. County to remove from BB list

Davidson Street and Hope Avenue Bridges

Project Description

This project will provide for superstructure replacement and substructure repair to the Davidson Street

structure and Hope Avenue structure over Weasel Brook.

Structure Nos.:  1600056; 1600057

Route:	Structure No.:	See Description

Project ID No.:	BPAS03

Municipality:	Clifton City

Project Start Date:	10/23/2003

Programmed:	$1,780,000

Expended:	$99,000

Status:

Under design 98% complete. Anticipated award date 7/07

Highland Avenue and Van Winkle Avenue Bridges

Project Description

This project will provide for superstructure replacement and substructure repair to the Highland Avenue

and Van Winkle Avenue structures over Weasel Brook.

Structure Nos.:  1600055; 1600054

Route:	Structure No.:	See Description

Project ID No.:	BPAS07

Municipality:	Passaic City

Project Start Date:	10/23/2001

Programmed:	$1,300,000

Expended:	$165,000

Status:

Design completed. Anticipated award date 5/07

Kingsland Road Bridge

Project Description

This project will provide for the replacement of the structure over Third River.

Route:	Structure No.:	1600081

Project ID No.:	BPAS05

Municipality:	Clifton City

Project Start Date:	1/9/2001

Programmed:	$740,000

Expended:	$88,486

Status:

Under design 90% complete. Anticipated award date 3/08

Magee Road Bridge

Project Description

This project will provide for the replacement of the structure over West Brook.

Route:	Structure No.:	1600404

Project ID No.:	BPAS11

Municipality:	Ringwood Boro

Project Start Date:	8/13/2001

Programmed:	$1,500,000

Expended:	$356,555

Status:

Under construction 85% completed

Osborne Terrace Bridge

Project Description

This project will provide for the replacement of the structure over Packanack Lake.

Route:	Structure No.:	1600420

Project ID No.:	BPAS15

Municipality:	Wayne Twp.

Project Start Date:	5/12/2001

Programmed:	$1,775,000

Expended:	$1,775,000

Status:

Construction completed. Awaiting final papers

Ratzer Road Bridge

Project Description

This project will provide for superstructure replacement and substructure repair to the structure over

Singac Brook.

Route:	Structure No.:	1600138

Project ID No.:	BPAS16

Municipality:	Wayne Twp.

Project Start Date:	4/24/2001

Programmed:	$815,000

Expended:	$199,482

Status:

Under design 85% complete. Anticipated award date 9/07

Skyline Lakes Drive Bridge

Project Description

This project will provide for superstructure replacement and substructure repair to the structure over

Meadow Brook.

Route:	Structure No.:	1600496

Project ID No.:	BPAS12

Municipality:	Ringwood Boro

Project Start Date:	10/23/2001

Programmed:	$630,000

Expended:	$155,000

Status:

Under design 96% complete. Anticipated award by 9/07

Warburton Road Bridge

Project Description

This project will provide for superstructure replacement and substructure repair to the structure over

Goffle Brook.

Route:	Structure No.:	1600105

Project ID No.:	BPAS06

Municipality:	Hawthorne Boro

Project Start Date:	10/23/2001

Programmed:	$1,020,000

Expended:	$137,244

Status:

Under design 80% complete. Anticipated award date 1/08

Willard Street Bridge

Project Description

This project will provide for superstructure replacement and substructure repair to the structure over Post

Route:	Structure No.:	1600143

Project ID No.:	BPAS10

Municipality:	Pompton Lakes Boro

Project Start Date:	4/13/2002

Programmed:	$550,000

Expended:	$168,692

Status:

Awarded. Anticipated start date 7/07

Summary for 'COUNTY' =  Passaic (13 detail records)

Sum	Programmed:	$16,624,000.00

Expended:	$5,218,087.00

Salem

Alloway Station Bridge

Project Description

This project will provide for the rehabilitation of the Alloway Station bridge over Alloway Creek.

Route:	CR 540	Structure No.:	1701028

Project ID No.:	BSAL03

Municipality:	Alloway Twp.

Project Start Date:	6/19/2002

Programmed:	$395,123

Expended:	$395,122

Status:

The project is complete.  Funded with BB-99 Funds.  Request the unused portion of BB-99 funds orignally

programmed to Courses Landing Bridge.

Almond Road Bridge

Project Description

This project will provide for the rehabilitation of the Almond Road bridge over Maurice River (County

structure number 1701296).

Route:	CR 540	Structure No.:	0600014

Project ID No.:	BSAL06

Municipality:	Pittsgrove Twp.	Vineland City

Project Start Date:	1/23/2001

Programmed:	$293,922

Expended:	$293,922

Status:

Design Build Project completed at $587,843 total cost, shared with Cumberland County. Salem County

used $293,922 in BB-99 funds.  Request the unused portion of BB-99 funds originally programmed be

transferred to Courses Landing Bridge.

Canton Drain Bridge

Project Description

This project will provide for the replacement of the bridge over Canton Drain.

Route:	CR 623	Structure No.:	1701364

Project ID No.:	BSAL09

Municipality:	Lower Alloways Creek Twp.

Project Start Date:	2/19/2003

Programmed:	$132,021

Expended:	$68,008

Status:

Design Consultant selected and work began. Split funding - $68,008.27 in BB-99 Funds and $64,012.73 in

83-89 BB Funds. Permits have been submitted to NJDEP for approval. Prelim. PS&E pacakge rec'd .

From consultsnt and is being reviewed. Construction will be funded with County Aid funds and award

target date is anticipated as June 2007.

Courses Landing Bridge

Project Description

This project will provide for the rehabilitation of the CR 646 bridge over Salem Creek.

Route:	CR 646	Structure No.:	1704000

Project ID No.:	BSAL08

Municipality:	Pilesgrove Twp.

Project Start Date:	5/24/2005

Programmed:	$1,370,000

Expended:	$1,673,062

Status:

Design contract was awarded for $105,971.65 using BB-99 funds. Design is complete. Construction

contract awarded for $1,571,317.00 (BB-99 funds). Construction Management awarded for $59,000

(additional BB Interest funds $30,000 to be used for Constr. Mgmt.). Project is substantially complete.

Awaiting final punchlist from consultant.

Hancock' s Bridge

Project Description

This project will provide for the rehabilitation of the existing structure, correct severe scour problems,

remove lead paint and recoat the bridge.

Route:	CR 658	Structure No.:	1701300

Project ID No.:	BSAL10

Municipality:	Pittsgrove Twp.

Project Start Date:	6/1/2003

Programmed:	$500,000

Expended:	$565,984

Status:

Design and Construction Management using BB-99 funds ($115,924). Construction Contract awarded for

$1,036,068.00 plus CO#2 for $9,000.00. Total costs = $1,160,992.28 using BB-99 funds of

$458,550.36 and $484,024 in FY 2000 Bridge Rehab. & Interest earned ($218,417.92) on BB-99 & FY

'00 Bridge Rehab. Funds. Contract 98% complete. Second contract for Steel Repairs ($238,000) issued for

$224,926.98; BB-99 funds $114,926.98 and balance paid using County Funds.

Husted Station-Palatine Road Bridge/Hawks Bridge

Project Description

This project will provide for the rehabilitation of the Husted Station-Palatine Road bridge over Indian

Run and Hawk's Bridge over Salem Creek.

Structure Numbers:  1701243, 1700200

Route:	Structure No.:	See Description

Project ID No.:	BSAL05

Municipality:	Pittsgrove Twp.	Carneys Point Twp.

Project Start Date:	8/21/2002

Programmed:	$1,208,889

Expended:	$1,082,882

Status:

Design and Construction Management cost $159,777.08 (BB-99 funds). Construction contract complete

final cost =$923,104.45. This is a joint contract with Hawk's Bridge.  Request the unused portion of BB-

99 funds originally programmed be transferred to Long Bank Bridge.

Long Bank Bridge

Project Description

This project will provide for the replacement of the CR 658 bridge over Long Bank Creek.

Route:	CR 658	Structure No.:	1701320

Project ID No.:	BSAL07

Municipality:	Lower Alloways Creek Twp.

Project Start Date:	9/1/2005

Programmed:	$1,764,478

Expended:	$1,487,029

Status:

Feasibility Study complete ($49,522 BB-99 funds). Design contract awarded ($147,403 BB-99 funds).

Construction contract awarded for $1,310,913 using $1,154,316.12 in BB-99 Funds, balance from

County Aid Funds. Construction management contract awarded for $129,394. CO#1 for $6,652.74 and

CO#2 for $570.00 using BB-99 Funds. Construction contract complete final cost - $1,318,135.74 using -

$1,161,538.86 in BB-99 Funds; $54,719.13 in BB Interest and $101,877.75 in 2000 County Aid Funds.

Witt Road Bridge

Project Description

This project will provide for the deck replacement on the Witt Road bridge over Alloway Creek.

Route:	Structure No.:	1701073

Project ID No.:	BSAL04

Municipality:	Alloway Twp.

Project Start Date:	12/1/1999

Programmed:	$335,567

Expended:	$335,566

Status:

Construction Management - $36,709.23.  Construction - $298,856.84.  The project is complete using

BB-99 Funds.  Request the unused portion of BB-99 funds originally programmed be transferred to Long

Summary for 'COUNTY' =  Salem (8 detail records)

Sum	Programmed:	$6,000,000.00

Expended:	$5,901,574.89

Somerset

Bunn Road Bridge

Project Description

The existing bridge over the North Branch of the Raritan River will be replaced with a new single-span

structure.  The new structure will be 30-feet wide and 58 feet long, and will provide two travel lanes.

Route:	Structure No.:	18D1103

Project ID No.:	BSOM10

Municipality:	Bedminster Twp.

Project Start Date:	12/17/2001

Programmed:	$595,000

Expended:	$595,000

Status:

Construction completed

Chimney Rock Road Bridge

Project Description

The existing structure over Middle Brook will be rehabilitated or replaced with a new single-span structure.

The new structure will be 40-feet wide, 40-foot long and will provide two travel lanes.

Route:	Structure No.:	18G0812

Project ID No.:	BSOM01

Municipality:	BridgewaterTwp.

Project Start Date:	7/8/2002

Programmed:	$830,000

Expended:	$830,000

Status:

Construction completed

Coriell Drive Bridge

Project Description

The existing structure over Chambers Brook will be replaced with a new structure per AASHTO standards.

Route:	Structure No.:	18F1008

Project ID No.:	BSOM04

Municipality:	Bridgewater Twp.

Project Start Date:	3/11/2002

Programmed:	$348,000

Expended:	$348,000

Status:

Construction completed.

East High Street Bridge

Project Description

The existing structure over Peter's Brook will be rehabilitated/replaced with a single-span, 60-foot wide

structure that will provide for two travel lanes.

Route:	Structure No.:	18F0803

Project ID No.:	BSOM06

Municipality:	Somerville Boro

Project Start Date:	7/1/2003

Programmed:	$909,971

Expended:	$909,971

Status:

Construction completed

Griggstown Causeway

Project Description

The existing structure over the Millstone River will be replaced with a new structure in accordance with

AASHTO standards.

Route:	CR 632	Structure No.:	18F0302

Project ID No.:	BSOM07

Municipality:	Franklin Twp.	Montgomery Twp.

Project Start Date:	8/1/2003

Programmed:	$2,432,029

Expended:	$1,281,561

Status:

Construction completed

Grove Street Bridge

Project Description

The existing structure over Stony Brook will be replaced with a single-span structure.  The new structure

will be 42 feet long and 50 feet wide and will provide two travel lanes.

Route:	Structure No.:	18M1006

Project ID No.:	BSOM02

Municipality:	North Plainfield Boro

Project Start Date:	8/1/2003

Programmed:	$1,767,127

Expended:	$1,287,748

Status:

Construction completed.

Holland Avenue Bridge

Project Description

The existing structure over Peapack Brook will be replaced with a single-span structure.  The new

structure will be 40 feet long and 42 feet wide and will provide for two travel lanes.

Route:	Structure No.:	18E1313

Project ID No.:	BSOM08

Municipality:	Peapack-Gladstone Boro

Project Start Date:	6/1/2003

Programmed:	$725,000

Expended:	$725,000

Status:

Construction completed

Mine Brook Road Bridge

Project Description

The existing structure over the Dead River will be replaced with a single-span.  The new structure will be

20 feet long and 34 feet wide and will provide for two travel lanes.

Route:	Structure No.:	18G1109

Project ID No.:	BSOM05

Municipality:	Bernards Twp.

Project Start Date:	11/1/2003

Programmed:	$800,000

Expended:	$466,000

Status:

Construction completed

Montgomery Road Bridge (B0405)

Project Description

The existing structure over a tributary of the Neshanic River will be replaced with a single span that will

be 59 feet long and 36 feet wide.

Route:	Structure No.:	18B0405

Project ID No.:	BSOM14

Municipality:	Hillsborough Twp.

Project Start Date:	10/1/2001

Programmed:	$880,000

Expended:	$880,000

Status:

Construction completed.

Opie (River) Road Bridge

Project Description

The existing structure over the South Branch of the Raritan River will be replaced with a two-span

structure.  The new structure will be 85 feet long and 34 feet wide and will provide for two travel lanes.

Route:	Structure No.:	18C0605

Project ID No.:	BSOM13

Municipality:	Brancburg Twp.	Hillsborough Twp.

Project Start Date:	4/1/2001

Programmed:	$1,433,873

Expended:	$1,433,873

Status:

Construction completed. Project closed.

Pleasantview Road Bridge

Project Description

The existing structure over Royce Brook will be replaced with a single-span structure.  The new structure

will be 23 feet long and 40 feet wide and will provide for two travel lanes.

Route:	Structure No.:	18D0501

Project ID No.:	BSOM11

Municipality:	Hillsborough Twp.

Project Start Date:	11/25/2002

Programmed:	$450,000

Expended:	$450,000

Status:

Construction completed.

River Road Bridge, Bedminster/Readington

Project Description

The existing structure over the Lamington River will be replaced with a single-span structure.  The new

structure will be 80 feet long and 30 feet wide and will provide for two travel lanes.

Route:	Structure No.:	18C1001

Project ID No.:	BSOM12

Municipality:	Bedminster Twp.	Readington Twp.

Project Start Date:	6/1/2003

Programmed:	$860,000

Expended:	$860,000

Status:

Construction completed.

River Road Bridge, Rocky Hill/Montgomery

Project Description

The existing structure over Van Horn Brook will be replaced with a single-span structure according to

AASHTO standards.

Route:	Structure No.:	18E0104

Project ID No.:	BSOM09

Municipality:	Rocky Hill Boro	Montgomery Twp.

Project Start Date:	11/1/2003

Programmed:	$2,113,000

Expended:	$2,113,000

Status:

Construction completed

Shore Drive Bridge

Project Description

The existing structure over Chambers Brook will be replaced with a single-span structure according to

AASHTO standards.

Route:	Structure No.:	18F1007

Project ID No.:	BSOM03

Municipality:	Bridgewater Twp.

Project Start Date:

Programmed:	$449,000

Expended:	$449,000

Status:

Construction completed.

Summary for 'COUNTY' =  Somerset (14 detail records)

Sum	Programmed:	$14,593,000.00

Expended:	$12,629,153.00

Sussex

Franklin Avenue Bridge (E-060)

Project Description

This project will provide for the replacement of the structure over Wallkill River.  Work will include

scoping, permits, final design and construction.

Route:	CR 631	Structure No.:	1900E06

Project ID No.:	BSUS02

Municipality:	Franklin Boro

Project Start Date:	4/1/2002

Programmed:	$473,100

Expended:	$173,020

Status:

Under design. Anticipated construction cost $300,000. Anticipated construction start by 11/07

Fredon Stillwater Road Bridge (S-01)

Project Description

This project will provide for the replacement of the structure over the Paulinskill River.  Work will

include scoping, permits, final design and construction.

Route:	CR 610	Structure No.:	1900S01

Project ID No.:	BSUS07

Municipality:	Stillwater Twp.

Project Start Date:	10/17/2004

Programmed:	$1,704,605

Expended:	$1,704,605

Status:

Under construction. 98% complete

Gingerbread Castle Road Bridge (H9-01)

Project Description

This project will provide for the replacement of the structure.  Work includes scoping, permits, final

design and construction.

Route:	Structure No.:	1900H91

Project ID No.:	BSUS08

Municipality:	Hamburg Boro

Project Start Date:	11/7/2002

Programmed:	$553,031

Expended:	$553,031

Status:

Under construction 95% complete

Halsey Myrtle Grove Road Bridges (H16 and H17)

Project Description

This project will provide for the replacement of the structure over the Paulinskill River.  Work will

include scoping, permits, final design and construction.

Route:	CR 626	Structure No.:	1900H16

Project ID No.:	BSUS04

Municipality:	Hampton Twp.

Project Start Date:	6/1/2001

Programmed:	$127,467

Expended:	$127,467

Status:

Construction completed. To close w/other BB projects

Hillside Terrace Bridge (B02)

Project Description

This project will provide for the replacement of the structure over Culver Creek.  Work will include

scoping, permits, final design and construction.

Route:	Structure No.:	1900B02

Project ID No.:	BSUS01

Municipality:	Branchville Boro

Project Start Date:	10/17/2001

Programmed:	$403,815

Expended:	$403,815

Status:

Construction completed 12/22/05. To close out w/other BB projects

Lake Drive Bridge C-13

Project Description

This project will provide for the replacement of a bridge that was washing out during the Storm of 2000.

Work will include scoping, design and construction.

Route:	Structure No.:	1900C13

Project ID No.:	BSUS10

Municipality:	Byram Twp.

Project Start Date:	10/1/2001

Programmed:	$464,028

Expended:	$464,028

Status:

Construction completed. To close out w/other BB projects

Montague Clove Road Bridge (M16)

Project Description

This project will provide for the replacement of the structure over Mill Brook.  Work will include

scoping, permits, final design and construction.

Route:	CR 635	Structure No.:	1900M16

Project ID No.:	BSUS06

Municipality:	Montague Twp.

Project Start Date:	12/11/2001

Programmed:	$582,700

Expended:	$167,700

Status:

Under design. Anticipated construction by 11/07

Morris Lake Road Bridge Q-10

Project Description

This project will provide for the replacement of a bridge that was washed out during the Storm of 2000.

Work will include scoping, design and construction.

Route:	Structure No.:	1900Q10

Project ID No.:	BSUS11

Municipality:	Sparta Twp.

Project Start Date:	10/1/2001

Programmed:	$783,800

Expended:	$783,800

Status:

Construction completed. Will close w/other BB projects

Newton Swartswood Road Bridge (H-03)

Project Description

This project will provide for the replacement of the structure over the Paulinskill River.  Work will

include scoping, permits, final design and construction.

Route:	CR 622	Structure No.:	1900H03

Project ID No.:	BSUS03

Municipality:	Hampton Twp.

Project Start Date:	10/17/2001

Programmed:	$562,726

Expended:	$76,107

Status:

Under design. Anticipated award by 11/07

Station Road Bridge (Q-08)

Project Description

This project will provide for the replacement of a bridge that was washed out during the Storm of 2000.

Work will include scoping, design and construction.

Route:	Structure No.:	Q08

Project ID No.:	BSUS09

Municipality:	Sparta Twp.

Project Start Date:	10/1/2001

Programmed:	$344,728

Expended:	$344,728

Status:

Construction completed. Will close w/other BB projects

Summary for 'COUNTY' =  Sussex (10 detail records)

Sum	Programmed:	$6,000,000.00

Expended:	$4,798,301.00

Union

Eastman Street Bridge

Project Description

This project will provide for the replacement of the structure over Rahway River.

Route:	Structure No.:	2003008

Project ID No.:	BUNI03

Municipality:	Cranford Twp.

Project Start Date:	7/28/2004

Programmed:	$1,450,000

Expended:	$1,317,117

Status:

Construction complete.

Goodman's Crossing Bridge

Project Description

This project will provide for the replacement of the structure over Robinsons Branch of Rahway River.

Route:	Structure No.:	2002027

Project ID No.:	BUNI01

Municipality:	Clark Twp.

Project Start Date:	3/15/2003

Programmed:	$830,000

Expended:	$652,274

Status:

Construction complete.

Jefferson Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Robinson Branch of Rahway River.

Route:	Structure No.:	2013008

Project ID No.:	BUNI07

Municipality:	Rahway City

Project Start Date:	12/12/2003

Programmed:	$1,300,000

Expended:	$869,546

Status:

Construction complete

Liberty Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Elizabeth River.

Route:	Structure No.:	2007020

Project ID No.:	BUNI05

Municipality:	Hillside Twp.

Project Start Date:	7/27/2004

Programmed:	$950,000

Expended:	$2,690,356

Status:

Construction complete.

Snyder Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Passaic River.

Route:	Structure No.:	2001001

Project ID No.:	BUNI10

Municipality:	Berkeley Heights Twp.	Chatham Twp.

Project Start Date:	10/22/2001

Programmed:	$400,000

Expended:	$265,296

Status:

Construction complete.

South Street Bridge

Project Description

This project will provide for the replace of the structure over Salt Brook.

Route:	Structure No.:

Project ID No.:	BUNI11

Municipality:	New Providence Boro

Project Start Date:	7/23/2003

Programmed:	$375,000

Expended:	$375,000

Status:

Construction complete.

Springfield Avenue Bridge

Project Description

This project will provide for the replacement of the structure over Rahway River.

Route:	Structure No.:	2003072

Project ID No.:	BUNI04

Municipality:	Cranford Twp.

Project Start Date:	10/17/2002

Programmed:	$1,675,000

Expended:	$1,491,571

Status:

Construction is 100% complete.

Union Avenue Bridge over Elizabeth River

Project Description

This project will provide for the replacement of the structure over Elizabeth River.

Route:	Structure No.:	2019040

Project ID No.:	BUNI09

Municipality:	Union Twp.

Project Start Date:

Programmed:	$1,200,000

Expended:	$594,911

Status:

Construction complete.

Union Avenue Bridge over Green Brook

Project Description

This project will provide for the replacement of the structure over Green Brook.

Route:	Structure No.:	2016059

Project ID No.:	BUNI08

Municipality:	Scotch Plains Twp.

Project Start Date:	2/3/2003

Programmed:	$1,000,000

Expended:	$618,400

Status:

Construction complete

Valley Road Bridge

Project Description

This project will provide for the replacement of the structure over Rahway River.

Route:	Structure No.:	2002005

Project ID No.:	BUNI02

Municipality:	Clark Twp.

Project Start Date:	11/6/2002

Programmed:	$1,858,000

Expended:	$1,924,829

Status:

Construction complete.  Balance of funding will be provided through Bridge Bond balances from other

projects within this county.

Watchung Avenue/River Road Bridge (See also Morris Cty.

portion)

Project Description

This project will provide for the replacement of the structure over Passaic River.

Route:	Structure No.:	1400515

Project ID No.:	BMOR01B

Municipality:	Summit City	Chatham Boro

Project Start Date:	7/1/2001

Programmed:	$1,000,000

Expended:	$1,092,384

Status:

Construction complete.  Balance of funding will be provided through Bridge Bond balances from other

projects within this county.

Summary for 'COUNTY' =  Union (11 detail records)

Sum	Programmed:	$12,038,000.00

Expended:	$11,891,684.00

Warren

County Route 602 Bridge (CB 04053)

Project Description

This project will provide for the rehabilitation of the arch over Blair Creek.

Route:	CR 602	Structure No.:	2100453

Project ID No.:	BWAR02

Municipality:	Blairstown Twp.

Project Start Date:	6/1/2003

Programmed:	$250,000

Expended:	$224,421

Status:

45,750 BB funds for design

County Route 605 Bridge (CB 13006)

Project Description

This project will provide for the replacement of the structure over a tributary of the Delaware River.

Route:	CR 605	Structure No.:	2101306

Project ID No.:	BWAR06

Municipality:	Knowlton Twp.

Project Start Date:	4/1/2003

Programmed:	$407,888

Expended:	$407,888

Status:

$57,841.25 BB funds for design. Project is complete.

County Route 633 Bridge (CB 05087)

Project Description

This project will provide for the replacement of the existing structure over the Pohatcong Creek.

Route:	CR 633	Structure No.:	2100587

Project ID No.:	BWAR08

Municipality:	Franklin Twp.

Project Start Date:	8/1/2003

Programmed:	$1,012,607

Expended:	$1,012,699

Status:

$146,370 BB funds for design. Project is complete

East Crisman Road Bridge (CB 04015)

Project Description

This project will provide for the rehabilitation of the arch over the Paulins Kill River.

Route:	Structure No.:	2100415

Project ID No.:	BWAR01

Municipality:	Blairstown Twp.

Project Start Date:	6/1/2003

Programmed:	$250,000

Expended:	$224,421

Status:

$45,750 BB funds for design. Project is complete

Jenny Jump Road Bridge (CB 11041)

Project Description

This project will provide for the rehabilitation of the arch over Trout Brook.

Route:	Structure No.:	2101141

Project ID No.:	BWAR03

Municipality:	Hope Twp.

Project Start Date:	4/1/2003

Programmed:	$250,000

Expended:	$224,421

Status:

$45,750 BB funds for design. Project is complete

Kings Highway Bridge (CB 16004) (See also Morris Cty. Portion)

Project Description

This project will provide for the replacement of the structure over the Musconetcong River.

Route:	Structure No.:	2101604

Project ID No.:	BWAR09A

Municipality:	Mansfield Twp.	Washington Twp.

Project Start Date:	8/1/2003

Programmed:	$700,000

Expended:	$1,008,435

Status:

This is a bi-county bridge with Warren and Morris Counties. Warren County's share is $700,000 and

Morris County's share is $700,000. $98,150 BB funds for design. Project is under construction

New Hampton Road Bridge (CB 22024)

Project Description

This project will provide for the replacement of the structure over the Musconetcong River.

Route:	Structure No.:	2102224

Project ID No.:	BWAR11A

Municipality:	Washington Twp.	Lebanon Twp.

Project Start Date:	4/1/2004

Programmed:	$700,000

Expended:	$101,066

Status:

This is a bi-county bridge.  Warren County's share is $700,000 which is being funded with Bridge Bond

funds; Hunterdon County's share is $700,000 which is being funded with county funds.  Project is under

design. $101,066 BB funds for design. Construction anticipated in August 2006

Plane Hill Road Bridge (CB 22016)

Project Description

This project will provide for the rehabiliation of the masonry arch over the Pohatcong Creek

Route:	Structure No.:	2102216

Project ID No.:	BWAR12

Municipality:	Washington Township

Project Start Date:	10/7/2002

Programmed:	$79,506

Expended:	$79,506

Status:

Completed

South Wandling Avenue Bridge (CB 21001)

Project Description

This project will provide for the replacement of the structure over Shabbecong Creek.

Route:	Structure No.:	2102101

Project ID No.:	BWAR10

Municipality:	Washington Boro

Project Start Date:	4/1/2003

Programmed:	$500,000

Expended:	$577,254

Status:

$144,857 BB funds for design. Project is complete

Stephensburg Road Bridge (CB 16006)

Project Description

This project will provide for the rehabilitation of the arch over the Musconetcong River.

Route:	Structure No.:	2101606

Project ID No.:	BWAR04

Municipality:	Mansfield Twp.

Project Start Date:	6/1/2003

Programmed:	$250,000

Expended:	$241,622

Status:

$45,750 BB funds for design. Project is complete

Stryker's Road Bridge CB 15016

Project Description

This project will provide for the replacement of the structure over Lopatcong Creek

Route:	Structure No.:	2101516

Project ID No.:	BWAR13

Municipality:	Lopatcong Twp.	Greenwich Twp.

Project Start Date:	8/1/2004

Programmed:	$800,000

Expended:	$0

Status:

This project is under design using County funds. Coordination with Lopatcong Township and Greenwich

Township road projects has slowed progress. Construction anticipated to be bid in October 2006

Wolverton Road Bridge (CB 05044)

Project Description

This project will provide for the rehabilitation, to include widening as well as a new deck, of the structure

over the Musconetcong River.

Route:	Structure No.:	2100544

Project ID No.:	BWAR07A

Municipality:	Franklin Twp.	Bethlehem Twp.

Project Start Date:	4/1/2004

Programmed:	$800,000

Expended:	$692,984

Status:

This is a bi-county bridge. Warren County's share is $800,0000 which is being funded w/bridge bond funds.

Hunterdon County's share is $800,000 which is being funded w/county funds. $98,487 BB funds for

design. Project is complete

Summary for 'COUNTY' =  Warren (12 detail records)

Sum	Programmed:	$6,000,000.00

Expended:	$4,794,716.56

Grand  Total	for all projects	Programmed	$500,000,000.00

Expended	$399,211,489.00