<Proposed Project Name>

Purpose:  The Transportation Systems Management (TSM) Limited Scope Concept Development (CD) Scope Statement lists the proposed project’s deliverables and the check-marked activities required to create those deliverables.  Depending upon the type and size of the project, the Project Manager will check-mark additional activities if required to deliver the project by customizing the CD phase using the additional activities from the CPM project delivery process.  The scope statement also provides a common understanding of the proposed project’s scope to stakeholders, subject matter experts, and the designer and lists the proposed project’s major objectives.  It enables the Project Manager to perform more detailed planning, it helps guide the design team’s work during execution, and provides the baseline for evaluating whether change requests or additional work are contained within or outside the proposed project’s boundaries.

Notes:  The TSM Limited Scope CD Scope Statement identifies the key elements of CD that are necessary to advance the proposed project to the Final Design (FD) Phase.  The TSM Limited Scope CD Scope Statement is developed by the Project Manager of Transportation Systems Management (TSM) prior to requesting the services of a consultant to perform the work.

Section 1 of the document focuses on Proposed Project Identification Information including the location, description, requirements, parameters, milestones, and recommendation/approval.

Section 2 of the document specifies the requirements for CD and is completed by the Project Manager with input (as needed) from the appropriate Subject Matter Experts (SME).

Section 1

PROPOSED PROJECT IDENTIFICATION INFORMATION

Proposed Project Specifics

| Proposed Project Name | Limits |
| --- | --- |
| NJDOT Project Manager | Director of MSE, TSM |
| Designer |  |
| Counties | Municipalities |

Additional Information

| UPC Number |  |
| --- | --- |
| DB Number |  |
| Legislative District(s) |  |
| Congressional District (s) |  |
| Route |  |
| Start Milepost |  |
| End Milepost |  |
| Alternate Route |  |
| Alternate Start Milepost |  |
| Alternate End Milepost |  |
| STIP Information |  |
| Structure Numbers |  |
| Project Classification: |  |
| MPO |  |

Proposed Project Description & Requirements

Problem Statement

Was a formal Problem Statement submitted? Yes No Date of Problem Statement: Attached Yes No Not Available.

Field Investigation

Was a Field Investigation performed? Yes No Date of Completion: Attached Yes No Not Available.

Charter Summary

Was a Charter developed? Yes No Date of Completion: Attached Yes No Not Available.

TSM Limited Scope Concept Development Deliverables

| Data Collection & Data Analysis | Environmental Documents |
| --- | --- |
| Stakeholder Input | Technical Environmental Studies |
| Traffic Data | Air Study |
| Crash Data | Noise Study |
| As-Built Plans | Ecology Study |
| Environmental Screening Report | Hazardous Waste Study |
| Purpose and Need Statement | Socio-Economic Study |
| Travel Projections | Cultural Resources Study |
| Utility Contact Letter | Section 4(f) |
| Utility Risk Assessment Plan | Individual Section 4(f) Evaluation |
| Project Fact Sheet | Programmatic Section 4(f) Evaluation |
| Scope Team Meeting Minutes | De Minimis Section 4(f) Evaluation |
| List of Substandard Design Elements | Net Benefit Section 4(f) Evaluation |
| CD Base Mapping | Executive Order 215 (E.O. 215) Document |
| ITS Needs Assessment | Environmental Commitments/Plan Sheets |
| CD Checklist | Historic Sites Council Concurrence |
|  | Categorical Exclusion Document |
|  | Certified Categorical Exclusion Document |
| Alternatives Analysis & CD Report | Contracts and Approvals |
| Concept Development Report | Final Design Designer Fee Proposal |
| Reasonable Assurance of DE Approval | Final Design Independent Cost Estimate |
| Preliminary Detour & Const. Staging Plans | Final Design Schedule |
| Preliminary Construction Cost Estimates | Final Design Budget |
| Alternatives | Notice of Authorization |
| Preliminary Preferred Alternative | Capital Program Screening Committee Recommendation |
| Final Design Scope Statement | Capital Program Committee Approval |
| CD Quality Management Certification | FHWA Approval |
| Design Communications Report |  |
| Systems Engineering Review Form |  |
| Preliminary Location Plan |  |

Schedule Milestones

Instructions: The proposed project sponsor, customer, or other stakeholders often dictate key events or major milestones affecting the completion of certain deliverables by a specified date. List key milestones and if known, associated dates that are required for the proposed project. This would include launching the proposed project by a specific date. Milestones are used in the schedule model. Traditional Concept Development Milestones: Data Collection Complete Purpose and Need Statement Complete Alternatives Analysis Select Preliminary Preferred Alternative Draft Concept Development Report Concept Development Completed Milestones for this Proposed Project (only if different):

Approval

| Name | Title | Date Approved | Comments |
| --- | --- | --- | --- |
|  | ____________________________________ Project Manager, Transportation Systems Management _____________________________________ Director of MSE, Transportation Systems Management | mm/dd/yy mm/dd/yy |  |

Section 2

TSM LIMITED SCOPE CONCEPT DEVELOPMENT SCOPE OF WORK

The intent of this scope of work is to solicit a designer man-hour estimate, cost proposal and project schedule for Concept Development for this proposed project.  This document will provide the starting point for discussions with the designer. The designer will perform the tasks associated with Concept Development as so marked, in preparation for Final Design. The Project Manager of TSM will review the proposal and lead the negotiations of the scope, budget and schedule. The Project Manager will execute a Task Order and instruct the designer to begin work. The Division of Mobility & Systems Engineering (MSE) will direct the proposed project. The Project Manager shall amend the “Responsible Unit” section if necessary, and will describe the breakdown of the work effort in the “Comments” section if more than one responsible unit is identified for a single activity.

# Concept Development

Initiate Concept Development

| Activity No. | Activity Name | Execute | Responsible Unit | Comments |
| --- | --- | --- | --- | --- |
| 2005 | Review Problem Statement Package | Yes No | TSM Designer |  |
| 2010 | Review Problem Screening Report | Yes No | TSM Designer |  |
| 2015 | Obtain Management Systems Input | Yes No | TSM SMEs |  |
| 2020 | Determine Mapping Level and Resources Required | Yes No | TSM SME |  |
| 2025 | Obtain Stakeholder Input | Yes No | TSM Designer SME |  |
| 2030 | Develop Community Profile | Yes No | TSM Designer |  |
| 2035 | Prepare CD Public Involvement Action Plan | Yes No | TSM Designer CCR |  |
| 2040 | Develop CD Scope Statement | Yes No | TSM |  |
| 2045 | Create CD Schedule | Yes No | TSM OSBM |  |
| 2050 | Develop CD Fee Proposal | Yes No | TSM Designer |  |
| 2055 | Update PRS | Yes No | TSM |  |
| 2060 | Execute CD Task Order | Yes No | TSM |  |
| 2065 | Start Design Communications Report | Yes No | TSM Designer |  |
| 2275 | Tier Assignment (COAST) | Yes No | TSM Designer |  |

Perform Data Collection

| Activity No. | Activity Name | Execute | Responsible Unit | Comments |
| --- | --- | --- | --- | --- |
| 2100 | Conduct Traffic Counts | Yes No | TSM Designer TSSE Data Development | Only necessary if traffic count data is not already available (e.g., Pavement Recommendation Report). |
| 2105 | Perform Supplemental Data Collection | Yes No | TSM Designer | Additional data collection may be necessary based on project type. |
| 2110 | Forecast Travel Projections | Yes No | TSM Designer | Only necessary if travel projections are not already available (e.g., Pavement Recommendation Report). |
| 2115 | Prepare CD Mapping | Yes No | TSM Designer |  |
| 2120 | Conduct Field Inventory of Physical Conditions | Yes No | TSM Designer | Complete the appropriate CD Checklist while conducting the field inventory. |
| 2125 | Identify Substandard Design Elements | Yes No | TSM Designer |  |
| 2130 | Coordinate with Local Officials | Yes No | TSM Designer CCR |  |
| 2135 | Perform Environmental Screening | Yes No | TSM Designer BLAES |  |
| 2140 | Review Environmental Screening | Yes No | BLAES |  |
| 2145 | Obtain Maps for SWM Rules Compliance | Yes No | TSM Designer |  |
| 2150 | Prepare Drainage Area Maps | Yes No | TSM Designer |  |
| 2155 | Send Utility Contact Letter | Yes No | TSM Designer |  |
| 2160 | Validate and Compare with Regional Model | Yes No | TSM Designer |  |
| 2170 | Obtain Crash Records | Yes No | TSM BSP |  |
| 2175 | Prepare Utility Risk Assessment Plan | Yes No | TSM Designer |  |

Perform Data Analysis

| Activity No. | Activity Name | Execute | Responsible Unit | Comments |
| --- | --- | --- | --- | --- |
| 2200 | Prepare Crash Analysis and Crash Diagram | Yes No | TSM Designer | Only necessary if substandard design elements are identified. |
| 2205 | Conduct Existing Traffic Analysis | Yes No | TSM Designer |  |
| 2210 | Conduct Scour and Seismic Retrofit Analysis | Yes No | Structural Design Designer |  |
| 2215 | Complete CD Checklist | Yes No | TSM Designer |  |
| 2230 | Conduct Hydrologic and Hydraulic Analysis | Yes No | TSM Designer BLAES |  |
| 2235 | Conduct ITS Needs Assessment | Yes No | TSM Designer |  |
| 2240 | Prepare Project Fact Sheet | Yes No | TSM Designer |  |
| 2250 | Prepare Draft Purpose and Need Statement | Yes No | TSM Designer BLAES |  |
| 2260 | Hold Scope Team Meeting | Yes No | TSM Designer | Only necessary if issues identified during field inventory require further discussion. |
| 2270 | Hold Initial Local Officials Briefing | Yes No | TSM Designer CCR |  |
| 2280 | Complete Purpose and Need Statement | Yes No | TSM Designer |  |

Perform Alternatives Analysis & Select Preliminary Preferred Alternative

| Activity No. | Activity Name | Execute | Responsible Unit | Comments |
| --- | --- | --- | --- | --- |
| 2300 | Develop Alternatives | Yes No | TSM Designer |  |
| 2310 | Obtain Stakeholder Input on Developed Alternatives | Yes No | TSM Designer CCR |  |
| 2315 | Prepare Railroad Agreement | Yes No | TSM Designer |  |
| 2320 | Develop Preliminary Detour and Construction Staging Plans | Yes No | TSM Designer |  |
| 2325 | Initiate OIT/IT Coordination | Yes No | TSM Designer |  |
| 2330 | Perform Impact Assessment | Yes No | TSM Designer |  |
| 2340 | Develop Preliminary Construction Cost Estimates | Yes No | TSM Designer |  |
| 2350 | Conduct Proposed Traffic Analysis | Yes No | TSM Designer |  |
| 2360 | Obtain Reasonable Assurance of Design Exception Approval | Yes No | TSM Designer QMS BSP | Activity is only applicable when existing structures are involved. |
| 2365 | Perform SWM Analysis | Yes No | TSM Designer Geotechnical Unit BLAES |  |
| 2380 | Prepare Alternatives Matrix | Yes No | TSM Designer |  |
| 2410 | Obtain SME Input | Yes No | TSM Designer |  |

Prepare Concept Development Report

| Activity No. | Activity Name | Execute | Responsible Unit | Comments |
| --- | --- | --- | --- | --- |
| 2500 | Perform PPA Constructability Review | Yes No | DPM Construction Mgmt. Designer |  |
| 2510 | Confirm Environmental Document | Yes No | TSM BLAES |  |
| 2515 | Prepare PE Public Involvement Action Plan | Yes No | TSM Designer CCR |  |
| 3170 | Prepare FD Scope Statement | Yes No | TSM Designer SMEs |  |
| 2530 | Develop Project Management Plan | Yes No | TSM Designer |  |
| 2535 | Prepare Systems Engineering Review Form (SERF) | Yes No | TSM Designer Traffic Operations |  |
| 2540 | Prepare CD ROW and Access Impact Plan & Matrix | Yes No | TSM Designer |  |
| 2550 | Prepare CD ROW and Access Cost Estimate | Yes No | ROW TSM Designer |  |
| 2560 | Complete CD Quality Certification | Yes No | Designer |  |
| 2570 | Prepare Draft CD Report | Yes No | TSM Designer |  |
| 2580 | Review Draft CD Report & Address Comments | Yes No | TSM Designer |  |

Obtain Concept Development Approvals/Select Preliminary Engineering Designer

| Activity No. | Activity Name | Execute | Responsible Unit | Comments |
| --- | --- | --- | --- | --- |
| 2600 | FHWA Reviews and Approves CD Report | Yes No | FHWA | For PODI Projects Only |
| 2610 | Present to CPSC | Yes No | TSM |  |
| 2620 | CPC Approves Advancement | Yes No | CPC |  |
| 2630 | Finalize CD Report | Yes No | TSM Designer |  |
| 3870 | Prepare Categorical Exclusion Document | Yes No | BLAES Designer | Necessary if preparing a CED. |
| 3875 | NJDOT Reviews and Approves CED | Yes No | BLAES | Necessary if preparing a CED. |
| 3890 | Prepare Certified Categorical Exclusion Document | Yes No | BLAES | Necessary if preparing a Certified CED. |
| 3900 | Review and Approve Certified Categorical Exclusion Document | Yes No | BLAES | Necessary if preparing a Certified CED. |
| 2640 | Complete CD Closeout | Yes No | TSM |  |
| 2700 | Prepare Solicitation Package | Yes No | TSM |  |
| 2710 | Form Technical Evaluation Committee | Yes No | TSM |  |
| 2720 | Receive Technical Proposals | Yes No | Procurement TSM |  |
| 2730 | Score Proposals | Yes No | Tech. Committee |  |
| 2740 | Hold Oral Presentations (2-Step) | Yes No | Procurement Tech. Committee Prospective Designers |  |
| 2750 | Select Designer | Yes No | CSC TSM |  |
| 3230 | Develop FD Designer Fee Proposal | Yes No | Designer |  |
| 3235 | Develop FD Independent Cost Estimate | Yes No | TSM OSBM |  |
| 2820 | Negotiate Contract | Yes No | TSM Designer |  |
| 2830 | Finalize Proposal | Yes No | Designer |  |
| 2840 | Prepare Draft Agreement | Yes No | TSM |  |
| 3240 | Create FD Schedule | Yes No | TSM OSBM |  |
| 3250 | Approve FD Schedule | Yes No | TSM OSBM |  |
| 3255 | Develop FD Budget | Yes No | TSM OSBM |  |
| 3260 | Finalize FD Budget | Yes No | TSM |  |
| 3265 | Approve FD Budget | Yes No | TSM OSBM |  |
| 3270 | Authorize Final Design | Yes No | TSM CIPD |  |
| 2890 | Execute Designer Agreement | Yes No | TSM DAG |  |

Additional Activities Necessary for Limited Scope Concept Development

(Please fill in any additional activities from the Preliminary Engineering Phase that are necessary to complete the Limited Scope Concept Development Phase. Add additional lines if necessary.)

| Activity No. | Activity Name | Execute | Responsible Unit | Comments |
| --- | --- | --- | --- | --- |