## HiddenData (hidden)
Index | Group | Project | Consultant | Agreement | AgreementDate | ModAddCode | ModAddDate | ProgressRptDate | NTPDate | PreRptDueDate | FinalRptDueDate | AuthTimeExtDate | SubmissionNum | PDFCDRecByStateDate | WorkFilesCDRecByStateDate | DBCDRecByStateDate | FinalInvRecByStateDate | OnSysFedJobNum | OnSysStateJobNum | OffSysfedJobNum | OffSysStateJobNum | NonSysFedjobNum | NonSysStateJobNum | InspType | Route | StructNum | System | PrevInspDate | AppInspDate | ActInspDate | IniPdiSubDate | Pre90PdiDate | AppPreRptDate | ActPreRptRevDate | StateComDate | FinalPdiSubDate | FinalRptRecDate | EuipMotDivSer | Remarks | OnSysFieldEstHrs | OnSysCalcEstHrs | OnSysRptEstHrs | OffSysFieldEstHrs | OffSysCalcEstHrs | OffSysRptEstHrs | NonSysFieldEstHrs | NonSysCalcEstHrs | NonSysRptEsthrs | OnSysFieldComp | OnSysCalcComp | OnSysRptComp | OffSysFieldComp | OffSysCalcComp | OffSysRptComp | NonSysFieldComp | NonSysCalcComp | NonSysRptComp | UniqueKey | OnSysRowNum | OffSysRowNum | NonSysRowNum | TotalOnSysRows | TotalOffSysRows | TotalNonSysRows | TotalProjectSchRows
1 | GGGG | 1 On and 1 Off System State Bridges | ABC Consultants | 2011BIxxxx | 0 | 00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Regular | 99 | 9999998 | Off System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 9 | 15.5 | 16 | 0 | 15.5 | [12 empty] | GGGG_9999998_Regular Off System_1 | 1 | 1 |  | 1 | 1 | 1 | 2
2 | GGGG | 1 On and 1 Off System State Bridges | ABC Consultants | 2011BIxxxx | 0 | 00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Regular | 99 | 9999999 | On System | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 9 | 15.5 | [15 empty] | GGGG_9999999_Regular On System_2 | 1 |  |  | 1 | 1 | 1 | 2

## ProjectSchedule
New Jersey Department of Transportation | [6 empty] | PROJECT SCHEDULE V3.0.1 |  |  |  | Bridge
Structural Evaluation Unit | [6 empty] | (To be submitted every 6 months, March & September, after Notice to Proceed)
Project* |  | 1 On and 1 Off System State Bridges | [8 empty] | FOR STATE USE ONLY
Consultant* |  | ABC Consultants | [5 empty] | *Notice to Proceed Date |  |  | PDF CD Received by State
Agreement* |  | 2011BIxxxx |  | *Agreement Date |  |  | *Preliminary Reports Due Date |  |  |  | Working Files CD Received by State
Group* |  | GGGG | *Modification/Addendum Code |  |  | 00 | *Final Reports Due Date |  |  |  | Database CD Received by State
Total Rows |  | 2 | Modification/Addendum Date |  |  |  | Authorized Time Extension Date |  |  |  | Final Invoice Received by State
* Required Fields |  |  | This Progress Report Date |  |  |  | This Submission Number
Insp Type | Route | Structure Number | Previous Insp Date | Approved Inspection Date | Actual Inspection Date | Initial PDI Submission Date | Prelim. and/or 90Days PDI Sub Date | Approved Prelim. Report Submission Date | Actual Prelim. Report Received by State | State Comments Received by Consultant | Final PDI Submission Date | Final Report Received by State | Insp Equip/ MOT/ Diving Services Required | Remarks | System
A* | B* | C* | D* | E* | F | G | H | I* | J | K | L | M | N | O | P
Regular | 99 | 9999998 | 2009-06-15 | [11 empty] | 2
Regular | 99 | 9999999 | 2009-07-09 | [11 empty] | 1
Note on G6: Code 2 digits: 00 for Original Agrmt 01 for Mod 1 /Add 1 02 for Mod 2 /Add 2 and so on..
Note on J9: This section is for STATE USE ONLY. Do not enter any dates in these four field.
Note on M9: This section is for STATE USE ONLY. Do not enter any dates in these four field.

## OnSystemProgress
New Jersey Department of Transportation | [11 empty] | ON-SYSTEM PROGRESS
Structural Evaluation Unit | [11 empty] | (To be submitted every month, along with Invoice)
Project |  | 1 On and 1 Off System State Bridges | [12 empty] | Progress Report Date |  | 0
Consultant |  | ABC Consultants | [6 empty] | Notice to Proceed Date |  |  |  | 0 |  | This Submission No. | 0
Agreement |  | 2011BIxxxx |  | Agreement Date |  |  | 0 |  | Preliminary Reports Due Date |  |  |  | 0 |  | On Sys Federal Job No.
Group |  | GGGG |  | Modification/Addendum Code |  |  | 00 |  | Final Reports Due Date |  |  |  | 0 |  | On Sys State Job No.
Total OnSys Rows |  | 1 | Modification/Addendum Date |  |  |  | 0 |  | Authorized Time Extension Date |  |  |  | 0
PROJECT PROGRESS FOR |  |  |  |  | ON-SYSTEM |  | Estimated |  |  | Completed |  |  |  |  | Interim | Regular | Other
INSPECTION RELATED TASK (Field, Calculation, & Report Writing) | [6 empty] | 35.5 |  |  | 0% |  |  |  | # of Insp. | 0 | 1 | 0
Insp Type | Route | Structure Number | Field Inspection (Mobilization & Field) |  |  |  | Computation (Calculations) |  |  |  | Report Writing (Cadd, Prelim. & Final Rpts) |  |  |  | Percent Total Overall Project Completed (%) | Note1 | Note2
|  |  | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%) | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%) | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%)
A | B | C | D_Hrs | D | E | F | G_Hrs | G | H | I | J_Hrs | J | K | L | M | N | O
Regular |  | 9999999 | 11 | 30.99% |  | 0% | 9 | 25.35% |  | 0% | 15.5 | 43.66% |  | 0% | 0%
Total |  |  | 11 | 30.99% |  | 0% | 9 | 25.35% |  | 0% | 15.5 | 43.66% |  | 0% | 0%

## OffSystemProgress
New Jersey Department of Transportation | [11 empty] | OFF-SYSTEM PROGRESS
Structural Evaluation Unit | [11 empty] | (To be submitted every month, along with Invoice)
Project |  | 1 On and 1 Off System State Bridges | [12 empty] | Progress Report Date |  | 0
Consultant |  | ABC Consultants | [6 empty] | Notice to Proceed Date |  |  |  | 0 |  | This Submission No. | 0
Agreement |  | 2011BIxxxx |  | Agreement Date |  |  | 0 |  | Preliminary Reports Due Date |  |  |  | 0 |  | Off Sys Federal Job No.
Group |  | GGGG |  | Modification/Addendum Code |  |  | 00 |  | Final Reports Due Date |  |  |  | 0 |  | Off Sys State Job No.
Total OffSys Rows |  | 1 | Modification/Addendum Date |  |  |  | 0 |  | Authorized Time Extension Date |  |  |  | 0
PROJECT PROGRESS FOR |  |  |  |  | OFF-SYSTEM |  | Estimated |  |  | Completed |  |  |  |  | Interim | Regular | Other
INSPECTION RELATED TASK (Field, Calculation, & Report Writing) | [6 empty] | 31.5 |  |  | 0% |  |  |  | # of Insp. | 0 | 1 | 0
Insp Type | Route | Structure Number | Field Inspection (Mobilization & Field) |  |  |  | Computation (Calculations) |  |  |  | Report Writing (Cadd, Prelim. & Final Rpts) |  |  |  | Percent Total Overall Project Completed (%) | Note1 | Note2
|  |  | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%) | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%) | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%)
A | B | C | D_Hrs | D | E | F | G_Hrs | G | H | I | J_Hrs | J | K | L | M | N | O
Regular |  | 9999998 | 16 | 50.79% |  | 0% | 0 | 0% |  | 0% | 15.5 | 49.21% |  | 0% | 0%
Total |  |  | 16 | 50.79% |  | 0% | 0 | 0% |  | 0% | 15.5 | 49.21% |  | 0% | 0%

## NonSystemProgress
New Jersey Department of Transportation | [11 empty] | NON-SYSTEM PROGRESS
Structural Evaluation Unit | [11 empty] | (To be submitted every month, along with Invoice)
Project |  | 1 On and 1 Off System State Bridges | [12 empty] | Progress Report Date |  | 0
Consultant |  | ABC Consultants | [6 empty] | Notice to Proceed Date |  |  |  | 0 |  | This Submission No. | 0
Agreement |  | 2011BIxxxx |  | Agreement Date |  |  | 0 |  | Preliminary Reports Due Date |  |  |  | 0 |  | Non Sys Federal Job No.
Group |  | GGGG |  | Modification/Addendum Code |  |  | 00 |  | Final Reports Due Date |  |  |  | 0 |  | Non Sys State Job No.
Total NonSys Rows |  | 1 | Modification/Addendum Date |  |  |  | 0 |  | Authorized Time Extension Date |  |  |  | 0
PROJECT PROGRESS FOR |  |  |  |  | NON-SYSTEM |  | Estimated |  |  | Completed |  |  |  |  | Interim | Regular | Other
INSPECTION RELATED TASK (Field, Calculation, & Report Writing) | [6 empty] | 0 |  |  | #DIV/0! |  |  |  | # of Insp. | 0 | 0 | 1
Insp Type | Route | Structure Number | Field Inspection (Mobilization & Field) |  |  |  | Computation (Calculations) |  |  |  | Report Writing (Cadd, Prelim. & Final Rpts) |  |  |  | Percent Total Overall Project Completed (%) | Note1 | Note2
|  |  | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%) | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%) | Estimated Hours of Overall Project | Estimated Percentage of Overall Project (%) | Part of This Task Completed (%) | Part of Overall Project Completed (%)
A | B | C | D_Hrs | D | E | F | G_Hrs | G | H | I | J_Hrs | J | K | L | M | N | O
|  |  |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! |  | #DIV/0! | #DIV/0!
Total |  |  | 0 | #DIV/0! |  | #DIV/0! | 0 | #DIV/0! |  | #DIV/0! | 0 | #DIV/0! |  | #DIV/0! | #DIV/0!
Note on R8: Other includes Blank.